
The City Of GREATER GEELONG

ANNUAL REPORT 
-----------------
2019–20
CONTENTS

3INTRODUCTION


5OUR PURPOSE, VALUES AND STRATEGIC PRIORITIES


6MAYOR AND CEO MESSAGE


8THE YEAR IN REVIEW


8FAST FACTS


9OVERVIEW OF FINANCIAL PERFORMANCE


13OUR COUNCIL


13COUNCIL INFORMATION


13OUR COUNCILLORS


18OUR PEOPLE


18OUR LEADERSHIP TEAM


19OUR ORGANISATIONAL STRUCTURE


20OUR PEOPLE


21EQUAL EMPLOYMENT OPPORTUNITY


22OCCUPATIONAL HEALTH AND SAFETY


23OUR PERFORMANCE


23HOW WE PLAN


24OUR COVID-19 RESPONSE


26TRENDS IMPACTING OUR SERVICES


27COUNCIL PLAN HIGHLIGHTS FOR 2019–20


29IMPROVED HEALTH AND SAFETY OF OUR COMMUNITY


37INFORMED SOCIAL INFRASTRUCTURE AND PLANNING


41A MORE INCLUSIVE AND DIVERSE COMMUNITY


45PLANNED SUSTAINABLE DEVELOPMENT


49EFFECTIVE ENVIRONMENTAL MANAGEMENT


55VIBRANT ARTS AND CULTURE


62INTEGRATED TRANSPORT CONNECTIONS


66A THRIVING AND SUSTAINABLE ECOMONY


70GROWING OUR TOURISM AND EVENTS


74INNOVATIVE FINANCES AND TECHNOLOGY


77ORGANISATIONAL LEADERSHIP, STRATEGY AND GOVERNANCE


84GOVERNANCE


84COUNCIL INFORMATION


87AUDIT AND RISK COMMITTEE


88GOVERNANCE AND MANAGEMENT CHECKLIST


91STATUTORY INFORMATION


103PERFORMANCE STATEMENT


114CONTACT US



Council acknowledges Wadawurrung, Traditional Owners of this land, and all Aboriginal and Torres Strait Islander people who are part of the Greater Geelong community today.

INTRODUCTION
The City of Greater Geelong Annual Report 2019–20 provides a comprehensive account of our performance from 1 July 2019 to 30 June 2020. 
With a population of almost 259,000 people, the City of Greater Geelong is Victoria’s largest regional city and located 75 kilometres from Melbourne. 

Key natural features of the region include Corio Bay, the Bellarine Peninsula, the Barwon River, You Yangs Regional Park, wetlands, beautiful parklands and wildlife sanctuaries. 
[image: image1.png]VICTORIA

GREATER GEELONG

if &

258,934 77.3% 133 KM 18,850 1,300 HECTARES
019 ESTIMATED  OF HOMESHAVE OFCOASTLINE  BUSINESSES  OF WORKFORCE  PROTECTED
RESIDENT AN INTERNET LIVE INGREATER  NATURAL
POPULATION CONNECTION GEELONG HABITAT

@ @ 2 qr

/1N Rl

2.4 40 16.2% 2.66% 6.0 MILLION 2,407
AVERAGE MEDIAN AGE POPULATION POPULATION VISITORS TO ABORIGINALAND
HOUSEHOLD BORN OVERSEAS GROWTH RATE THE REGION TORRES STRAIT

SIZE (2018-19) ISLANDER PEOPLES




Employment 
While Greater Geelong has recorded strong Gross Regional Product and jobs growth in recent years, the coronavirus (COVID-19) pandemic, and associated restrictions, have interrupted this trend. 
Forecasts show that all industries have experienced job losses and reduced revenue, except healthcare and social assistance. Sectors facing the largest economic impact include tourism, hospitality, retail, personal services, professional services, education and training, arts and recreation, and construction.
Many jobs in the region are generated to service our growing population. The industries that contribute the most jobs and value-added Gross Regional Product in Greater Geelong are:

· healthcare and social assistance
· education and training

· construction

· retail trade and

· manufacturing.
Manufacturing is still an important contributor to local economic value. Job losses in the sector have slowed as high-value industries, such as advanced manufacturing, cleantech and agribusiness, have grown. 
Sectors we anticipate will experience long-term growth in Greater Geelong include tourism, specialised finance and insurance services, and creative, design and digital industries.
OUR PURPOSE, VALUES AND STRATEGIC PRIORITIES
Our community vision

By 2047, Greater Geelong will be internationally recognised as a clever and creative city-region that is forward looking, enterprising and adaptive, and cares for its people and environment.

Our purpose

Working together for a thriving community.

Our values

To deliver our purpose we will:

· respect and encourage each other

· create a healthy and safe environment for all

· embrace new ideas and better ways to work

· make people the centre of our business. 
Our 11 strategic priorities

· Improved health and safety of our community

· Informed social infrastructure and planning

· A more inclusive and diverse community

· Planned sustainable development

· Effective environmental management

· Vibrant arts and culture

· Integrated transport connections

· A thriving and sustainable economy

· Growing our tourism and events

· Innovative finances and technology

· Organisational leadership, strategy and governance.
MAYOR AND CEO MESSAGE 
On behalf of the Council and our administration, we are pleased to present the City of Greater Geelong’s Annual Report for the year ending 30 June 2020.
This report has been prepared in accordance with the relevant requirements of the Local Government Act (Vic) 1989.

Over the past 12 months, and against the backdrop of the COVID-19 pandemic, Council has made major progress towards achieving its commitments, as described in the four-year Council Plan 2018–2022 – Putting Our Community First. 

This plan guides the allocation of resources to deliver infrastructure, services and programs across the 11 strategic priorities we’ve set to lead Greater Geelong to a clever and creative future.

A generational framework to put sustainability at the centre of how we deliver services, a long-term plan to support our community with much-needed social housing, and significant investment to help build essential facilities at the core of our liveability were among key achievements in 2019–20. 

However, the COVID-19 pandemic will, without doubt, be the dominant memory of the 2019–20 financial year.

The health, wellbeing and economic impacts in Greater Geelong, like everywhere, have been profound. At the same time, the determination of our community to overcome the challenges has been remarkable.

Over four months – from March to June – the Council allocated $10.8 million through four separate support packages, committing us to deliver targeted assistance measures across a range of areas to both community members and business owners.

Our initial strategy was to provide immediate relief, but subsequent measures looked further ahead, focusing on our region’s medium-to-long-term economic and social recovery. 

We transitioned the majority of our office employees to working from home arrangements, in line with Victorian Government directions, while our frontline employees continued to deliver essential services under tight health and safety protocols.

Unfortunately, over 600 of our employees were impacted by the forced closure of facilities, but we responded with an organisation-wide redeployment program, creating 247 new roles (as at 30 June). 

Taking into account the community support measures and the impacts to our facilities and services, the COVID-19 pandemic had a direct $10.5 million effect on our 2019–20 operating result. 

Throughout these challenges, we have worked hard to progress our four-year Council Plan and the community’s 30-year clever and creative vision. 

Across the region, our $122.9 million capital works program has resulted in new family centres, sporting pavilions and changerooms, and community centres. Our keen focus has included progressing other important infrastructure such as the 50-metre swimming pool for the northern Bellarine and the Lara Recreation Reserve Masterplan.



We also endorsed several vital strategies and programs that will make a positive, long-term impact in our community. These include:

· our landmark Social Housing Plan 2020–41, which aims to increase the supply of social housing in our region by an estimated 12,000 dwellings over the next 20 years

· our Waste and Resource Recovery Strategy 2020–2030, which will transform the way we manage waste, helping us reduce the volume of material sent to landfill 

· our Shared Trails Master Plan, designed to create a fully-connected network of trails across the region over the next 10 years, and

· Greater Geelong’s first ever Reconciliation Action Plan, a proud collaboration between the City and a community working group, which included the Wadawurrung Traditional Owners.
In addition, we increased the availability of local emergency food relief by committing $1.7 million over five years, introduced a successful hard waste collection service and trialled free, 30-minute parking in all 2-hour parking spaces in Central Geelong.

And we have continued to progress our major Digital Modernisation Project to transform the organisation’s capability into the future, including flexibility and adaptability to news ways of working.

Sitting above all of these plans and projects is our new Sustainability Framework, a watershed document that will embed sustainability into all our decision-making – environmental, social, financial and governance-related.

None of this progress would have been possible without the input and passion of our very resilient community. 

We are proud to serve you and will continue to strive towards the clever and creative future our region and its people deserve. 

	[image: image2.png]



	[image: image3.jpg]




	Cr Stephanie Asher – Mayor
	Martin Cutter – Chief Executive Officer


THE YEAR IN REVIEW
FAST FACTS
We deliver a wide range of infrastructure, services and programs to the Geelong community. In 2019–20, this included: 
[image: image4.jpg]people following
Events Geelong
on social media

o
o
o

$40m

invested in new
community
infrastructure

oo0Q3)
ooo

400+

virtual and
group fitness
classes provided

>
o
106

Wi-Fi access

points for our
community

3,255

new trees planted
in our parks and
reserves

2,600

youth programs,
activities and
events facilitated

=S
1,575

planning
decisions made

273

families supported
by our Family Day
Care Program

(.

470+ km

of unsealed roads
maintained

0 oo

@)

15,533

residential
hardwaste
collections

192,040

calls to our
customer service
call centre

N
38,500

tonnes of
kerbside green
waste collected

25,297

people participated
in 2019 Tastes of
Central Geelong

Q

Q)

4,656

people assisted
by our community
care services

i
8,000+

objects from the
National Wool Museum
made available online

20b+

business and
investment enquiries





OVERVIEW OF FINANCIAL PERFORMANCE 
This is a summary of our financial results for 2019–20. 

For full details, please go to www.geelongaustralia.com.au/annualreport.
· Surplus of $85 million – decrease of $40.3 million on the previous year. The total surplus includes an operating recurrent deficit of $17.8 million and a non-recurrent surplus of $102.8 million. The non-recurrent result includes gifted assets of $89 million.

· $487.4 million revenue, with 49.6 per cent coming from rates and charges.

· $402.4 million expenditure – 40.6 per cent employee costs and 33.2 per cent materials and services.

· $2.76 billion in net assets – $251 million increase on the previous year.

· $122.9 million capital expenditure – 39.5 per cent relating to roads, foot and bike paths, and drainage; 24.4 per cent to land and buildings; and 20.7 per cent to parks and open space, as well as recreational, leisure and community facilities.

Comprehensive Income Statement

The comprehensive income statement shows how much we earned during the 2019–20 financial year. It details where we received our income and how it was spent.

Net Result 
[image: image5.png]125.3

76.0 85.0

[ ] []

2016-17 2017-18 2018-19 2019-20





FIGURE 1: Net result for 2016–17 to 2019–20 ($m)

Total Comprehensive Results


[image: image6.png]251.0
2175

156.3

66.0

2016-17 2017-18 2018-19 2019-20




FIGURE 2: Total comprehensive results for 2016–17 to 2019–20 ($m)

Recurrent Operating Results 

[image: image7.png]204

45 i (178)

2016-17 2017-18 2018-19 2019-20




FIGURE 3: Recurrent operating results for 2016–17 to 2019–20 ($m)
The $40.3 million decrease in our surplus – that is, income minus expenditure – is shown in Figure 1.
This result can be explained by: 

· grants decreasing by $10.7 million

· employee costs increasing by $8.7 million

· materials and service expenses increasing by $16.5 million

· additional amortisation, finance costs and borrowing costs of $4.4 million.

The total comprehensive result accounts for items that will not be classified to surplus or deficit in future periods. In this case, it is the net asset revaluation of land and buildings which, in 2019–20, was an increment of $166 million. 

Our Strategic Resource Plan forecasts surpluses over the next four years, including a $85.6 million surplus in 2020–21. This is a critical part of our financial strategy, as it gives us the capacity to maintain our community assets.
The total surplus of $85 million includes an operating recurrent deficit of $17.8 million and a non-recurrent surplus of $102.8 million. The non-recurrent result includes gifted assets of $89 million.
Balance Sheet

The balance sheet shows what we own (assets), what we owe (liabilities) and our net worth (equity).

Assets 

Our assets are primarily made up of:

· cash and cash equivalents of $103.4 million – used to cover our long-service leave obligations and provide funds for capital works that have been carried over

· property, plant and equipment worth $2.8 billion – an increase of $290 million on the previous year.

These asset types make up 98.5 per cent of our total assets.

Total assets 

[image: image8.png]2,962.6

2,667.8
2236.0 24715

2016-17 2017-18 2018-19 2019-20




FIGURE 4: Total assets 2016–17 to 2019–20 ($m)
Investments


[image: image9.png]105.5

103.4
103.0 1026

2016-17 2017-18 2018-19 2019-20





FIGURE 5: Investments 2016–17 to 2019–20 ($m)
Capital program

We deliver an extensive capital works program – renewing, upgrading and building assets to meet community need. 

As Figure 6 shows, our capital works expenditure in 2019–20 was $122.9 million. This included: 

· $76.4 million on new assets (62.2 per cent),

· $36.8 million on renewal works (29.9 per cent) and

· $9.7 million on upgrade works (7.9 per cent).


[image: image10.png]124.5 122.9

113.3

76.9

2016-17 2017-18 2018-19 2019-20




FIGURE 6: Capital works expenditure 2016–17 to 2019–20 ($m)
The main categories of expenditure were:

· $30 million on land and buildings

· $27 million on roads

· $16 million on drainage

· $14.3 million on recreational, leisure and community facilities

· $10.9 million on plant and equipment

· $5.6 million on foot and bike paths

· $19.1 million on other assets.
Liabilities

Our liabilities include future commitments to suppliers, employees (for leave entitlements), loans and costs associated with providing landfill.

Total liabilities

As Figure 7 shows, total liabilities were $201.3 million, an increase of 27.8 per cent on the 2018–19 balance. This increase is due to new loans financing our Civic Precinct project, grants received in advance, and the take up of new lease liabilities, in line with Australian Accounting Standards Board 16 Leases.


[image: image11.png]201.3
157.6

135.7

2016-17 2017-18 2018-19 2019-20

17.7





FIGURE 7: Total liabilities 2016–17 to 2019–20 ($m)

Loans

Our loan balance equates to 41 per cent of total liabilities, which is consistent with 2018–19 (41.2 per cent). 

The overall increase in our loan balance of $16.8 million is due to $25 million in new loans, offset by $8.2 million of debt paid off during the year.

[image: image12.png]826
65.8
455 487

2016-17 2017-18 2018-19 2019-20




FIGURE 8: Loans from 2016–17 to 2019–20 ($m)

Debt commitment

The debt commitment ratio shows the percentage of rates required to meet loan repayments for the following 12 months. 

Figure 9 shows that a low percentage of rates are being used to service loans and we have ample capacity to meet our debt repayments. The slightly higher ratio in 2019–20 was due to:
· an increase in loans of $16.8 million and 

· an increase in rates income of $11 million.
[image: image13.png]5.06 460 4.82

2016-17 2017-18 2018-19 2019-20




FIGURE 9: Debt commitment percentage 2016–17 to 2019–20 (%)
Ratepayer equity

Ratepayer equity is represented by our net worth – that is what we own ($2,962.55 million) minus what we owe ($201.35 million). 

As Figure 10 shows, ratepayer equity at 30 June 2020 was $2,761.2 million – a 10 per cent increase on the previous year. This is due to continued growth of our fixed asset base – that is, property, plant and equipment – and the impact of land and building revaluations.


[image: image14.png]2,118.3 2,335.8 2,492.1 27612

2016-17 2017-18 2018-19 2019-20




FIGURE 10: Ratepayer equity 2016–17 to 2019–20 ($m)

OUR COUNCIL
COUNCIL INFORMATION
The role of council

The Local Government Act (Vic) 1989 requires all councils to provide leadership for the good governance of the municipality and the local community. This means:

· considering the diverse needs of the local community in decision-making

· establishing strategic objectives and monitoring achievements

· managing resources in a responsible and accountable manner

· advocating local community needs to other communities and governments

· giving everyone the opportunity to participate in the democratic process and decision making that shapes our community.

OUR COUNCILLORS
Our community elected its Council for a three-year term on 28 October 2017.

Councillors set the strategic direction for the municipality, which influences policy, service standards and performance across the organisation. 

The municipality is divided into four, multiple-councillor wards (see Figure 11): 
· Bellarine Ward: three councillors
· Brownbill Ward: three councillors
· Kardinia Ward: three councillors
· Windermere Ward: two councillors.
[image: image15.png]WINDERMERE
WARD

BROWNBILL
WARD

BELLARINE
WARD

KARDINIA
WARD





FIGURE 11: Ward map of the City of Greater Geelong
KEY: Chair (C) Deputy Chair (DC) Substitute (S) 
[image: image57.jpg]PEOPLE FEEL SAFE
WHEREVER THEY ARE




Cr Stephanie Asher

Mayor

Bellarine Ward

Portfolios:

· Economic Development (C)

· Environment (DC) 

· Leadership and Governance (C)
Committees:

· Audit and Risk Advisory Committee

· Central Administrative Office Advisory Committee (C)

· CEO Employment Matters Committee (C)
· G21 Pillars - Economic Development, Environment, Geelong Region Alliance

· Regional Capitals Australia

· Regional Cities Victoria

[image: image58.jpg]AN INCLUSIVE, DIVERSE,
HEALTHY AND SOCIALLY
CONNECTED COMMUNITY



Cr Kylie Grzybek

Deputy Mayor

Windermere Ward

Portfolios:

· Finance (DC)

· Leadership and Governance (DC)

· Transport and Connections (C)
Committees:

· Audit and Risk Advisory Committee
· Central Administrative Office Advisory Committee

· CEO Employment Matters Committee

· G21 Pillar – Transport
[image: image59.jpg]SUSTAINABLE DEVELOPMENT
THAT SUPPORTS POPULATION
GROWTH AND PROTECTS THE
NATURAL ENVIRONMENT




Cr Anthony Aitken
Windermere Ward

Portfolios:

· Finance (C)

· Parks, Gardens and City Services (C)

· Waste Management (DC)
Committees:

· Access and Inclusion Advisory Committee (C)
· Central Administrative Office Advisory Committee
· CEO Employment Matters Committee

· G21 Pillar – Environment
[image: image60.png]


Cr Bruce Harwood
Kardinia Ward

Portfolios:

· Central and Civic Geelong (DC)
· Transport and Connections (DC)

· Waste Management (DC)

Committees:

· Barwon South West Waste and Resource Recovery Group Committee Forum
· Central Administrative Office Advisory Committee
· G21 Pillars – Economic Development (C), Transport
· Geelong Major Events
[image: image61.jpg]PEOPLE FEEL SAFE
WHEREVER THEY ARE




Cr Eddy Kontelj
Brownbill Ward

Portfolios:

· Central and Civic Geelong (DC)

· Environment (C) 
· Sport and Recreation (DC)

Committees:

· CEO Employment Matters Committee
· G21 Pillars – Environment, Sports and Recreation 
· Multicultural Action Plan Advisory Committee (C)
[image: image62.png]


Cr Sarah Mansfield

Brownbill Ward

Portfolios:

· Community Health, Wellbeing and Safety (DC)

· Environment (DC) 

· Social Inclusion (C)
Committees:

· G21 Pillars – Education and Training, Environment

· Karreenga Aboriginal Advisory Committee

· Women in Community Life Advisory Committee
[image: image63.jpg]A PROSPEROUS ECONOMY
THAT SUPPORTS JOBS AND
EDUCATION OPPORTUNITIES




Cr Jim Mason AM

Bellarine Ward

Portfolios:
· Arts, Culture and Heritage (DC)
· Parks, Gardens and City Services (DC)
· Planning (DC)

· Rural and Coastal (C)
Committees:

· Association of Bayside Municipalities
· Audit and Risk Advisory Committee (S)
· Central Administrative Office Advisory Committee
· CEO Employment Matters Committee
· G21 Pillars – Arts, Heritage and Culture, Planning and Services

· Geelong Regional Library Corporation

· Heritage Advisory Committee (C)
· Municipal Association of Victoria

· Geelong-Queenscliffe Coastal Adaptation Program

· Rural and Peri-Urban Advisory Committee (C)
[image: image64.jpg]A DESTINATION THAT
ATTRACTS LOCAL AND
INTERNATIONAL VISITORS




Cr Pat Murnane
Kardinia Ward

Portfolios:
· Community Health, Wellbeing and Safety (C)

· Social Inclusion (DC)

· Transport and Connections (DC)

Committees:

· Ageing Well Advisory Committee (C)
· Central Administrative Office Advisory Committee 
· G21 Pillars – Education and Training, Health and Wellbeing, Transport
[image: image65.jpg]=
A LEADER IN DEVELOPING AND

ADOPTING TECHNOLOGY




Cr Peter Murrihy

Brownbill Ward

Portfolios:

· Arts, Culture and Heritage (DC)
· Central and Civic Geelong (C)

· Economic Development (DC)

· Parks, Gardens and City Services (DC)

· Tourism and Events (DC)
Committees:

· Bellarine Multi Arts Facility (Potato Shed) 
· Central Administrative Office Advisory Committee
· Central Geelong Marketing Committee
· G21 Pillars - Arts, Heritage and Culture, Sports and Recreation

· Geelong Major Events (C)
· Geelong Regional Library Corporation
[image: image66.png]


Cr Ron Nelson
Kardinia Ward

Portfolios:

· Tourism and Events (DC)

· Sport and Recreation (C)
· Waste Management (C)

Committees:

· Central Administrative Office Advisory Committee
· G21 Pillar - Sports and Recreation

· Geelong Major Events

· Geelong Regional Library Corporation (C)
[image: image67.jpg]


Cr Trent Sullivan

Bellarine Ward

Portfolios:

· Arts, Culture and Heritage (C)
· Economic Development (DC)
· Planning (C)
· Rural and Coastal (DC)

· Tourism and Events (C)
Committees:

· Bellarine Multi Arts Facility (Potato Shed) (C)

· Central Administrative Office Advisory Committee

· Central Geelong Marketing Committee (S)
· G21 Pillars – Arts, Heritage and Culture, Economic Development, Planning and Services

· Geelong Art Gallery

· Geelong Major Events
· Geelong Regional Library Corporation

· Planning Committee (C)

· Submissions Review Panel (C)
· Tourism Greater Geelong and The Bellarine
-------------------------------------------------------------------------------------------------------------------------------
MUNICIPAL MONITORS

After being appointed for three years to oversee Council governance and administration in November 2017, our municipal monitor
, Jude Munro, resigned from her position on 31 January 2020. Our second monitor, Peter Dorling, will remain in place until the general elections in 2020. 
OUR PEOPLE

OUR LEADERSHIP TEAM
We are led by the Chief Executive Officer (CEO), who operates under the delegation of the elected Council and is responsible for our overall management and performance.  
Our Executive Leadership Team, consisting of seven directors and the CEO, are responsible for implementing Council decisions and delivering sustainable and effective services, activities and infrastructure to the community through our daily operations.
[image: image16.png]OUR LEADERSHIP TEAM

1}
|

MARTIN CUTTER MICHAEL DUGINA REBECCA LEONARD.

Chief Exacutive Director Customer Director Governancs,

Officar and Corporate Strategy and
Services Performance

-
‘ i !

BRETT LUXFORD KAARINA PHYLAND GARETH SMITH

Director Economy, Director Director Planning,

Investment and People and Culture Design and

Astraction Development

A3

ROBYN STEVENS GUY WILSON-
Diractor BROWNE
Diractor City Sarvices.

Community Life





FIGURE 12: Our leadership team as at 30 June 2020
OUR ORGANISATIONAL STRUCTURE
Our organisation is structured around seven directorates that work together to deliver a range of services, activities and infrastructure to our community. 
[image: image17.png]city

Capital
Projects

City
Works

| Emergency
Management

Engineering
Services

Environment
& Waste
Services

Parks &
Gardens

Community
Life

Community
Care

Comnected
Communities

Family
Services

Healthy
Communties

Laisure &
- Recreation
Services

Social
L Planning &
Investment

Customer &
Corporate
Services.

Business
Improvement

Civie
Accommodation

Customer
Service

Digital
Information &
Tachnology.

Financial
Service

Program
Integration &
Development

Property,
Procurement
& Assots

Economy,

Investment &

Astraction

As &
Culture.

Central
Geslong &
Waterfront

Economic
Development
& Events

Tourism

Governance,

Strategy &

Performance.

Corporate
Affirs

Enterprize
Risk

Governanca

Internal
Ombudsman

Logal
Services

Mayor &
Councilor
Support

| strategy &

Performance

People &
Culture

Businass
Partnering

Change
Management
Offics

Health,
Safety &
Welbing

People
Shared
Services

Policy &
~ Workplsce
Relations

Talent,
Capability
& Employes
Experience

Planning,
Design &
Development

city
Development

Heatth &
Local Laws

Planning &
Growth

Urban Design
&Heritage





FIGURE 13: Our organisational structure as at 30 June 2020
OUR PEOPLE
We are proud to be an inclusive and flexible organisation that is one of the largest employers in the region.

We currently employ 2,722 people – equivalent to 1,632.30 full-time employees
. Our turnover
 in 2019–20 was 8.4 per cent – up from 8.2 per cent the previous year. 

Table 1 shows a summary of full-time equivalent employees by employment type and directorate. 

TABLE 1: Total full-time equivalent employees by directorate in 2019–20

	EMPLOYEE TYPE
	CEO
	CITY SERVICES
	COMMUNITY LIFE
	CUSTOMER AND CORPORATE SERVICES
	ECONOMY, INVESTMENT AND ATTRACTION
	GOVERNANCE, STRATEGEY AND PERFORMANCE
	PEOPLE AND CULTURE
	PLANNING, DESIGN AND DEVELOPMENT

	Full-time
	6.00
	434.80
	295.10
	119.50
	56.00
	44.80
	35.10
	123.70

	Part-time
	0.00
	22.13
	317.06
	20.55
	19.50
	7.03
	6.60
	49.44

	Casual
	0.00
	5.52
	50.80
	4.45
	5.46
	0.00
	6.30
	2.46

	Total
	6.00
	462.45
	662.96
	144.50
	80.96
	51.83
	48.00
	175.60


Table 2 shows a summary of full-time equivalent employees by employment type and gender. 

TABLE 2: Gender and employment type of full-time equivalent employees

	EMPLOYEE TYPE
	MALE
	FEMALE
	TOTAL

	Full-time
	617.40
	497.80
	1,115.20

	Part-time
	64.90
	377.30
	442.20

	Casual
	22.70
	52.20
	74.90

	Total
	705.00
	927.30
	1,632.30


EQUAL EMPLOYMENT OPPORTUNITY

We are an equal opportunity employer and value the contribution a diverse workforce brings to our community. 

We recognise and respect the importance of diversity and inclusion and incorporate the principles of equal employment opportunity into our recruitment practices.
From 31 March 2021, all local councils and public sector entities will be required to undertake Gender Impact Analysis to meet the requirements of the Gender Equality Act 2020. In November 2019, we were pleased to be one of 10 local governments in Victoria asked to test the toolkit that will be used to support this process. 
In our efforts to become a gender-balanced organisation, we are guided by Ba-gurrk: A Gender Equity Framework for the Greater Geelong Region. In July 2019, Council endorsed an implementation plan to support the framework. It described the short, medium and long-term actions we’ll implement to address gender equity as a governance, community and organisational issue. 
Other plans we are currently implementing to further improve diversity and inclusion in our workplace include: 

· The City of Greater Geelong Multicultural Action Plan 2018–22
· The City of Greater Geelong Access and Inclusion Plan 2018–22 
· City of Greater Geelong Reflect Plan May 2020–May 2021.
Achieving the workplace actions described in these plans will help us build on the work we’re already doing, which includes equal opportunity training for all employees as part of their induction.   
OCCUPATIONAL HEALTH AND SAFETY

Health and safety matters to us.
Our safety management system, CitySafe, gives us the tools and processes we need to address employee, contractor and community health and safety, and is constantly being reviewed and updated. 
Using this system, we successfully reduced the frequency rates below our targets level during the 2019–20 period for ‘lost time injuries’ and ‘high potential incidents’. ‘Total recordable injuries’ – which include lost time and medical treatment injuries – ended slightly above the target level.
TABLE 3: Occupational health and safety performance in 2019–20
	
	Lost time injury frequency rate
	
	Total recordable injury frequency rate
	
	High potential incident frequency rate
	

	2018–19 Results
	27.5
	
	31.7
	
	18.9
	

	2019–20 Targets
	24.0
	
	25.0
	
	18.0
	

	2019–20 Results
	18.1
	
	25.7
	
	3.8
	

	2019–20 Variation 
	-24.6% 
	[image: image18.png]



	+2.8%
	[image: image19.png]



	-78.9%
	[image: image20.png]





COVID-19 response
Like most organisations, we were forced to rapidly adapt to new ways of working in 2020 to help prevent the spread of COVID-19. 
We moved quickly to develop systems for employees performing critical work, securing appropriate supplies to assist with hygiene and assisting those who were able to work from home.

We also worked with our employees to develop COVID Safe Risk Assessments and Safe Work Plans, which were efficiently implemented to keep our people and customers safe.
Contractor safety
We introduced a new contractor management system called LinkSafe to better protect the health and safety of contractors. 
Using LinkSafe, we have improved our general and site-specific induction processes. We can also better monitor contractor status and communicate our expectations to the contractor workforce more easily. 

Workplace injuries and reported incidents
One of our goals in 2019–20 was to reduce ‘near-miss’ incidents with a potential for serious injury or death – also known as ‘high potential incidents’. As such, we were able to reduce these incidents by almost 80 per cent (see Table 3 above). 
We also expanded our early intervention program to improve treatment of injuries sustained by employees through our In2Work program. This program gives employees priority access to general practitioners and helps address musculoskeletal injuries and discomfort through the associated physiotherapy program.
OUR PERFORMANCE
HOW WE PLAN
Planning in our organisation occurs on multiple levels, as demonstrated in Figure 14. 
[image: image21.png]STATE AND REGIONAL STRATEGIES AND PLANS

CLEVER AND CREATIVE COMMUNITY VISION

zE
£2
Bo
1
g3
&
L





FIGURE 14: Our planning framework
Council Plan 2018–22 is the key document that guides us. It translates our community’s needs and expectations into actions and establishes what we want to achieve over the term of this Council. It is supported by other important plans and strategies including: our municipal public health and wellbeing plan; social infrastructure plan; asset and land management plans; environment strategy, sustainability framework and ten-year financial plan. 
While our priorities and measures of success are set for four years, we review and update the aims every 12 months. This helps us to respond to our rapidly changing environment and keeps us on track. 

Our annual work planning and budgets are aligned to the council plan aims, in addition to the services we deliver for our community.

We also use long-term service planning to help us predict how trends like advancing technology, climate change, growth and asset renewal will impact our future delivery of services, and then identify opportunities to prepare for the future. 
OUR COVID-19 RESPONSE 
From March 2020, we took on the important task of helping our community and employees adapt to the challenges brought on by the COVID-19 pandemic. 
Thanks to the leadership of our councillors, and our team’s quick response, we were able to not only maintain vital services but, in some cases, boost them. 

Support packages
From March to June 2020, Council approved more than $10.8 million in support and recovery packages for the 2019–20 and 2020–21 financial years. The breakdown of funding support was as follows (see Figure 15):

Budgeted income foregone

· Free parking and parking permit refunds ($5.3 million)

· Reduced and refunded rent and fees for community groups and businesses ($2.73 million)  

· Rate and interest waivers ($848,000)

Expenditure

· Tourism and events campaign support ($500,000)

· Heritage, arts and culture recovery support ($490,000) 

· Extended season opening for Kardinia Pool ($300,000) 

· COVID-19 quick response grants ($250,000) 

· Initiatives to support international students ($133,000)

· Training and professional advice for local businesses ($130,000)

· Social housing support ($100,000)

· Support for food relief ($50,000)

Recognising that hardships caused by COVID-19 restrictions are a shared responsibility, Council also adopted a COVID-19 Financial Hardship Policy. This policy made financial relief available to both businesses and individuals and applied to all monies owed, with the exception of fines.

We shared information about all the support available via our website, promoting it widely. We also advertised information about financial support in 15 languages, via SBS Radio and 94.7 The Pulse. 

FIGURE 15: Greater Geelong COVID-19 support package breakdown (2019–20 and 2020–21)
[image: image68.jpg]



Emergency response

As part of our municipal emergency management responsibilities, we worked closely with other agencies to prepare for, and respond to, the impacts of COVID-19. 

We activated our Influenza Pandemic Response Plan 2020 on 11 March 2020 – the same day the World Health Organisation declared COVID-19 a pandemic. Five days later, when a State of Emergency was declared, we started developing our COVID-19 Municipal Relief and Recovery Plan.   

To minimise the potential spread of COVID-19, we closed many of our facilities a few days before government restrictions took effect. Swimming pools and leisure centres, golf courses, halls, recreation and community centres, cultural facilities, libraries and playgrounds were all impacted. 

With support from the Victorian Government, we also increased cleaning and sanitation of shopping precincts and high-use pedestrian areas, including bike racks, bench seats, bus stops and signs. 

As part of our relief and recovery efforts, we connected those in need with local community services and food relief agencies. We also carried out welfare checks on residents in isolation and doubled our written communication with our aged and disability service clients. 

Emergency response

As part of our municipal emergency management responsibilities, we worked closely with other agencies to prepare for, and respond to, the impacts of COVID-19. 

We activated our Influenza Pandemic Response Plan 2020 on 11 March 2020 – the same day the World Health Organisation declared COVID-19 a pandemic. Five days later, when a State of Emergency was declared, we started developing our COVID-19 Municipal Relief and Recovery Plan.   

To minimise the potential spread of COVID-19, we closed many of our facilities a few days before government restrictions took effect. Swimming pools and leisure centres, golf courses, halls, recreation and community centres, cultural facilities, libraries and playgrounds were all impacted. 

With support from the Victorian Government, we also increased cleaning and sanitation of shopping precincts and high-use pedestrian areas, including bike racks, bench seats, bus stops and signs. 

As part of our relief and recovery efforts, we connected those in need with local community services and food relief agencies. We also carried out welfare checks on residents in isolation and doubled our written communication with our aged and disability service clients. 

Employee redeployment
In total, over 600 permanent and casual employees were impacted by COVID-19 and the associated restrictions. To address this, we established an employee redeployment program in mid-March. By the end of the financial year, we had redeployed 247 employees through this program.  

Temporary redeployment assignments included: 

· delivering meals to our aged and disability service clients 

· supporting employee welfare

· administration

· accounting 

· tree and park management and

· cleaning and sanitation in busy areas. 

Our redeployment program received great feedback and many other regional councils looked to it as a model for their own employees. 

New ways of doing things

To keep our employees and community safe, many of our services had to be moved online, or delivered by phone. Customer and statutory planning services, council meetings and services for families, children and youth were just some of the many areas of our business we adapted to this new way of working. 

For services that couldn’t be moved online, we quickly established COVID-safe work procedures and made sure our frontline employees were given the necessary training and protective equipment. This was particularly important for our community care workers, who continued caring for over 5,000 aged and disability service clients. 

In order to help slow the spread of the virus and manage the delivery of our services, the majority of our employees worked from home from mid-March. To support them, we established flexible work policies, provided mobile devices and implemented employee health, welfare and support programs. 

To support the wellbeing of the broader community, we launched a Swim Sport & Leisure at Home online program, which included live and pre-recorded workouts, healthy recipes and general health information. The virtual fitness classes were particularly popular, receiving over 10,000 views per week at their peak. 

Other wellbeing programs we initiated include: 

· the Healthy at Home toolkit 

· the Geelong City Kids Challenge

· gardening tips from the Geelong Botanic Gardens and

· the Youth Postcard Project, which shared artwork and messages of hope from young people with clients of our delivered meals service.

Finally, with the easing of restrictions towards the end of the financial year, we supported community groups and clubs to become COVID-safe, giving advice and offering quick-response grants to help them with the transition.  
TRENDS IMPACTING OUR SERVICES

There are several factors that impact on the delivery of our services, as Table 4 shows. 

	Trend
	What it means for us
	How we need to respond

	Pandemic response and management 
	We must continue to deliver essential services and support to address the social and economic impacts of government restrictions caused by COVID-19.  
	We need to review our priorities, change how we do things and allocate resources appropriately. We must also manage the impacts on our internal workforce and long-term operational sustainability. 

	Technology
	Rapidly advancing technology shifts the world we work in.
	We need the skills and know-how to cost efficiently adopt new technology to better meet community expectations. 

	Environmental sustainability and climate change
	The community expects us to show leadership in both policy and work practice, as part of a growing global focus on climate and environmental sustainability.
	We must work with the community and stakeholders towards zero carbon emissions, better resource recovery mechanisms and protection and restoration of our natural environment. 



	Social inequity
	Some members of our community are the most at risk of social exclusion in Victoria, with the impacts of COVID-19 magnifying these risks and impacts. 
	We must apply a social equity lens to all our policies, programs and services to help us find and address barriers, and create better opportunities for all. Our responses must be deliberate, driven by data and evidence-based.  

	High growth
	We are one of the state’s fastest growing regional municipalities, so timing and sequencing of services in new growth areas is a challenge.
	We need a ‘whole-of-organisation’ effort to service, plan and deliver infrastructure for growth corridors and areas impacted by infill development. This must be balanced against maintaining service delivery in established areas.  

	Growing community and customer expectations
	Our community is seeking greater input into local decision making, as well as more responsive customer services. 


	While we prepare for our changing future, we must also manage our community’s evolving and growing expectations of the services we currently deliver, as well as those we will deliver in the future.

	Growing pressure on financial sustainability
	Cost increases, including those associated with our COVID-19 response, will have longer-term implications for our budget.
	We need to operate on a sustainable financial model and continuously improve the efficiency of our services.

	Organisational change
	We must learn to adapt to a changing work environment and work culture, as well as new work practices and digital modernisation.
	We need to align our culture with strategy, so people can be productive and engaged, while upgrading their skills to deliver quality services.

	Balancing our asset investment
	As Geelong’s population grows, it is becoming increasingly difficult to get our asset investment mix right.  
	We need to achieve optimal investment in maintaining, renewing, replacing, enhancing and disposing assets. 


TABLE 4: Trends impacting our services
COUNCIL PLAN HIGHLIGHTS FOR 2019–20
In the 2019–20 update of our council plan, we committed to 130 initiatives in total. Fourteen of these were major initiatives.  

FIGURE 16: Council plan progress for 2019–20 (overall, major and other initiatives)

[image: image69.jpg]


[image: image22.png]33.8% (44) 46.9% (61)

0.8% (1)

6.2% (8)

4.6% (8) 7.7% (10)



[image: image70.jpg]



[image: image71.jpg]


[image: image23.png]35.7% (5)

50.0% (7)

14.3% (2)




[image: image24.png]31.9% (37)

48.3% (56)

0.9%

6.9% (8)

5.2% (6) 6.9% (8)



[image: image72.jpg](2




	
	On track
	
	Needs improvement
	
	Off track
	
	Off track COVID-19
	
	Not started
	
	Complete


	STRATEGIC DIRECTION
	
	ACHIEVEMENTS

	Improved health and safety of our community
	
	· Council allocated $1.7 million over five years to support food relief services in the region.

· Council endorsed The City of Greater Geelong Social Housing Plan 2020–41 in February 2020.

	Informed social infrastructure and planning
	
	· We awarded over $4 million in Community Investment and Support Fund grants to 248 groups.
· We opened the Northern Skate Park in Corio.

	A more inclusive and diverse community
	
	· We developed our first Reconciliation Action Plan.

· We upgraded sport and recreation facilities to provide modern, unisex amenities supporting female participation in sport across the municipality.

	Planned sustainable development
	
	· We developed a draft 20-year master plan for the Sparrovale Wetlands.
· We managed over 1,300 hectares of nature reserves.

	Effective environmental management
	
	· Council adopted The City of Greater Geelong Waste and Resource Recovery Strategy 2020–2030.

· We consulted with the community about our draft Environment Strategy 2020–30 and Environment Strategy Action Plan 2020–22. 

	Vibrant arts and culture


	
	· Council endorsed the Our Heritage, Our Collection strategic report, which is designed to help us better manage our heritage collection.

· Council allocated $510,000 to a COVID-19 recovery response supporting  the arts, culture and heritage sectors.  

	Integrated transport connections
	
	· Council adopted the Shared Trails Masterplan, a 10-year plan that aims to create a fully-connected network of shared trails across the region.

· We completed the western link of the Building Better Bike Connections Project, which connects Geelong’s western suburbs to Central Geelong. 

	A thriving and sustainable economy
	
	· The Regional Industry Sector Employment program (RISE) won a national award for excellence from Economic Development Australia, and was a finalist in the Victorian Training Awards.  

· We helped 370 businesses adapt to the impact of COVID-19 restrictions through the Geelong Business Support Program.

	Growing our tourism and events
	
	· We introduced a new Community Events grant stream, allocating $170,000 to support 32 community events.

· We completed and opened the Geelong Botanic Gardens Sustainable Visitor facility.

	Innovative finances and technology
	
	· We provided $5.165 in financial support to help communities adapt to COVID-19 as part of our 2020–21 budget. 

· We were the first city within Victoria to install public space ‘Smart Node’ street poles. 

	Organisational leadership, strategy and governance
	
	· Council adopted The City of Greater Geelong Sustainability Framework and Action Plan, to encourage and lead a culture of sustainability throughout the organisation and community.

· We established a Redeployment Program to match employees left without work due to COVID-19 restrictions with those community services facing increased demand.


A full account of our achievements under each strategic priority follows. 
IMPROVED HEALTH AND SAFETY OF OUR COMMUNITY

The health and safety of our community is vital. We will address family violence, homelessness, food shortages and public safety.

LINKS TO THE CLEVER CREATIVE VISION[image: image73.jpg]


:
[image: image74.jpg]



Achievements 

· Council allocated $1.7 million over five years to support food relief services in the region.
· Council endorsed The City of Greater Geelong Social Housing Plan 2020–41 in February 2020. 

· We presented the Women in Community Life Awards at an International Women's Day event in March 2020. 

· We participated in the Barwon Month of Action and 16 Days of Activism against Gender-Based Violence. 
· We were awarded a $95,844 Safer Together grant, in partnership with the Country Fire Authority and Department of Environment, Land and Water Planning, to address bushfire prone areas. 
· We launched our Healthy at Home online toolkit to give residents reliable advice on creating and living a healthy lifestyle.
· We supported our community care clients during the pandemic with increased communication and fact sheets and adjusted how we delivered services to minimise risks.  

· We received a $250,000 grant to install ‘smart’ lighting, incorporating CCTV and Wi-Fi, at bus stops and key locations along the Bellarine Rail Trail.
· Our Family Day Care was named the 2019 Service of the Year at the national Excellence in Family Day Care Awards.

Focus areas

· Developing long-term strategies that can address social equity without comprising our existing service standards.
· Improving food security, which affects the most vulnerable in our community. 
Progress report
	[image: image75.jpg]



	On track
	[image: image76.jpg]



	Needs improvement
	[image: image77.jpg]



	Off track
	[image: image25.jpg]



	Off track COVID-19
	[image: image78.jpg]



	Not yet available
	(
	Complete




	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	  Status

	Increase in the percentage of residents feeling safe where they live.
	Every two years
	54%
	57%
	-
	The next Preventative Health Survey results are due to be released in the 2020–21 financial year.
	[image: image79.png]Budgeted income foregone

= Free parking/parking permit refunds
 Rent/fee relief initiatives

= Rate and interest waivers





	Increase in the percentage of adults rating their health as very good, or excellent.
	Every two years
	59%
	60%
	-
	The next Preventative Health Survey results are due to be released in the 2020–21 financial year.
	[image: image80.png]Expenditure

26%

$1.95m
15.4% [ 25.6% |

= Food relief support = Social housing
= Business training and support = Tourism and events campaign
= Arts recovery initiative Kardinia Pool (winter opening)

= Quick response grants = International student support





	Increase in the percentage of adults who are sufficiently physically active.
	Every two years
	41%
	43%
	-
	The next Preventative Health Survey results are due to be released in the 2020–21 financial year.
	

	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	  Status

	Increase in the percentage of children enrolled who participate in Maternal Child Health Services.
	Annual
	73.46%
(2016–17)


	75%
	73.14%

(2019–20)

73.17%

(2018–19)


	We’ve observed consistent participation rates in recent years, even taking into account that some face-to-face services were moved online due to COVID-19 directives from the Victorian Government.
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	  Status

	Show leadership in gender equity, diversity and family violence prevention.
	Implement actions in the Ba-gurrk Gender Equity Framework.
	We delivered a Gender Equity Forum at Deakin University with our key strategic partners in October 2019. 

We also worked with the Municipal Association of Victoria to complete Stage 1 of a three-month pilot project testing an analysis toolkit designed to make sure women, men and gender non-binary individuals are considered in important decision making. The findings will inform our Arts and Culture Strategy and open space referrals.

We continued to support the Women in Community Life Advisory Committee and presented the Women in Community Life Awards at an International Women's Day event on 6 March 2020. The event featured Nova Peris as the keynote speaker. 
	

	Support local organisations that address homelessness, family violence and food shortages.
	Work with partner agencies to implement strategies aimed at addressing homelessness in Central Geelong.
	We commenced a new project with key partners, such as the Barwon Homelessness Network, to consider security measures for rough sleepers in Central Geelong. While several agencies were consulted about secure lockers, they’re yet to be placed. We also worked with several agencies to offer rough sleepers and homeless people services during the COVID-19 pandemic, such as showers. Finally, a partnership with NEAMI, a community-based organisation, and Victoria Police helped connect rough sleepers with accommodation and other support.
	

	
	Implement a strategic response to address food shortages in the Geelong region.*
	We worked with key community food relief and assistance stakeholders to develop a business case for increasing the region’s food distribution and storage capacity significantly. In May 2020, Council subsequently resolved to support and fund the development of a new Food Relief Facility in North Geelong and provide five years funding to support the Geelong Food Relief Centre. The legal agreements have been drafted and are currently being reviewed.   
	   (


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Develop a housing policy to provide a range of social and affordable housing options.
	Adopt and commence delivery of the first year of the Social Housing Plan.
	We presented a draft social housing plan to Council in November 2019 and received over 90 responses and 14 written submissions from the community.

Council endorsed The City of Greater Geelong Social Housing Strategy 2020–41 in February 2020 and a plan to implement it has begun. 

As part of the COVID-19 recovery program, we’ve also started working in partnership with the Department of Health and Human Services to determine the feasibility of using Council-owned sites for social housing.
	

	Improve safety in our community.
	Work with partner agencies to develop a Community Safety Strategy and Action Plan.
	We commenced scoping a community safety strategy and action plan with key agencies including Victoria Police and the Department of Justice and Community Safety. Progress has been delayed as we’ve prioritised our COVID-19 response and sought additional funding. However, we aim to complete the   strategy and plan by September 2020.
	

	Provide safer public spaces.
	Improve safety in the CBD, including the Little Malop Street Mall and Moorabool Street.
	We removed the public toilet to make way for a performance space, reinstated the water feature and added new festoon lights, children’s play equipment, planter boxes and seating as part of the Little Malop Street Central activation and public realm improvement project. A Place Score survey, completed in February 2020, shows perceptions of the space have since improved demonstrably. What we’ve learnt will help shape the long-term master plan for the space, in conjunction with extensive community consultation. 
	   (

	Encourage responsible pet ownership.
	Implement the Domestic Animal Management Plan focusing on community awareness and education.
	We implemented the following actions in 2019–20:

· completed the July 2019 cat desexing program 

· audited dog signage across the municipality, with new signs rolled out to key locations

· installed temporary ‘pick up poo’ signs at sporting grounds

· rebranded animal management vehicles to improve our visibility within the community

· communicated via the Park Your Pet App 

· engaged with the community about proposed changes to dog control orders on Barwon-Coast-managed land 

· distributed City-branded dog poo bag dispensers at events

· created a video about effective dog control

· added pet selection articles and links to our website
· developed a dog attack registry to help identify trends in the municipality.
	   (

	Promote healthy eating and support active living.
	Continue to work with sporting clubs, community groups and businesses to promote healthy eating.
	We continued our work to reduce sugar-sweetened beverages at all Council-owned and operated recreation facilities and, in conjunction with partner organisations, supported the ‘Choose Water Every Day’ Campaigns. 

We also finalised the Healthy Catering Guide, designed to assist workplaces, associations and community groups to make healthier choices when organising catering.
	   (


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	
	Create and facilitate more health and fitness options.
	We offered the following health and fitness programs in 2019–20: 
· over 400 virtual and group fitness classes, which were highly successful during the COVID-related closures of our leisure centres

· over 100 MOTIVATE30 small-group training classes

· Yoga by the Pool classes at Kardinia Aquatic Centre from November to December, as well as in March 

· member Health Series events on family health and nutrition

· group personal training sessions at Leisurelink focused on women, beginners, older people and injured members

· a free 2019 Swim Guide, to promote lap swimming supported by a free two-week program.
	   (

	
	Create the Mental Health Strategy and Action Plan.
	We developed a scoping paper to further understand our role in facilitating positive mental health. Based on this scoping paper, a pilot project across the organisation will be trialled between July and December 2020 in lieu of an action plan.
	

	Create healthy environments in children’s settings.
	
	To create healthy children’s settings in 2019–20, we:

· reviewed our implementation of the Child Safe Standards

· implemented daily safety checks of outdoor play spaces in children’s centres
· started ‘Be You’ online training for educators to support children's mental health and wellbeing.
In response to COVID-19, we have made the following changes in children’s centres:

· installed hand sanitiser stations 

· installed floor decals and signage with social distancing reminders 
· staggered lunch times for children, to reduce the number of children coming together at one time

· increased monitoring of children / parents, reminding them to stay home if they are showing any signs of being unwell

· encouraged one child / one parent drop-off (this applied to Maternal Child Health appointments as well)
· implemented additional cleaning across all services, with a focus on high-touch points.
	

	Work towards having the safest roads in Victoria.
	Work towards becoming a ‘Towards Zero’ council for road safety.
	We started preparing a new road safety strategy. This will be considered by Council later in 2020. 

We also worked to secure $3 million to implement additional road safety treatments throughout Corio and South Geelong.

Finally, we installed pedestrian safety improvements around schools in Armstrong Creek and continued to advocate for safer speeds in local streets. 
	


*Major Initiative
Local Government Performance Reporting Indicators 

To help measure performance across all Victorian councils in a transparent and accountable way, we report to Local Government Victoria on the following mandatory indicators:
	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Aquatic Facilities
	
	
	
	
	

	Service standard

Health inspections of aquatic facilities
[Number of authorised officer inspections of Council aquatic facilities / Number of Council aquatic facilities]
	0.67
	0.67
	1.00
	1.00
	One inspection was conducted at each of our six pools. 



	Utilisation
Utilisation of aquatic facilities
[Number of visits to aquatic facilities / Population]
	8.48
	8.36
	8.82
	6.53
	The utilisation of our aquatic facilities was impacted by:

· unfavourable weather during the 2019–20 summer season

· centre closures due to smoke haze from bushfires

· centre closures caused by COVID-19 restrictions.  

	Service cost
Cost of aquatic facilities
[Direct cost of the aquatic facilities less income received / Number of visits to aquatic facilities]
	New in 2020
	New in 2020
	New in 2020
	$3.01
	Costs reflect the impact of COVID-19 including site closures, lost revenue and memberships being placed on hold. 
Learn to Swim was not run from March to June 2020.

	Animal Management
	
	
	
	
	

	Timeliness
Time taken to action animal management requests
[Number of days between receipt and first response action for all animal management requests / Number of animal management requests]
	1.00
	1.00
	1.00
	1.00
	All animal management requests are actioned within one day.


	Service standard
Animals reclaimed
[Number of animals reclaimed / Number of animals collected] x100
	48.31%
	20.26%
	18.65%
	23.92%
	We make every effort to reunite registered cats and dogs with their owners before they are impounded. 
COVID-19 restrictions led to a decrease in impounded animals, as more people were at home than usual.

	Service standard
Animals rehomed
[Number of animals rehomed / Number of animals collected] x100
	New in 2020
	New in 2020
	New in 2020
	59.61%
	We actively try to rehome unclaimed animals, advertising them for adoption online. Increased adoptions in 2019–20 coincided with COVID-19 restrictions. 

	Service cost
Cost of animal management service per population
[Direct cost of the animal management service / Population]
	$11.03
	$11.86
	$12.28
	$13.48
	This indicator changed in 2019–20 so costs are worked out per head of population – not by number of registered animals. 
Increased costs caused by an increase in prosecutions, as well extra labour needed to deliver the domestic animal management plan. 

	Health and safety
Animal management prosecutions [Number of successful animal management prosecutions / Number of animal management prosecutions] x100
	New in 2020
	New in 2020
	New in 2020
	100.00%
	Animal management prosecutions presented to the Magistrates Court have increased over the past three years in proportion to the reported number of serious dog attacks. All 27 prosecutions heard this financial year were successfully prosecuted.  

Six additional prosecutions have been postponed until 2020–21, due to COVID-19 restrictions. 

	Food Safety
	
	
	
	
	

	Timeliness
Time taken to action food 
complaints
[Number of days between receipt and first response action for all food complaints / Number of food complaints]
	2.64
	2.04
	1.78
	1.64

	Actioning complaints has decreased by one day since 2017. This is particularly notable given that complaints are increasingly lodged after hours, and response times are only actioned during business hours.

	Service standard

Food safety assessments
[Number of registered class 1 food premises and class 2 food premises that receive an annual food safety assessment in accordance with the Food Act (Vic) 1984 / Number of registered class 1 food premises and class 2 food premises that require an annual food safety assessment in accordance with the Food Act (Vic) 1984] x100
	101.28%
	105.74%
	99.94%
	98.27%
	In the 2019 calendar year, 30 businesses due for an assessment couldn’t be inspected. Of these, 12 were either closed or not trading.  

	Service cost
Cost of food safety service
[Direct cost of the food safety service / Number of food premises registered or notified in accordance with the Food Act (Vic) 1984]
	$481.94
	$506.52
	$517.04
	$532.42
	In addition to our annual labour cost rises and the growth in new food businesses, we have applied a more rigorous methodology to our recent reporting processes and expect future data to be more aligned with our 2019–20 results.

	Health and safety
Critical and major non-compliance outcome notifications
[Number of critical non-compliance outcome notifications and major non-compliance notifications about a food premises followed up / Number of critical non-compliance outcome notifications and major non-compliance notifications about a food premises] x100
	96.48%
	99.46%
	99.32%


	98.19%
	Despite slight variations, we have performed very well in this indicator since 2017. In the 2019 calendar year, only three notifications did not receive timely follow-up, as the businesses were not trading frequently.

	Maternal and Child Health (MCH)
	
	
	
	
	

	Service standard

Infant enrolments in the MCH service
[Number of infants enrolled in the MCH service / Number of birth notifications received] x100
	101.43%
	100.00%
	98.89%
	101.12%
	Participation rates are consistently high. 

	Service cost
Cost of the MCH service
[Cost of the MCH service / Hours worked by MCH nurses]
	$75.33
	$79.68
	$80.35
	$80.18
	In addition to our annual labour cost rises, we have applied a more rigorous methodology to our recent reporting processes and except future data to be more aligned with our 2019–20 results.

	Participation

Participation in the MCH service
[Number of children who attend the MCH service at least once (in a year) / Number of children enrolled in the MCH service] x100
	73.46%
	73.78%
	73.17%
	73.14%
	Moving some face-to-face services online to accommodate COVID-19 restrictions has had no obvious impact on participation rates.

	Participation

Participation in the MCH service 

by Aboriginal children
[Number of Aboriginal children who attend the MCH service at least once (in the year) / Number of Aboriginal children enrolled in the MCH service] x100
	73.26%
	64.86%
	63.39%
	76.37%
	We have continued to build our partnership with the Wathaurong Aboriginal Co-operative to provide a place-based Maternal and Child Health service.

	Satisfaction
Participation in 4-week Key Age  and Stage visit
[Number of 4-week key age and stage visits / Number of birth notifications received] x100
	New in 2020


	New in 2020


	New in 2020


	93.77%
	Participation rates are high. 



As part of the ongoing review and improvement of reporting, Local Government Victoria retired the following indicators:
	RETIRED

SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Aquatic Facilities
	
	
	
	
	

	Health and safety
Reportable safety incidents at aquatic facilities
[Number of WorkSafe reportable aquatic facility safety incidents]
	16
	22
	18
	Retired in 2020
	As of 1 July 2019, councils are no longer required to report on this indicator.

	Service cost
Cost of indoor aquatic facilities
[Direct cost of indoor aquatic facilities less income received / Number of visits to indoor aquatic facilities]
	$0.91
	$0.51
	$0.69
	Retired in 2020
	As of 1 July 2019, Cost of indoor aquatic facilities and Cost of outdoor aquatic facilities have been merged into one measure.

	Service cost
Cost of outdoor aquatic facilities
[Direct cost of outdoor aquatic facilities less income received / Number of visits to outdoor aquatic facilities]
	$4.90
	$4.71
	$6.21
	Retired in 2020
	As of 1 July 2019, Cost of indoor aquatic facilities and Cost of outdoor aquatic facilities have been merged into one measure.

	Animal Management
	
	
	
	
	

	Service cost
Cost of animal management service
[Direct cost of the animal management service / Number of registered animals]
	$57.66
	$64.22
	$66.26
	Retired in 2020
	As of 1 July 2019, this indicator was replaced by Cost of animal management service per population. 

	Health and safety
Animal management prosecutions
[Number of successful animal management prosecutions]
	12
	21
	19
	Retired in 2020
	As of 1 July 2019, this indicator was replaced by an amended Animal management prosecution measure that is a proportion rather than a number. 

	Maternal and Child Health (MCH)
	
	
	
	
	

	Participation

Participation in first MCH home visit
[Number of first MCH home visits / Number of birth notifications received] x100
	100.94%
	94.22%
	96.84%
	Retired in  2020
	As of 1 July 2019, this indicator was replaced by Participation in 4-week Key Age and Stage visit. 


INFORMED SOCIAL INFRASTRUCTURE AND PLANNING

We will strive for social equity in the infrastructure and services we deliver for our community.

LINKS TO THE CLEVER CREATIVE VISION:

Achievements 

· We awarded over $4 million in Community Investment and Support Fund grants to 248 groups for community-based initiatives and projects.

· We opened the Northern Skate Park in Corio.

· We delivered new and upgraded sporting and community facilities, including:
· Bella Wiyn Birralee Family Centre (Drysdale) 

· Korayn Birralee Family Centre (Corio)

· St Mary’s social room extension

· St Joseph’s Football and Netball Club changeroom upgrade.
· We delivered nine new and upgraded playgrounds across the municipality. 

· We identified potential locations for a new 50-metre pool to service the northern Bellarine.
· We added 24.8 hectares to our open space network.

· We completed concept designs for a new Barwon Heads Arts and Community Centre.
· We engaged with the community to seek their views on the draft Social Infrastructure Plan - Generation One: 2020–2023, which aims to provide places, spaces and services where and when people need them the most.
Focus areas

· Planning on how we can deliver infrastructure for our growth corridors, whilst balancing service delivery to our established areas.
· Securing land for new infrastructure developments in established areas.
Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image26.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	  Status

	No net loss of public open space by suburb.
	Annual
	2,147.6 ha (530 sites)

(November 2017)
	Maintain
	2,202.7 ha (568 sites)
(June 2020)
2,177.9 hectares (549 sites) (2018)
	An increase of 19 sites and 24.8 hectares since 2018.
An increase of 38 sites and 55.1 hectares on the baseline result of 2017, with no net loss in any suburb.
	


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	  Status

	Per cent of plans for key community infrastructure projects completed.
	Annual
	37 key community infrastructure projects have been identified for delivery by 2022.
	100%
	81%

(June 2020)

65%

(June 2019)


	We completed 31 of the 37 priority projects, in addition to new and priority projects that have emerged in the first two years of our council plan.  
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Provide more quality spaces that support active lifestyles.
	Identify locations and construct two fenced dog parks.
	We identified locations in Belmont and Lara for two new dog parks. Proposed designs were made available for community feedback in June 2020. We also started the process for selecting a site on the Bellarine.

Furniture and fencing contracts for all three parks have been approved.
	

	Support the growth of localised and regional sporting facilities.
	Provide new sports and leisure facilities and upgrade existing ones.
	In 2019–20, we did the following:

· completed the design and planning work needed to support West Oval becoming a regional AFL facility

· finalised the draft of a facility improvement plan for the Geelong Baseball Centre at Waurn Ponds 

· progressed all designs for redevelopment of change facilities and pavilions for West Oval, Herne Hill and South Barwon

· upgraded the St Mary's Football Netball Club pavilion 

· redeveloped the St Albans Football Club change room 

· redeveloped the East Geelong Football Netball Club umpire change room 

· installed flood lighting at the Collendina Reserve 

· installed lighting at Anakie Reserve 

· completed the Stead Park Skatepark in Norlane.
In addition to the above:

· Council endorsed a scoping study for the proposed 50-metre outdoor pool in Drysdale  

· Council adopted the final Drysdale Sporting Precinct Master Plan
· we signed $9 million worth of funding agreements with the Victorian Government for the delivery of the West Oval and Herne Hill joint facilities for AFL and cricket.
	   (


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Deliver accessible and attractive community infrastructure, based on community need.
	Advocate for funding for the Northern ARC Health and Wellbeing Hub.
	We collaborated with G21, Regional Development Victoria, Sport and Recreation Victoria and the Barwon Region Partnerships to advocate for state and federal government funding. We will continue to advocate for funding in 2020–21.
	   (

	
	Engage with sporting clubs and community groups to improve access to community and sporting facilities.
	We are meeting with Leisure Networks on bi-monthly basis to develop capacity in sports clubs. Clubs helped identify a need for disability inclusion training in early 2020. We’ll deliver this with Leisure Networks when social distancing restrictions lift.
	

	 
	Complete planning to upgrade children’s centres, and construct and open new centres.*
	We completed and opened the following new facilities:

· Rosewall Community Centre 

· Korayn Birralee Family Centre 

· Bella Wiyn Birralee Family Centre.
	   (

	
	Acquire land for new community infrastructure.*
	We purchased land in Bell Post Hill for a new early learning centre and finalised the contract with VicRoads to purchase land for a new future community facility in Fyansford. 

We started working with VicRoads to acquire land for the development of the Armstrong Creek Sports Precinct.
	   (

	
	Implement a new approach for the Community Investment and Support Fund.
	We awarded $4,008,444 Community Investment and Support Fund grants to 248 groups to undertake community-based initiatives and projects. We also implemented a new process for the grants, which included:

· more budget allocated to community infrastructure

· final assessment by a community panel

· a new grant for community events

· guideline changes designed to better reflect the priorities of council plan.

The proposed 2020–21 round of competitive community grants was suspended in April 2020 to assess the best way to support the region’s recovery from COVID-19. 
	   (

	
	Develop a feasibility study for a livestock and information exchange facility.
	An organisation was appointed to undertake the study and engagement with key stakeholders was extended by six weeks to make sure the community had every opportunity to share their views. Stage 2 of the feasibility study, the assessment of issues uncovered from the consultation process, is now complete. 
	

	
	Finalise and implement the Osborne Park Precinct Master Plan and business case.
	Following a series of meetings with Osborne Park Association representatives and a community stakeholder forum on 12 November 2019, we rescoped the project and prepared a program of renewal works. Following further engagement with key stakeholders, a report was then sent to Council in February 2020. 
Council resolved to prepare a Sustainable Development Plan for Osborne House and consultants were engaged in April. A consultation forum was then held with the community project reference group in May 2020. 

We engaged weekly with the Osborne Park Association executive and a project control group was convened with representatives from government and heritage organisations.  Five options will be considered by the project control group in July and a report will be presented to Council in August 2020. 
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Maintain our public open space.
	Improve playgrounds using the Geelong Play Strategy.
	We re-opened Kingston Park in Ocean Grove after completing a $370,000 upgrade.

We engaged with the community in November and December about upgrading nine neighbourhood playgrounds. Site works were then commenced as a part of the annual renewal program. 
In addition, we also installed story cubes outside the Corio Library, as well as sign rocks marking the location of the Waurn Ponds Creek Environmental Walk on Pioneer Road and Ghazeepore Road.

We have identified sites across the municipality for the 2020–21 playground renewal program and will install extra infrastructure, including paths, fences and trees, where required.  
	


*Major Initiative
A MORE INCLUSIVE AND DIVERSE COMMUNITY

We want to recognise all members of the Geelong community and not leave anyone behind.

LINKS TO THE CLEVER CREATIVE VISION:

Achievements 

· We developed our first Reconciliation Action Plan.
· We upgraded sport and recreation facilities to provide modern, unisex amenities supporting female participation at multiple sites across the municipality.

· We installed a Changing Places facility at Westfield Geelong, as part of the Central Geelong Accessibility Improvements Project.
· We hosted an International Women's Day event featuring key note speaker, Nova Peris, and over 200 people attended. 
· We worked closely with the community to develop a draft concept design for the new Rippleside Inclusive Playspace.

· We identified a community shed and garden site for the Armstrong Creek West precinct.
· We celebrated the graduation of 13 participants from our 22-week Community Leadership Program, designed to build the confidence of community members to lead community projects. 
· We improved all abilities access to facilities across the municipality, including:

· Anakie Community Centre 
· Springdale Community Centre
· Ocean Grove Senior Citizens Centre
· Highton Senior Citizens Centre.

· We engaged with 15,114 young people through 1,160 programs, including groups, drop-in programs, holiday programs and events.

· We facilitated Mental Health First Aid Courses for 1,800 young people, parents and community members. 

· We developed a suite of digital engagement and development programs for young people to help them remain connected the COVID-19 lockdown.
· We assisted tenants and community facility users to safely resume allowed activities by giving them support to develop COVID-safe work plans.
Focus areas

· Driving and implementing strategies to drive long-term solutions aimed at improving community equity. 
· Providing a diverse range of opportunities for people to participate in their community.

Progress report

	
	On track
	
	Needs improvement
	
	Off track
	[image: image27.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	
Status

	Increase in the percentage of adults who definitely feel multiculturalism makes life better.
	Every four years
	57.4%

(2014)
	60%
	-
	The 2018 Victorian Population Health Survey at Local Government Area results are due to be released in the second half of 2020.
	

	Increase in the percentage of adults attending a local community event.
	Every four years
	71.2%

(2014)
	75%
	-
	The 2018 Victorian Population Health Survey at Local Government Area results are due to be released in the second half of 2020.
	

	Increase in the percentage of adults feel that they can get help from family, friends or neighbours when needed.
	Every four years
	73.5%

(2014)
	80%
	-
	The 2018 Victorian Population Health Survey at Local Government Area results are due to be released in the second half of 2020.
	

	More community facilities with gender-neutral and accessible toilets, or change areas.
	Annual
	· 
	Increase
	7 facility increase 

(June 2020)
	The seven new and upgraded facilities were in addition to the eight facilities completed last financial year. 
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Advocating for, and helping to achieve, the priorities set by local Aboriginal people.
	Develop and launch the Reconciliation Action Plan.


	We developed our first Reconciliation Action Plan after working closely with the local Aboriginal and Torres Strait Islander community, the Reconciliation Action Plan Working Group and the community. Reconciliation Australia provided conditional consent after the plan was adopted by Council in April 2020, but still needs to endorse the plan. A community celebration will be held once COVID-19 restrictions ease. 
	   (

	Advocate for inclusive, multicultural activities and respect for cultural diversity.
	Implement the first year of the Multicultural Action Plan.
	We delivered a men's s swimming program and started to review our Diversity Policy.
	   (


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Support activities that improve social connections in our community.
	
	We engaged with 15,114 young people through 1,160 programs, including groups, drop-in programs, holiday programs and events. We also:

· provided grants to support community events as part of the International Day of People with Disability in December 2019

· partnered with the Gordon Skills and Jobs Centre to support the WorkWise Women program, which helped 20 women build their social connections and capacity for work and training

· attended the Wyndham Community Education Centre to share strategies for minimising isolation with newly-arrived job seekers 

· partnered with Barwon Child, Youth & Family to refine how the Autism Spectrum peer support group is delivered 
· celebrated the graduation of 13 participants from our 22-week Community Leadership Program, designed to build the confidence of community members to lead community projects
· facilitated the Postcard Project, aimed at increasing connections between older people living in aged care homes and the young people who the designed postcards

· provided welfare phone calls during COVID-19 and after the Waurn Ponds storm event in May 2020 
· linked community members impacted by COVID-19 to local food security organisations
· utilised the CAOS Network to help coordinate the community agency response to COVID-19

· assisted tenants and community facility users to safely resume allowed activities by giving them support to develop COVID-safe work plans.
	 

	Promote gender equity and diversity in our sporting and leisure facilities, and programs.
	Continue to invest in programs and facilities to support gender equity in sport.*
	We hosted a forum in December 2019 to recognise local sporting clubs with successful gender equity practices, with funding support from the Municipal Association Victoria. 

We also worked with sporting clubs to emphasise the importance of gender equity approaches.
	   (

	Facilitate employment programs for the communities that need it most, including young people.
	Deliver employment programs for people with Jobs Victoria Employment Network and Skilling the Bay.
	In partnership with Go Traffic, we continued to support the GROW (G21 Region Opportunities for Work) initiative. Over 60 people attended information sessions, 21 completed certification training and a further 121 registering for the jobs program.

Forty new participants registered in the Skilling the Bay programs, which included: 

· Good Cycles program

· Certificate II Production Horticulture 

· Certificate III Cleaning Operations

· Jamie's Ministry of Food Program 

· Go Traffic training program

· Work ready life skills program.
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Improve access to facilities and programs for people of all abilities.
	Implement the Community Access and Inclusion Plan including the Changing Places Strategy.
	We installed the Changing Places amenities in Westfield Geelong as part of the Central Geelong Accessibility Improvements Project. We now have seven Changing Places facilities across the municipality. 
We completed audits on our changing places facilities and the Rosewall, Cloverdale and Armstrong Creek Hubs.

We are delivering Mobi Chair Beach Wheelchair Training with Leisure Network disability support workers to help community members with a disability access beaches. Training will resume once COVID-19 restrictions are eased. 
We started a new online social group for parents and carers of children with Autism Spectrum Disorder in May 2020. 

We worked hard with internal teams to make sure the new Civic Precinct will comply with disability standards and guidelines.
	

	
	Start design of inclusive playground at Rippleside Park.
	We partnered with Variety – the children’s charity – to create a play area at Rippleside Park for children of all ages and abilities. We asked the community for design ideas in October and November, then developed draft concept plans. The plans were released for further feedback in early 2020, and over 500 responses were received. 
A draft concept design will be released for further community engagement in July 2020, following endorsement from Council. 
	   (

	Recognise our returned service men and women.
	
	In 2019–20, we: 
· relocated the Spirit of ANZAC statue and Victoria Cross recipient pavers within Johnston Park
· supported the special Remembrance Day performance of 'The Mission' by Tom Molyneux at Courthouse Youth Arts
· cleaned all war memorials and monuments and identified conservations works need before ANZAC Day 
· installed honour walls at the Ocean Grove Memorial
· added three new ANZAC Spirit digital stories to the Connecting Memory Storytelling app
· digitised the Charles Wilson Collection 
· selected a series of war-related objects for the Our Heritage, Our Collection online exhibition 

· supported Vietnam Veterans in collections management 
· started a process to digitise First World War naval objects from the Maritime Museum, adding objects related to veterans

· developed a special pop-up travelling display of Charles 'Tug' Wilson naval artefacts (on hold due to COVID-19 restrictions)
· commenced design work on the renewal of the Malay Borneo memorial at St Helens Park

· started planning a public artwork for returned Aboriginal service people

· started planning and design for a new Memorial in Anakie. 
	

	Further develop programs that support older people and young people in our community.
	Develop and launch the Positive Ageing Plan.
	We recruited an officer to help develop the positive ageing plan. 

Due COVID-19 restrictions, we were forced to cancel the community and stakeholder consultation sessions scheduled for March 2020. The plan development was placed on hold until 2021.
	[image: image28.jpg]





*Major Initiative
PLANNED SUSTAINABLE DEVELOPMENT

We will use sustainable principles to guide development of growth areas and help protect our townships.
LINKS TO THE CLEVER CREATIVE VISION:

Achievements 

· We developed a draft 20-year master plan for the Sparrovale Wetlands.
· We managed over 1,300 hectares of nature reserves, conserving and enhancing the natural environment on the coast, along our rivers, and in wetland, bushland and grassland areas.

· We started developing precinct structure plans for the Northern and Western Geelong Growth Areas of Elcho Road East (Northern) and Creamery Road (Western).
· We released the draft Pakington Street and Gordon Avenue Urban Design Framework for community consultation. 

· We incorporated Environmentally Sustainable Development guidelines into the Greater Geelong Planning Scheme, to make sure that new buildings in Geelong will meet high sustainability standards. 

Focus areas

· Accommodating population growth without negatively affecting the region’s unique environment and liveability.

· Continuing infrastructure planning in our growth areas to meet the social infrastructure needs of new residents.

Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image29.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	Status   

	More protected natural habitat that we manage.
	Annual
	898.712 hectares

(December 2018)
	Increase
	1,275.703 (June 2020)
1,275.471 hectares

(June 2019)
	We have increased the natural habitat that we manage by 376.991 hectares since December 2018.
	

	15 years of residential land supply planned.
	Annual
	14+ years

(January 2017)
	Maintain
	26 years

(October 2019)
26 years

(June 2019)
	There are a range of development fronts and housing choices for new and existing residents to meet their diverse housing needs
	


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	Status   

	Increase in the percentage of new housing construction conducted within existing urban areas.
	Annual
	37.8%

(December 2016)
	40%
	25.8%

(2019)

23.0%

(2018)
27.0%

(2017)


	High levels of dwelling growth have been sustained in recent years. While the number of dwellings constructed in existing areas has remained constant, this development is declining in proportion to overall development due to the rapid expansion of major greenfield growth fronts. 
	

	All new large, City-owned buildings rated 5-star 'Green Star'.
	Annual
	-
	100%
	100%

(2019–20)
100%

(2018–19)
	The Bella Wiyn Birralee Family Centre, Korayn Birralee Family Centre and Highton Early Learning Centre all met these standards in 2019–20.
	

	All new small, City-owned buildings with built environment sustainability scorecard or equivalent.
	Annual
	-
	100%
	100%

(2019–20)
100%

(2018–19)
	The Armstrong Creek Sports Pavilion, Highton Enhanced Children’s Centre and St Mary’s social room extension reached this standard.
	

	Mandatory sustainable design assessment of all new developments.
	n/a
	n/a
	Planning controls in place
	-
	The Environmentally

Sustainable Development guidelines were incorporated
into the Greater Geelong Planning Scheme via a planning scheme amendment, gazetted on 17 October 2019.
	(


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Ensure housing supply, diversity and affordability can meet the needs of our growing community.
	Implement the Settlement Strategy to guide growth and development in townships and urban areas.
	Council referred Amendment C395, which seeks to implement the Settlement Strategy into the Geelong Planning Scheme, to an independent planning panel. The panel hearing concluded in mid-March 2020 and the report was completed. The amendment will be considered by Council in August 2020.
	

	Facilitate opportunities for infill residential development.
	Adopt the Saleyard Precinct Master Plan.
	We engaged with the community and key stakeholders to inform the development of the draft Saleyard Precinct Master Plan in August 2019. The draft was considered by Council in May 2020 and subsequently released for community feedback. Consultation will conclude in August 2020.
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Continue to develop urban growth areas across the region.
	Commence a Precinct Structure Plan in each of the Northern and Western Geelong Growth Areas.*
	We signed a third-party funding agreement with the landowners in the Elcho Road precinct, completed biodiversity field assessments and started technical reports that will inform the Elcho Road Precinct Structure Plan and Creamery Road Precinct Structure Plan.
	

	
	Unlock barriers to investment in key development areas, urban renewal areas and station precincts.
	We started preparing the draft South Geelong Station Urban Design Framework and planned a community engagement for late July, dependent on Council approval.  
Council endorsed the draft Pakington Street (Geelong West) and Gordon Avenue Urban Design Framework for community consultation in February 2020. This was extended until 10 July 2020 after face-to-face consultations were cancelled due to COVID-19 restrictions. 
	

	
	Continue to implement the Armstrong Creek Urban Growth Area to ensure infrastructure and services meet the needs of the new communities.
	We continued to implement the Armstrong Creek Urban Growth Plan, with development progressing in four precincts.
	

	
	Work with Victorian Government to deliver the Geelong Growth Area Transport Infrastructure Strategy.
	We awarded the contract for the Geelong Growth Areas Transport Infrastructure Strategy, attracted funding from the Department of Transport and continued working on the strategy. Working in partnership with the Department of Transport and the Victorian Planning Authority, we started the technical modelling. 
	

	Manage the impact of development on the unique character of our townships.
	Progress the Municipal Heritage Strategy in partnership with the Heritage Advisory Committee.
	We continue to work on a thematic history for Geelong.
	

	
	Work with Victorian Government to conserve the Bellarine as a distinctive landscape area.
	The Bellarine Peninsula was declared a Distinctive Area and Landscape under the Planning and Environment Act 1987 on 22 October 2019. We continued to work with the Department of Environment, Land, Water and Planning on the technical work and analysed the findings of the Stage 2 consultation, which concluded in June 2020.
	   (

	Improve the environmental performance of new developments, using planning controls.
	
	We incorporated the new Environmentally Sustainable Development guidelines into the Greater Geelong Planning Scheme, via a planning scheme amendment gazetted on 17 October 2019. The guidelines have since been implemented in many developments across our region. 
	   (

	Preserve nature reserves, rural and coastal environments.
	Develop the Sparrovale Wetlands Master Plan and begin construction.*
	The draft Sparrovale Master Plan was considered by Council in May 2020 and subsequently opened for community feedback. 
We engaged with Wadawurrung representatives about naming the area and features to be contained within the reserve.

We completed construction of primary drainage infrastructure.
	


*Major Initiative
Local Government Performance Reporting Indicators 

To help measure performance across all Victorian councils in a transparent and accountable way, we report to Local Government Victoria on the following mandatory indicators:
	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Statutory Planning
	
	
	
	
	

	Timeliness
Time taken to decide planning applications
[The median number of days between receipt of a planning application and a decision on the application]
	65.00
	64.00
	84.00
	83.00
	Response times are similar to last year and reflect the high number of planning applications we received, as well as their complexity.
New digital process improvements led to a drop in the median days taken to reach a decision in the last four months of the financial year.   

	Service standard
Planning applications decided within required time frames
[Number of planning application decisions made within 60 days for regular permits and 10 days for VicSmart permits / Number of planning application decisions made] x100
	73.57%
	72.20%
	68.50%
	69.39%
	Digital process improvements implemented in the last four months of the financial year resulted in 80 per cent of planning applications being decided under 60 days. Of the 237 VicSmart permit decisions decided in 2019–20, 92 per cent were determined within 10 days.

	Service cost
Cost of statutory planning service
[Direct cost of the statutory planning service / Number of planning applications received]
	$1,973.37
	$1,887.19
	$2,415.62
	$2,453.48
	Costs are similar to last year and below the Victorian council average for cost of service in the previous financial year.



	Decision making
Council planning decisions upheld 
at VCAT
[Number of VCAT decisions that did not set aside council's decision in relation to a planning application / Number of VCAT decisions in relation to planning applications] x100
	61.54%
	68.00%
	64.00%
	54.17%
	In 2019-20, 13 of the 24 matters referred to VCAT were set aside. As only 2 per cent of total planning decisions were referred to VCAT, this is a very small proportion of planning decisions overall. Notably, there is no obvious pattern to the types of planning decisions being set aside. 
One appeal was postponed until 2020-21 due to COVID-19 restrictions.  


EFFECTIVE ENVIRONMENTAL MANAGEMENT

We will show leadership to address waste, climate change and environmental challenges.

LINKS TO THE CLEVER CREATIVE VISION:
[image: image30.jpg]DEVELOPMENT AND
IMPLEMENTATION OF
SUSTAINABLE SOLUTIONS




Achievements 
· Council adopted The City of Greater Geelong Waste and Resource Recovery Strategy 2020–2030.
· We developed and released a draft Environment Strategy 2020–30 and Environment Strategy Action Plan 2020–22 for community consultation.

· We introduced the Restoring Rural Landscapes Program for pest plant and animal management on City-managed reserves and roadsides.

· We started to develop a new Climate Change Response Plan. 
· We committed to upgrading approximately 24,000 street lighting fittings with LED alternatives over the next three years.
· Our Highton Early Learning Centre achieved a 6-Star Green Star certification.
· We completed biodiversity mapping for all the nature reserves and rural roadsides we manage. 

· We continued to provide a hard waste collection service, with 15,533 residential collections provided.
· We led a community effort to plant 3,500 trees along the Ted Wilson Trail for National Tree Day. 
· We established a partnership with Barwon Water and other G21 councils to investigate organic waste solutions, under the Renewable Organics Network initiative.
Focus areas

· Implementing solutions in response to the statewide recycling and waste management system crisis.

· Planning for and adapting to climate change.

Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image31.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	  Status

	Increase in percentage of garbage, recyclables and green organics collected from kerbside bins diverted from landfill.
	Annual
	56.32% 
(2016–17)
	60%
	55.73%

(2019–20)
54%
(2018–19)


	Green waste and recycling ratios have been relatively consistent over the past few years. 

The growing population is increasing green organic and waste tonnage, but recycling tonnage has remained the same because of changes in product stream, newspapers and glass content.   
	


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	  Status

	Reduction in emissions from street lights, buildings and vehicle fleet use.
	Annual
	23,135

tCO2-e 
(2014–15)
	50% reduction
	21,886 tCO2-e

(2019–20)
22,633 tCO2-e

(2018–19)


	Despite an increase in building stock, there has been a 5.4 per cent decrease in emissions, compared to the baseline. Annual emissions have decreased due to improved energy efficiency and a greater capacity to generate energy from roof-top renewables. 
	

	Increased use of sustainable material in our asset construction and renewal.
	Annual
	8,000 tonnes of asphalt recycled in-house annually

3,000 tonnes of concrete to recycling annually
(2017–18)
	Increase
	8,745 tonnes of asphalt and 6,547.5 tonnes of concrete recycled

(2019–20)
8,000 tonnes of asphalt and 3,000 tonnes of concrete recycled

(2018–19)
	Future volume increases are dependent on the type of construction and maintenance work carried out each year.
	

	Increased suburban tree canopy.
	Every five years
	14%

(June 2017)
	16%
	14%

(November 2019)
	Although we’ve increased our street and park planting programs, we are not anticipating an increase in urban tree canopy for the next 10 years. This is partially because of the time taken for current plants to mature, but also because of rapid urban growth. 

Urban tree canopy includes  public and private land. Bigger houses on smaller blocks limit space to retain and plant canopy trees on private land. We’re working with the community and developers to address this. 
	

	Increased number of street trees planted per annum.
	Annual

	-
	>1,850 per annum
	2,890

(2019–20)
1,489

(2018–19)
	In addition to our street tree planting program, 365 trees were planted in parks.
	
   


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	    Status

	Reduce our carbon footprint through the use of solar initiatives and other renewable energy options.
	
	We have joined 47 other Victorian councils switching to 100 per cent renewable energy for buildings, offices, leisure centres and streetlights. 
We installed four solar photovoltaic systems (Potato Shed, Barwon Valley Activity Centre, Belmont and Drysdale depots) as part of our Zero Carbon Buildings Program, increasing our generating capacity to over 1 megawatt (1,000 kilowatts). 

We also committed to upgrading approximately 24,000 street lighting fittings with LED alternatives over the next three years. The upgrade will be phased over three years and is expected to reduce energy use by 65 per cent, paying back on the cost within 6 years.
	   (

	Educate and assist our community to act on climate change, by reducing waste, emissions and water usage.
	Complete feasibility study of the Food Organics Processing and Transfer Station.
	In 2019–20, we:

· visited several organics collection and processing facilities in Gippsland and Melbourne 

· engaged a consultant to help us investigate a Towards Zero Waste Program and the options available to support it 

· worked with Barwon Water to explore food organics processing options for the region

· carried out modelling of various options, including a kerbside food collection service. 
A report outlining the options will be finalised in 2020–21.
	

	
	Develop and adopt the Waste and Resource Recovery Strategy.*
	We conducted further community and stakeholder engagement in September 2019. We used this to help inform the draft strategy, which  was then endorsed by Council in December for further community engagement. 
We incorporated the feedback received into the draft, along with new state and federal governments policies, and the final strategy was adopted by Council on 28 April 2020.
	   (

	
	Continue the hard waste collection service trial.*
	On 12 May 2020, we presented a report to Council on the results of the trial. Council endorsed extending the trial for another 12 months and expanding it. 

Hard waste pick-ups have increased by 50 per cent since early May, and are now averaging over 500 pick-ups per week.
	   (

	
	Implement short-and long-term strategies to respond to changes in recycling markets.
	We resumed kerbside recycling collections on 16 December 2019 and continued our expanded recycling services at the Geelong and Drysdale Resource Recovery Centres.
We developed a recycling marketing campaign aimed at decreasing contamination in household kerbside bins. 
We also worked with state government agencies, the recycling industry and other councils to develop longer-term responses.
	

	
	Work with other local governments to implement regional initiatives (sustainable street furniture and road materials, zero landfill waste, waste-to-energy).
	We attended regional forums of G21 and the Barwon South West Waste and Resource Recovery Group to develop the Regional Recycling Action Plan. 

In partnership with neighbouring and regionally-linked municipalities, we are undertaking a variety of projects in the waste management sector to better manage changes in this area.

In addition, in partnership with Geelong Manufacturing Council and state government, we are utilising innovative approaches to encourage the use of recycled material.
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	       Status

	
	Work with partners for an integrated water strategy for the Northern and Western Geelong Growth Areas.
	We continued towork in partnership with Barwon Water and the Department of Environment, Land, Water and Planning  on an integrated water management strategy for the Northern and Western Growth Areas. This project forms part of the Barwon Integrated Water Management initiative, a collaborative approach to water planning and management in the Barwon region.   
	

	
	Support Barwon Water to deliver a regional Integrated Water Management strategy.
	Council endorsed The City of Greater Geelong Stormwater Services Strategy 2020–30 on 30 June 2020. Several objectives outlined in this strategy will help progress regional integrated water management projects, in partnership with Barwon Water.  

We also supported Barwon Water’s ‘Water for our Future’ program in 2019–20.
	

	Use sustainable materials to construct and renew roads, footpaths and street furniture.
	
	We trialled a new form of asphalt made with recycled plastics on a 1,100 metres of road across three locations – Highton, Geelong and Corio – saving the equivalent of 3,500 kg of plastics going to landfill. 

We also constructed a carbon-fibre, reinforced-polymer, modified pedestrian bridge over Cowies Creek.  
	

	Progressively change standard street lights to LED lights, to help reduce carbon emissions.
	
	We approved the transition of street lights to LED. The lighting design is currently underway, and we plan to commence the changeover in residential areas in the second half of 2020.

We held workshops with smart lighting providers and drafted a revised Street Lighting Policy and procedure, which supports LED and smart controls.
	

	Commence Drysdale landfill rehabilitation.
	
	We trialled an evapotranspiration (phyto) cap in the Drysdale landfill and monitored the results. Although results have been positive so far, the trial will continue for another 12 months to help us determine whether we should seek approval to rehabilitate the entire site using this method. A draft post-closure landscape plan has been prepared.
	

	Construct a green organics facility.
	
	Our garden organics processing facility in Anakie received and processed 38,500 tonnes of kerbside garden organics material in 2019–20. The compost produced was turned into valuable organic material that was shared with neighbouring farms.  
	   (

	Plant more trees to green and cool our urban areas.
	Implement the Urban Forest Strategy.
	Of the 3,255 new trees we planted across the municipality in 2019–20, 2,890 were street trees and 365 were park trees. 
	   (

	Reduce single-use plastic across the region.
	Trial the Plastic Wise Program at events in our region.
	We developed a Plastic Wise program, that will now need to be revisited as COVID-19 has implications for reusables.  
	  























































































































  

	Manage pest plants and animals more effectively.
	
	We developed a draft Rabbit Action Plan 2020–24 that will be available for community comment in July and August 2020. We also implemented an integrated rabbit control program. 

We completed extensive woody weed removal on roadsides across the municipality and started a program to address roadside exotic bulbs. We also mapped Chilean Needle-grass on roadsides to inform our future control program. 
	

	Deliver biodiversity conservation programs.
	Develop and implement the Biodiversity Strategy.
	We mapped biodiversity assets across the municipality, with help from key government agencies, environment groups and a consultant. This delayed the strategy, as did the need to complete the draft Rabbit Action Plan 2020–24 and draft Sparrovale Wetlands Master Plan, as these will feed into the biodiversity strategy. 
	


	
	Develop the Northern and Western Growth Areas Biodiversity Conversation Strategy. 
	We have completed field surveys and started reviewing the findings, which will be used to inform strategy. Further surveys will be conducted in spring and summer 2020–21 to complete the data collection process.
	

	
	Foster best agricultural and environmental management practices in rural and peri-urban communities and on Council land.
	We partnered with the Bellarine Landcare Group to support landowners in the Swan Bay Catchment Area with new landholder incentive grants. The aim of the program is to protect and increase areas of environmental significance on private property and improve the water quality in Swan Bay.


	

	
	Implement initiatives from the Rural Peri-Urban Advisory Committee, including restoration of rural landscapes.
	Our Restoring Rural Landscapes Program maintained focus on rabbit and weed control on City-managed reserves and roadsides, but also introduced a private land support program for rabbit and weed control. 

As part of this program, we identified four areas across the municipality for implementation. Rabbit control started in the first zone and was expanded in autumn. 
We worked with the Rural and Peri-Urban Advisory Committee, Landcare and other community groups to develop the draft Rabbit Action Plan 2020–24, which will be available for community comment from July 2020.
	


*Major Initiative
Local Government Performance Reporting Indicators 

To help measure performance across all Victorian councils in a transparent and accountable way, we report to Local Government Victoria on the following mandatory indicators:
	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Waste Collection
	
	
	
	
	

	Satisfaction

Kerbside bin collection requests
[Number of kerbside garbage and recycling bin collection requests / Number of kerbside bin collection households] x1,000
	194.37
	236.69
	256.80
	256.85
	Requests for additional bins increased following directives from the state government to work from home where possible, as part of COVID-19 restrictions.

	Service standard
Kerbside collection bins missed
[Number of kerbside garbage and recycling collection bins missed / Number of scheduled kerbside garbage and recycling collection bin lifts] x10,000
	9.21
	9.29
	9.71
	12.14
	The rate of bins being missed increased this financial year because: 
· new drivers are missing bins during their learning period

· there’s been a slight increase in the number of bins not being on the kerb by collection time

· cars blocking bins in denser suburbs have led to second collections 
· new collection routes in housing estates can increase the chance of human error. 

	Service cost
Cost of kerbside garbage bin collection service
[Direct cost of the kerbside garbage bin collection service / Number of kerbside garbage collection bins]
	$101.24
	$100.71
	$104.98
	$115.38
	Costs are in line with increasing properties and rises in contract and disposal costs.


	Service cost
Cost of kerbside recyclables collection service
[Direct cost of the kerbside recyclables bin collection service / Number of kerbside recyclables collection bins]
	$25.70
	$28.75
	$37.58
	$57.40
	Increasing costs in 2019–20 were due to:

· the collapse of our former recycling contractor 
· new contractor costs

· a fall in global prices for all recyclable materials 

· higher processing costs for recycled products.

	Waste diversion
Kerbside collection waste diverted from landfill
[Weight of recyclables and green organics collected from kerbside bins / Weight of garbage, recyclables and green organics collected from kerbside bins] x100
	56.32%
	54.75%
	54.00%
	55.73%
	Green waste and recycling ratios have been relatively consistent over the past few years. 

The growing population is increasing green organic and waste tonnage, but recycling tonnage has remained the same because of changes in product stream, newspapers and glass content.


VIBRANT ARTS AND CULTURE

We treasure Geelong’s culture and heritage and will help our creative community to grow.

LINKS TO THE CLEVER CREATIVE VISION:
[image: image33.jpg]CREATIVITY DRIVES CULTURE




[image: image34.jpg]A DESTINATION THAT
ATTRACTS LOCAL AND
INTERNATIONAL VISITORS





Achievements 
· Council endorsed the Our Heritage, Our Collection strategic report, which is designed to help us better manage our heritage collection.

· Council allocated $510,000 to a COVID-19 recovery response for the arts, culture and heritage sectors, including employment opportunities, recovery grants and funding to support skills training.  

· We established the Geelong COVID-19 Arts Recovery Panel, an arts sector representative group established to explore the impact of the global pandemic on the local arts community.
· We hosted seven major exhibitions at the National Wool Museum. 
· We collaborated with the Torch Foundation to showcase the work of Aboriginal and Torres Strait Islander artists, as part of National Reconciliation Week.  

· We launched six interactive videos as part of the online StoryCraft Program.

· We supported The ExChange, an international folk music conference for the Australia and New Zealand music industry, which was held here in March 2020. 

· We distributed $220,210 to community festivals and arts projects through the 2019–20 Creative Communities Grants Program. 
Focus areas

· Attracting new creative industries and supporting existing ones.

· Supporting the creative and cultural sector to seek funding from a range of sources.
Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image35.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	Status

	Increased number of objects actively cared for within our arts and heritage collections.
	Annual
	11,971^
(30 June 2018)
	Increase
	12,475
(30 June 2020)
12,273^
(30 June 2019)
	We added 200 new objects to the National Wool Museum Collection in May 2020 and we also acquired two objects as part of the Maritime Collection. 
	


^ We completed an audit as part of Our Heritage, Our Collection. This revealed that 5,354 objects of the Maritime Museum Collection belonged to the Maritime Association and had been incorrectly reported in the data (baseline and 30 June 2019). This has now been corrected. 


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	Status

	Increased access to cultural collections through online engagement.
	Annual
	49,093

(30 June 2018)
	Increase
	157,767

(30 June 2020)
68,815

(30 June 2019)
	The 68,815 reported at 30 June 2019 did not accurately capture some of our online engagements, which are now included in the current data.
	

	Increase in the percentage of active library borrowers in the municipality

	Annual
	19.28%

(2016–17)
	20%
	17.57%

(2019–20)

18.20%
(2018–19)


	The definition of this indicator changed in 2019–20 and now averages the past three years data. The result is therefore not comparable to past years. 
COVID-19 restrictions had a significant impact on collection use as Geelong Regional Library Corporation branches were closed from 19 March to 8 June, then opened to restricted hours and patron limits.

Note this indicator only measures collection item loans and doesn’t capture other library activity, such as events, programs, Wi-Fi use and in-library attendance.
	

	Increased employment in creative occupations.
	Every five years
	4.75% of total employment
	Increase
	-
	Data for this will not be available until the next Census results are released in 2021–22.
	

	Maintained visitation to our key cultural facilities: National Wool Museum (NWM), Potato Shed, Geelong Gallery, Courthouse Youth Arts (CYA), Geelong Library & Heritage Centre (GL&HC). 

	Annual
	NWM 851,879 

Potato Shed 108,444 

Geelong Gallery 116,940 

CYA 

13,940 

GL&HC 456,934 
(2017–18)
	Maintain
	NWM 806,404 

Potato Shed 67,051 

Geelong Gallery 46,836 

CYA 

5,995
GL&HC 320,813 

(2019–20)
	COVID-19 restrictions had a significant impact on visitor numbers at all cultural facilities.
	[image: image36.jpg]





	Four-year council plan priorities
	2019–20 actions
	Progress comment
	       Status

	Incorporate arts and cultural initiatives into infrastructure development, to enhance our sense of place.
	
	We started exploring the potential to include heritage objects and display areas into our new Civic Precinct. We also started working with Revitalising Central Geelong on a Digital Placemaking project for the next stage of the Green Spine.  
We refreshed the Potato Shed Redevelopment Business Case and carried out further community engagement and project management for the Sunken Gallery at The Dell. 

We helped progress the TAC Road trauma memorial artwork, 'Solace', at Limeburners Point and completed a new mural as a part of street beautification works in St Leonards. 

We also continued to look for new opportunities to enhance current and new developments with artwork.
	   



	Recognise and share our heritage through storytelling.
	
	We launched the Bronze Stories Public Art Trail. This project, which tells local stories on bronze plaques outside historic sites in Central Geelong, was completed by a local artist. 

We completed an intangible heritage report, as part of the Mountain to Mouth review. The review, completed by a social historian, recommended a refreshed approach to collecting and curating intangible heritage. As part of the process, heritage film that will be useful for other projects was also curated.

We started a review of the Connecting Memory app to explore future story-gathering directions, maximise community access to the collection and to resolve functionality issues. We also added three new stories about ANZAC Spirit to the app and continued development of an interpretative trail commemorating our ANZAC heritage in Armstrong Creek.  

We launched two online exhibitions - Our Heritage, Our Collection and We The Makers 2020. We also launched four online, interactive craft activities – one in collaboration with the Geelong Regional Library Corporation. 

Finally, we started upgrading the core wool story galleries with extended images from the 'Invisible Farmer Project’ at the National Wool Museum. 
	   



	Work with the Geelong Regional Library Corporation to deliver efficient and effective services and programs.
	
	We completed the final evaluation report for the redevelopment of the Geelong Library and Heritage Centre, funded by Regional Development Victoria. The report identified project outcomes and achievements in the first five years. 

We continued to support the Word for Word National Non-Fiction Festival and helped deliver the StoryCraft program through a partnership with the National Wool Museum. 

We continued to provide funding and services to the library network and were represented on the committee of management. 
	

	
	
	
	

	Recognise and celebrate Geelong’s Aboriginal culture and history.
	Continue to work across all Council events to link and emphasise Aboriginal culture and history.
	We’ve secured approvals and permits to remove and conserve the Queens Park Scar Tree. 
In partnership with Aboriginal artists, the National Wool Museum hosted exclusive masterclasses, as part of The Design Series, exploring creativity with fibre, weaving, textile fibre. The museum also partnered with the Geelong Regional Library to present StoryCraft, based on the book My Country, by Ezekiel Kwaymullina.
For National Reconciliation Week in May/June 2020, we worked in partnership with The Torch Project to deliver an online exhibition of Aboriginal artwork by men currently detained in prison. A digital showreel of the artworks was also created for NAIDOC Week (rescheduled to November 2020).

We worked with Wadawurrung Elders, artists and advisors on several projects, including:                                                                                                  

· the Strong Brother Strong Sister partnership, an Aboriginal Youth song-writing mentorship project

· the Green Spine Triangle

· the launch of Bronze Stories at Johnstone Park

· Wadawurrung translations of Geelong’s endangered bird species 

· the Armstrong Creek Town centre

· upcoming online craft and making programs for the National Wool Museum
· the Mountain to Mouth Review

· the Geelong COVID-19 Arts Recovery Panel.
	   (

	Work with galleries and museums to improve our public art and heritage offering.
	Continue remedial works of Osborne House.*
	We completed minor maintenance works in 2019 and Council approved a list of further maintenance and improvement works that will cost $900,000–$1.1 million. 
We developed a tender focused on repairs to key heritage aspects of the building and investigated other minor works, separate to the approved tender.
	

	Attract new and support existing creative industries.
	Continue the support and delivery of Geelong’s iconic arts and cultural events and programs.
	We delivered and supported arts and cultural events at the National Wool Museum, including Happy Birthday Play School – Celebrating 50 years and Art Quilt Australia. We also commissioned a major art work featuring 80 vegan taxidermy (papier-mâché) models of local endangered bird species, as well as a display that engaged over 1,000 students.
We supported the Geelong Arts Centre’s Reflex: The future of our creative community forum in November 2019, which was for  local artists and creative businesses.
Unfortunately, many scheduled events were impacted by COVID-19 restrictions and had to be either changed, suspended or cancelled. 
	    [image: image37.jpg]





	Four-year council plan priorities
	2019–20 actions
	Progress comment
	       Status

	
	Support the development and promotion of local artists, arts organisations and live music.
	We announced the successful Creative Communities Grant applicants in November 2019, with $211,510 distributed across 14 community festivals and 25 community arts projects. 

We promoted local artists and organisations through the StoryCraft online program and delivered 250 craft and making packs to local schools with locally-sourced supplies and books. We also commissioned local artist and fabricator Simon Lucio - SPEL Designers as part of We The Makers installation and fabrication.

We supported the first of three capacity building workshops for musicians, Meet the Locals, and partnered with Music Victoria to deliver the Geelong Music Venues Day. 

We continued to develop a locally-focused website for musicians, venues and audiences and created a Spotify playlist titled 'Sounds of Geelong'. 
We participated in several music industry discussions, including the Victorian Government’s Live Music Roundtable, and supported the The Folk Alliance International conference in Geelong.
While COVID-19 restrictions led us to postpone some capacity-building workshops, these were rescheduled with a post-COVID focus for July 2020. The Live Music Plan Advisory Group also met to discuss COVID-19 challenges. 
To help us further  investigate and address the impact of COVID-19 on arts and cultural industries, we appointed twenty-one leading cultural and creative practitioners to the Geelong COVID-19 Arts Recovery Panel in May 2020.
	   (

	
	Assist cultural venues to cross-promote programs and events.
	As well as supporting the 2020 Potato Shed Season launch, we are also refreshing the business case for this multi-arts venue. 
At the National Wool Museum, we exhibited Without Consent and National Geographic Wildlife Photographer of the Year 55 Exhibition. The museum also worked with Geelong Library to present StoryCraft, based on book My Country by Ezekiel Kwaymullina.

We renewed four-year funding agreement to support delivery of Platform Youth Arts Strategic Plan 2019–21 and renewed the Back to Back Theatre lease at the Old Courthouse Building

We supported the Geelong Arts Centre’s Reflex: The future of our creative community forum in November 2019, which was for  local artists and creative businesses.

We continued to support the Geelong Regional Library Corporation through a broad range of funding, operational, committee and maintenance program mechanisms.
Finally, we continued to produce the Geelong Region ArtsAtlas and Arts Bulletin.  
	   (

	Deliver UNESCO City of Design creative outcomes, including:

· National Wool Museum Master Plan

· Geelong Gallery redevelopment

· Mountain to Mouth

· Geelong After Dark

· cultural trails.
	Adopt and implement recommendations of the Strategic Plan for Use and Management of Geelong’s Heritage Assets.
	We completed a heritage asset audit and the Our Heritage, Our Collection strategic report, which will help us better manage and provide access to the 12,000 moveable artworks, objects and artefacts in our heritage collection. The report was adopted by Council in April 2020. 

We launched the Our Heritage, Our Collection website and online exhibition in April 2020, highlighting 50 objects from the heritage collection that were curated by the themes of ‘War, Wool and Work.’
We added a HerStory Trail to the Geelong Arts and Culture Trails app, celebrating stories of significant women of Geelong. 

We cleaned, crated and moved the City Hall stained glass window to our collections storage. 
	   (

	
	Adopt and implement the first year of the Cultural Strategy.
	We completed our research, finalised requirements, developed key actions, timelines and drafted an engagement plan for the Arts and Culture Strategy in 2019–20. The Stage 1 research included a cultural mapping report.  

Stage 2 and engagement actions have been postponed until August 2020, due COVID-19 restrictions.  As a result, the strategy will now be completed in March 2021.
	   [image: image38.jpg]




	
	Undertake the Geelong Gallery redevelopment business case in partnership with the Geelong Gallery.
	We started working with the Geelong Gallery to determine the feasibility of expanding the gallery space into City Hall.

We secured funding in the 2020–21 budget to develop a business case for the redevelopment and anticipate this will be completed by June 2021. 
	


*Major Initiative
Local Government Performance Reporting Indicators 

To help measure performance across all Victorian councils in a transparent and accountable way, we report to Local Government Victoria on the following mandatory indicators:
	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Libraries
	
	
	
	
	

	Utilisation

Physical library collection usage
[Number of physical library collection item loans / Number of physical library collection items]
	6.12
	6.06
	5.96
	4.45
	The definition of this indicator changed in 2019–20 to exclude eCollections, so results are not comparable to previous years. 

COVID-19 restrictions had a significant impact on collection use as Geelong Regional Library Corporation branches were closed from 19 March to 8 June, then opened to restricted hours and patron limits.  

	Resource standard
Recently purchased library collection
[Number of library collection items purchased in the last 5 years / Number of library collection items] x100
	73.71%
	72.46%
	74.08%
	73.18%
	Purchase of new items was not impeded by COVID-19 restrictions, maintaining a high proportion of resources less than five years old.

 

	Participation
Active library borrowers in the municipality
[The sum of the number of active library borrowers in the last 3 financial years / The sum of the population in the last 3 financial years] x100
	19.28%
	18.17%
	18.20%
	17.57%
	The definition of this indicator changed in 2019–20 and now averages the past three years data. The result is therefore not comparable to past years. 
COVID-19 restrictions had a significant impact on collection use as Geelong Regional Library Corporation branches were closed from 19 March to 8 June, then opened to restricted hours and patron limits.
Note this indicator only measures collection item loans and doesn’t capture other library activity, such as events, programs, Wi-Fi use and in-library attendance. 

	Service cost
Cost of library service per population
[Direct cost of the library service / Population]
	$34.43
	$35.36
	$36.83
	$37.00
	Annual labour cost rises have increased overall costs slightly. In addition, operational expenses increased after the new Leopold Library opened in 2018–19. 


As part of the ongoing review and improvement of reporting, Local Government Victoria retired the following indicator:
	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Libraries
	
	
	
	
	

	Service cost
Cost of library service
[Direct cost of the library service / Number of visits]
	$4.70
	$5.09
	$5.49
	Retired in 2020
	As of 1 July 2019, this indicator was replaced by an amended Cost of library service per population measure.


INTEGRATED TRANSPORT CONNECTIONS

Our focus will be on improving our public and active transport, and better connecting our networks.
LINKS TO THE CLEVER CREATIVE VISION:
[image: image39.jpg]A FAST, RELIABLE AND
CONNECTED TRANSPORT
NETWORK





Achievements 

· Council adopted the Shared Trails Masterplan, a 10-year plan that aims to create a fully-connected network of shared trails across the region.

· We completed the western link of the Building Better Bike Connections Project, which connects Geelong’s western suburbs to Central Geelong. 
· We started to develop a parking strategy for Central Geelong, following extensive consultation with the community and a range of key stakeholders.

· We maintained over 16,000 kilometres of sealed roads and 470 kilometres of unsealed roads.
Focus areas

· Balancing the maintenance and renewal of aging existing infrastructure with the delivery of much needed new assets.
· Advocating for the transport infrastructure and services needed to sustainably support our rapidly growing population.
Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image40.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete



	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	Status     

	Increased kilometres of bicycle and walking paths.
	Annual
	206 km bike paths

1,674 km footpaths
(June 2018)
	Increase
	223 km bike paths
1,822 km footpaths

(June 2020)
210 km bike paths

1,755 km footpaths
(June 2019)
	Bike paths have increased by 13 km this year and 17 km since the baseline measurement.

Footpaths have increased 67 km this year and 148 km since the baseline measurement.

	

	Increased community satisfaction rating with sealed local roads.
	Annual
	49

(2018)
	60
	60

(2020)
54
(2019)
	Community satisfaction with sealed local roads has increased by 6 index points since last year.
	


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	Status     

	Renewal gap for road management reduced.
	Annual
	$4.5 million

(2017)
	Reduce
	$3 million

(2020)
$3 million

(2019)


	The asset modelling data that produces this result has not changed. 

New condition assessment data and modelling are due by the end of 2020.
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status

	Support projects in the G21 Region Road Transport Plan.
	
	We continued to support Regional Roads Victoria and Major Projects Victoria to deliver the Drysdale Bypass, Barwon Heads Road duplication, safety improvements on the Bellarine Highway and planning for freight movement initiatives. 

G21 has supported an integrated transport plan for Geelong as a priority project.
	

	Work with VicRoads to deliver the Network Operating Plan, to improve bus services.
	Adopt the Transport Network Operating Plan including recommendations from the Bus Services Review.
	We engaged with the community to hear their views on the draft Transport Network Operating Plan. The plan expanded from Central Geelong to include the whole municipality.

We supported the Department of Transport to help them prepare an integrated transport plan for Geelong.
	

	Improve our road management and engagement program.
	
	We continued to develop an online interactive map to inform our community about infrastructure projects under construction across the municipality.

We also continued to improve our road management and engagement programs, which was reflected in a 6-index point increase in our community satisfaction survey result for sealed local roads this financial year (see measures table above). 
	

	Deliver better-connected walking, cycling and trail paths across our region.


	Implement council program of infrastructure upgrades including streets, roads and drains.
	We completed the pavement rehabilitation of Ormond Road, East Geelong and started planning the upgrade for McClelland Road, Lara.

In addition, we commenced:

· widening of Anakie Road, north of the ring road, to improve safety and access for heavy vehicles

· two major drainage projects to mitigate flooding of properties at Epworth Street, Ocean Grove, and Coriyule Road, Curlewis.
	

	
	Upgrade and deliver new footpaths, cycling and trail paths and create linkages between paths.
	We completed the western link of the Building Better Bike Connections Project and started designing the southern link. We have also officially opened Stage 1 of the Hovells Creek shared trail path in Lara.

We started constructing a new footpath on Breakwater Road, adjacent to the Geelong Showgrounds and Racecourse, and on Surfcoast Highway, Grovedale, to link existing shared trails.
	

	
	Review and implement Greater Geelong Cycling Strategy.
	The review of The Greater Geelong Cycling Strategy is on hold, as we may incorporate it into a broader municipal wide transport strategy.
	Not started

	
	Undertake detailed design to create linkages between shared paths across the region.
	We engaged with the community to help inform the Shared Trails Masterplan. Council adopted this plan in March 2020, and we commenced implementing the actions.
	

	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status

	Advocate to improve rail, road and sea connections for our region.
	Lead the Regional Fast Rail Advocacy Alliance.*
	We continued to advocate for a fast rail connection between Melbourne and Geelong by:

· being active members of the Victorian Government Geelong Fast Rail Reference Group (Mayor and CEO)
· partnering with the City of Wyndham to write to the Victorian Government about the issue
· meeting with the Minister for Transport Infrastructure 
· advocating to the Secretary of Transport for improved transport connections (February 2020)
· leading the regional fast rail alliance, which advocates for a regional-wide approach to fast rail for Geelong, Ballarat, Bendigo, Shepparton and Latrobe.
	

	
	Explore opportunities to enable the Geelong- Melbourne ferry service.
	The twice-daily ferry service to Docklands from Steampacket Quay commenced in December 2019. 
The service was suspended, due to COVID-19 restrictions, but recommenced with a reduced timetable for weekends only.

The company plans to recommence full services once the restrictions are lifted.
	

	Work with government to improve freight connections to the Geelong Port.
	
	We worked with Geelong Port to plan for future port access via road and rail.

We welcomed the news that TT-line is moving its Spirit of Tasmania ferry service to Geelong Port, and are working with them to provide safe access to the new terminal.
	

	Advocate and plan for a second container port at Bay West.
	
	We continued to advocate for a second container port at Bay West with various Geelong partners, including G21, Committee for Geelong and Regional Development Victoria.
	

	Support further international flights at Avalon.
	
	Tourism Greater Geelong and The Bellarine continued to support Avalon Airport via a tourism partnership, although visitor information services were suspended when Avalon Airport closed due to COVID-19 restrictions. This work will continue once the airline environment is better understood.
	   [image: image41.jpg]




	Support the redevelopment of the rail station precinct, including a modern bus terminal.
	
	We continued to support Victorian Government precinct planning for the rail station, via the Central Geelong Revitalisation partnership. The project was also included in the new City Deal funding agreement.

We anticipate the urban planning framework, which will include the Geelong train station area, will be finalised in mid-2021.
	

	Deliver the Better Bike Connections project.
	Progress Better Bike Connections, west and southern routes.
	We completed the construction phase for the western link. We started designing the southern link of the project and plan to commence works in the second half of 2020.
	


*Major Initiative
Local Government Performance Reporting Indicators 

To help measure performance across all Victorian councils in a transparent and accountable way, we report to Local Government Victoria on the following mandatory indicators:
	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Roads
	
	
	
	
	

	Satisfaction of use

Sealed local road requests
[Number of sealed local road requests / Kilometres of sealed local roads] x100
	94.10
	59.46
	45.70
	85.86
	We have applied a more rigorous methodology to our recent reporting processes and expect our future data to be aligned with our 2019–20 results.

	Condition
Sealed local roads maintained to condition standards
[Number of kilometres of sealed local roads below the renewal intervention level set by Council / Kilometres of sealed local roads] x100
	91.98%
	95.65%
	95.30%
	91.86%
	Our sealed local roads are consistently maintained to the required standards.

	Service cost
Cost of sealed local road reconstruction
[Direct cost of sealed local road reconstruction / Square metres of sealed local roads reconstructed]
	$213.27
	$199.05
	$177.83
	$201.39
	Cost variations are expected, as they depend on the weather and the scope of works required.

	Service cost
Cost of sealed local road resealing
[Direct cost of sealed local road resealing / Square metres of sealed local roads resealed]
	$16.92
	$17.18
	$16.45
	$18.23
	Local road resealing includes spray seals and asphalt. In 2019–20, we undertook a higher percentage of asphalt resurfacing compared to previous financial years. As asphalting has a higher unit cost, this has resulted in increased average costs. 

	Satisfaction 
Satisfaction with sealed local roads
[Community satisfaction rating out of 100 with how council has performed on the condition of sealed local roads]
	47
	49
	54
	60
	Our Roads to Success in-house business improvement program, improved engagement and online interactive map of infrastructure projects has led to an increase in community satisfaction of 13 index points since 2017.


A THRIVING AND SUSTAINABLE ECOMONY

We will capitalise on Geelong’s incredible economic opportunities.

LINKS TO THE CLEVER CREATIVE VISION:
[image: image42.jpg]A PROSPEROUS ECONOMY
THAT SUPPORTS JOBS AND
EDUCATION OPPORTUNITIES





Achievements 

· In 2019, the Regional Industry Sector Employment program (RISE) won the Economic Development Australia National Award for Excellence (Community Collaboration category) and was a finalist in the Victorian Training Awards Industry (Collaboration category).  
· We helped 370 businesses adapt to the impact of COVID-19 restrictions through the Geelong Business Support Program.
· We were also chosen as a finalist for the 2019 Economic Development Australia National Awards for Excellence (Economic Development Initiatives over 15,000 residents category) for our implementation of the Sustainable Agribusiness Strategy for the G21 Region 2017–2022. 
· We supported several programs for business in the region, including: 

· Geelong Small Business Festival (44 events and 3,000 attendees) 

· Business Victoria workshops

· mentoring through Business Victoria’s mobile business centre

· free social media promotion for local businesses.
· We supported Clean Tech Innovations Geelong’s second Procurement for Innovation process, which called for tenders to generate road, footpath and kerb surface materials from kerbside recycling collection. 

· We delivered seven online events for the first-ever Geelong Design Week after the City-led events were cancelled due to COVID-19 restrictions.  

Focus areas

· Identifying opportunities for Geelong to leverage and benefit from our UNESCO designation. 
· Targeting industry growth in agribusiness, clean technology and advanced manufacturing.
Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image43.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	      Status      

	More businesses within the municipality.
	Annual
	17,336 businesses
(30 June 2017)
	Increase
	17,995 businesses
(30 June 2018)

18,850 businesses

(30 June 2019)
	Businesses increased 855  in 2019–20, and by 659 in the previous financial year.
	


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	      Status      

	15 years of industrial land supply planned.
	Annual
	21 years
(September 2018)
	Maintain
	28 years
(June 2018)

28 years

(June 2019)


	There are a range of industrial development areas for new and existing businesses, however there’s a shortage south of the Barwon River. The North East Industrial Precinct and West Employment Precinct at Armstrong Creek will be important to address this local shortage of supply.
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status

	Continue to work with government to deliver projects that revitalise Central Geelong.
	Work with Victorian Government to implement Central Geelong Action Plan.
	We continued to work with the state government to deliver the Revitalising Central Geelong Action Plan and the program of capital works under the Geelong City Deal. 
Arrangements to complete the next section of work on the Green Spine are in place. The project is now being implemented by the Victorian Government through Regional Roads Victoria.   

The delay in this action was a result of Geelong City Deal announcements and the finalisation of new governance arrangements.
	

	Work with government to deliver City Deal projects.
	
	The Geelong City Deal Implementation Plan was released in October 2019. As members of the implementation committee, we met monthly with federal and state government representatives.

We developed a plan for the rollout of the Smart City initiatives identified in the City Deal, which include Smart Parking and the use of sensor technology to provide real time data. 

We completed the Gheringhap Street drain project, a key project to improve water flow through Central Geelong.

In partnership with the Royal Geelong Yacht Club, we started work on the Geelong Safe Harbour Precinct Project. The club started installing the wave attenuator, but damage to some pontoons caused delays and works are expected to be complete by late 2020. 
	

	Use Geelong’s UNESCO City of Design award to secure economic development projects.
	Collaborate with partners to deliver projects that support the UNESCO City of Design goals of sustainable cities and communities.
	We attended the City of Design Sub Network meeting in Detroit, presented at the UNESCO Asia Pacific Creative Cities Conference in Adelaide, partnered with Deakin University to present the first three lectures in the Clever and Creative Lecture Series and hosted three Geelong Pecha Kucha events, where 60 community members presented on their design-led projects.
We met with our fellow Victorian Creative Cities of Melbourne, Ballarat and Bendigo to sharing information and resources and coordinate our approach to state and federal governments.
We appointed a consultant to work on the UNESCO framework plan process and engage with important internal and external stakeholders. 
Although we were ready to deliver over 80 events during Geelong’s Design Week in March 2020, many events were cancelled due to COVID-19 restrictions. Despite this, seven events still went ahead online.  

We developed a City of Design Champion program and assigned 18 champions. 

In partnership with Montreal, we progressed a Code Souvenir Program to support local designers. 

We reviewed the annual monitoring reports on behalf of the UNESCO City of Design sub-network.
	   (

	Attract new investments to the region
	Advocate for Geelong businesses and major projects that contribute to regional economic development.
	We worked with several potential investment opportunities and businesses across several industry sectors.
Cleantech have committed funds to five scalable demonstration projects in Geelong. These projects respond to Geelong's challenges in either waste, water or energy.

We have supported Hanwha in their bid to manufacture howitzers and Land400 tanks in Geelong. Hanwha was selected as one of the final two businesses to build four tanks for testing. Through the Geelong Defence Alliance, we assisted them in their search for land in the Geelong region. 
We worked with Surdex Steel, Glencore and Elgin Energy to help them establish their businesses in the region, along with other businesses, including a registered training organisation and day spa.

Through the Better Approvals Process, we assisted 132 businesses with regulatory advice, preferable business locations and Council permit applications. 
	   (

	
	Make decisions to support the start-up and entrepreneurial ecosystem.
	Our partnership program with ManuFutures to help build capacity, refine ideas and provide pathways for start-ups and entrepreneurs with a manufacturing focus was cancelled due to COVID-19. 
	      


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status

	Help to renew industrial precincts.
	Develop screening strategies to improve the entrance into Geelong.
	We identified key areas of focus for landscape improvements and finalised plans. Minor works will be implemented during 2020–21, while additional works will be the subject of future budget bids.
	   (

	
	Integrate the Retail Strategy 2016–36 into the Greater Geelong Planning Scheme.
	Independent planning panel hearings for Amendment C393, that will implement The City of Greater Geelong Retail Strategy 2016–36 into the Greater Geelong Planning Scheme, were conducted between October 2019 and January 2020. 

We received the panel report and the Amendment will be considered by Council in their meeting on 25 August 2020.
	

	Execute strategies for economic growth in the region’s north.
	Promote the economic assets and investment opportunities in the region’s north.
	The Regional Industry Sector Employment Program (RISE), a collaboration led by the City and funded by Gforce, reached the end of its two-year pilot, but was extended into 2020–21. In 2019, the program won the Economic Development Australia National Award for Excellence (Community Collaboration category) and was a finalist in the Victorian Training Awards Industry (Collaboration Category).   
	   (

	
	Continue to deliver the Regional Industry Sector Employment (RISE) Program to support jobs in the construction industry.
	The RISE Program continued in 2019–20. Program 7 was completed but Program 8 was cancelled due to COVID-19 restrictions. 
Sponsorship funding was secured from Gforce to continue the program into 2020–21. We will continue as lead of the program with a revised training program, following a review by The Gordon. There are 29 candidates registered for the next program.  
	   (

	Support and promote local businesses, markets and products.
	Trial a flexible parking solution for the CBD.*
	We introduced free 30-minute weekday car parking in two-hour zones in Central Geelong in December 2019. To achieve this, we had to integrate several different technologies, including a new parking app, license plate recognition technology, digital upgrades to parking machines and a new data platform. 
	 (


*Major Initiative
GROWING OUR TOURISM AND EVENTS

Our tourism and events offering is strong, but we aim to grow it further.

LINKS TO THE CLEVER CREATIVE VISION:

Achievements 
· We introduced a new Community Events grant stream, allocating $170,000 to support 32 community events.

· We completed and opened the Geelong Botanic Gardens Sustainable Visitor facility.

· We attracted new major events to the region, including the Victorian Teachers Games and the Geelong Tennis International tournament.  

· We partnered with the Australian Federation of Disability Organisation to support over 100 local tourism businesses to review their operations and improve accessibility.

· Tourism Greater Geelong and The Bellarine won two gold awards at the 2019 Victoria Tourism Awards (‘Visitor Information Services’ and ‘Tourism Education and Training’ categories).

· We hosted two major tourism conferences – the Victorian Tourism Industry Council Conference and the Australian Cruise Association Conference – and welcomed over 600 delegates to the region.

· We helped over 127,095 visitors through the Geelong Visitor Information Service network.

· We delivered an extensive program for the Geelong Seniors Festival, with over 10,000 attendees.

· We launched a new online listing for virtual community events.
Focus areas

· Providing additional accommodation to support visitor demand.

Supporting growth in lifestyle and tourism sectors, while protecting our region’s unique environment.
Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image44.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	 Status

	Annual increase in visitors.
	Annual
	5.1 million

(Apr 17 to Mar 18)
	2.1% per annum
	6.0 million# (Apr 19 to Mar 20) 
6.0 million^ (Apr 18 to Mar 19)
	An increase of 0.2 per cent.

	

	Annual increase in expenditure by visitors.
	Annual
	$936 million (Apr 17 to Mar 18)
	3.8% per annum
	$1.1 billion# (Apr 19 to Mar 20)
$1.1 billion^ (Apr 18 to Mar 19)
	An increase of 1.7 per cent. 


	

	Annual increase in international overnight visitors.
	Annual
	55,900

(Apr 17 to Mar 18)
	4.9% per annum
	56,900#
(Apr 19 to Mar 20)
61,800^
(Apr 18 to Mar 19)
	A decrease of 7.9 per cent.

	

	Annual increase in domestic overnight visitors.
	Annual
	1.3 million

(Apr 17 to Mar 18)
	1.9% per annum
	1.6 million# (Apr 19 to Mar 20)
1.6 million^ (Apr 18 to Mar 19)
	A decrease of 1.3 per cent.

	

	Annual increase in tourism employment.
	Annual
	Estimated 5,906

(2017–18)
	1.6% per annum
	Estimated 5,961

(2019–20)
Estimated 6,226

(2018–19)
	A decrease of 4.3 per cent. Tourism employment was adversely impacted by the restrictions COVID-19 restrictions. 
	   [image: image45.jpg]




	Return on investment of Geelong major events to the municipality.
	Annual
	46:1

(2017–18)
	30:1
	45:1

(2019–20)
49:1

(2018–19)
	$53 million of event spending was generated, despite six major events being cancelled due to COVID-19 restrictions.
	


^Data reported in the 2018–19 annual report was for the period January 2019 to December 2019 and has been corrected in this report.

#There has been a methodology change in the collection of tourism data, so caution should be applied when comparing results from January 2019 onwards.

	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status

	Work with government to deliver City Deal tourism infrastructure projects, including the Convention and Exhibition Centre.
	
	The Geelong City Deal Implementation Plan was launched in October 2019, outlining milestones and next steps for several tourism infrastructure projects, including the Convention and Exhibition Centre. 
We participated in the Geelong City Deal Advisory Group and  2019–20 and will continue to be a key stakeholder in the development of the project.
	

	Deliver the Visitor Economy Strategy 2017–21 and the Tourism Development Plan.

	Support Geelong Yacht Club to implement stage one of the Geelong Waterfront Safe Harbour Master Plan.*
	We signed a funding agreement with the Royal Geelong Yacht Club for Stage 1 of the project. 
The club started installing the wave attenuator, but damage to some pontoons caused delays and works are expected to be complete by late 2020. 

The club submitted planning application to seek approval for the building developments and started working to resolve the lease boundary.
	

	
	Construct and launch the first stage of the Sunken Gallery.
	Following community engagement in October 2019, we revised the project plan to better align with the community’s preference for a more localised attraction managed using good governance principles. These changes delayed the project, as did COVID-19 restrictions.
	

	
	Open the Geelong Botanic Garden Sustainable Visitor Facility.
	Our new facility was completed and opened to the public. Further landscaping and irrigation works will continue into 2020–21. 
	   (

	
	Update the Tourism Development Plan to identify new priority infrastructure projects (public and private).
	The Greater Geelong and The Bellarine Tourism Development Plan 2019–22 was completed. 
Tourism Greater Geelong and The Bellarine continued working with key stakeholders to advocate for the planned outcomes.


	   (   

	
	Support and grow international education as part of the local visitor economy.
	Tourism Greater Geelong and The Bellarine's Study Geelong program continued to support and grow international education through initiatives including: 
· Student Ambassador Program

· Mentor Program

· My Geelong Tour Guide Program

· partnerships developed with Avalon Airport and Air Asia X.

Some projects were placed on hold or transitioned online in response to COVID-19 restrictions. 
Council approved Study Geelong support initiatives on 30 June 2020, to provide further support to international students living in the Greater Geelong community.
	

	
	Participate in the development of the You Yangs and Serendip Sanctuary Master Plan.
	Tourism Greater Geelong and The Bellarine provided input into the draft master plan, which is a Parks Victoria initiative. 
We were also represented on the You Yangs Precinct Project Control Group. 
The draft master plan will be released for a final community consultation period in 2020–21. 
	

	
	Support the development of shared trail linkages to create a trail network across the region.
	Tourism Greater Geelong and The Bellarine provided advice in relation to the Shared Trails Master Plan linking key tourism assets and destinations.
	   ( 


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status


	Build on the current events program and increasing cross-promotional opportunities.
	Establish and fund the Community Events Grant Fund.
	We established the Community Events Grants, designed to support moderate-sized events that:

· bring economic benefits to Greater Geelong
· enrich the community

· celebrate common interests

· provide opportunities for local participation.

We ran two grant rounds and awarded a total of $169,900 to 57 community organisations. All successful applicants were required to submit a COVID-19 safety plan. 
	   (

	
	Continue to drive visitation by supporting local events.
	In partnership with Geelong Major Events, Tourism Greater Geelong and The Bellarine supported local events through extended marketing and promotion, including Deakin  University Open Day and Victorian Teachers’ Games. 

Following the introduction of COVID-19 restrictions, we transitioned our promotion to focus on businesses with delivery and take-away services and campaigns encouraging the community to support and buy locally.
	     [image: image46.jpg]





*Major Initiative
INNOVATIVE FINANCES AND TECHNOLOGY

Clever and sustainable financial management, matched with digital growth, will advance our future.
LINKS TO THE CLEVER CREATIVE VISION


Achievements 

· We provided $5.165 million in financial support to help communities adapt to COVID-19 as part of our 2020–21 budget
· We were the first city within Victoria to install public space ‘Smart Node’ street poles which enable power and connectivity for various devices including CCTV cameras, Wi-Fi access points and ‘Internet of Things’ sensors. 
· We developed the COVID-19 Financial Hardship Policy to provide a framework for financial relief to individuals and businesses who need assistance from the impacts of this pandemic.
· We launched the Geelong Data Exchange allowing the community to view, obtain, utilise and reuse valuable information we and other organisations have gathered.

· We trialled in-ground parking sensors which provide us with a detailed picture of parking activity. 
· We progressed Our Clever Together Project which brings together the building of our new Civic Precinct and the upgrade of our digital capability through our Digital Modernisation Program. 

· We delivered infrastructure enhancements to support and enable over 1,000 employees to remotely work from home as a result of the COVID-19 restrictions.
Focus areas

· Investing in our processes, tools and technology whilst operating under tight financial constraints.
· Leveraging advances in technology that are shifting the world in which we live.

Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image47.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	Status        

	Better Wi-Fi access in community facilities and public spaces.
	Annual
	92 Wi-Fi access points across the City and       11 City-owned facilities with free Wi-Fi
(1 July 2018)
	Increase
	106 Wi-Fi access points across the City and

13 City-owned facilities with free Wi-Fi
(June 2020)

	We added five new Wi-Fi access points this financial year. This is in addition to the nine new Wi-Fi access points and free Wi-Fi at two City-owned facilities last year. Contract delays in the Free Wi-Fi project mean that no new City-owned facilities have been added to the network this year. 
	   


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	Status        

	More online transactions with our customers.
	Annual
	Payments  114,257

Forms   17,517

Requests for service       24,074
(2017–18)
	Increase
	Payments  124,431
Forms   24,109
Requests for service  29,187
(2019–20)
	All online transactions have increased since last financial year – payments  by 7.4 per cent, forms by 43.9 per cent and requests for service by 9 per cent. COVID-19 closures of our customer service centres are the likely cause of this. 
	

	Less than 5 per cent budget variation (actual to budget).
	Annual
	-
	<5% variation
	>5% 
(2019–20)
5% variation

(2018–19)

	The 8.7 per cent variation was caused by better-than-expected gifted assets of $35 million and higher developer contributions. This was partially offset by an operating result that was ($19 million) lower than expected – $10.5 million of which was related to COVID-19 impacts. 
	

	Increased revenue streams.
	Annual
	-
	Increase
	-

	An increase in the ‘rates and charges’ revenue stream was caused by rateable property growth, as well as supplementary valuations.
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status

	Deliver smart technology solutions to areas such as street lighting, parking, waste management and children’s services.
	Install sensor networks to enable the use of smart sensors for services including parking and waste management.
	We introduced a ticketless parking system from 1 December 2019 with a new mobile app that gives users real-time information about parking status and the ability to pay while away from their car. 

In total, 320 sensors have been installed to monitor parking (turnover and occupancy), bins (capacity), mobile devices (people) counting, air quality, weather (wind temperature, UV, rainfall) and soil moisture. 
	   (

	Develop digital tools and technologies to improve service delivery and our customer experience.
	Establish and embed the Smart City Office function.

	We developed communication and stakeholder management plans with a focus on building employees’ knowledge and capacity to better utilise new technologies and data in service delivery. 

We engaged an external consultant to help develop a strategic framework for Smart Cities and  consulted with internal and external stakeholders through workshops and a survey. 
The framework is due for release in late 2020.
	   (

	
	Implement Mobile Maintenance Management System.
	We started investigating the requirements of a new Mobile Maintenance Management System to plan the best way of implementing the chosen product. Responsibility for management of this project changed due to the impacts of COVID-19 on available resources.   
	

	Increase free Wi-Fi in public spaces and community facilities.
	Support greater levels of digital inclusion in the community.
	We continued installing new Wi-Fi points at 57 new locations in Geelong, as part of the Wi-Fi and Enhanced Broadband project. These will be available in the second half of 2020.

Delays in contract finalisation have delayed the Free Wi-Fi and Enhanced Broadband project by six months.
	

	Deliver Smart Cities infrastructure using electronic data collection to better manage assets and resources.
	Install enhanced broadband for the Bellarine.
	We finalised the design and planning approval
phase of this project, which will roll out in stages during 2020. 
We started working on project agreements and procurement for contractor installation. Delays in finalising project agreements and procurement have resulted in a six-month delay. 
	

	Attract more technology-focused businesses to our region.
	
	We worked with several technology focused businesses that wanted to establish themselves in our city-region, across a broad range of areas including:

· transportation

· drone technology 

· shared bike services

· cleantech in agribusiness 

· green waste 

· smart materials

· advanced fibres 

· the health sector. 
	
   

	Examine our budget to fund future initiatives.
	
	We reviewed our budget process and implemented improvements into the 2020(21 budget process, including a new budget timetable and a refined budget bid process to improve efficiency. 

Our draft 2020(21 budget, adopted by Council 30 June 2020, included additional support packages designed to address known and emerging impacts arising from COVID-19.
	
  

	Establish sustainable financial and infrastructure management systems for our future.
	Commence Digital Transformation with a focus on customer experience.*
	Our Customer Experience Program, an initiative of our Clever Together program, is now fully underway. 
We developed a Customer Experience Strategy that highlights six key areas of focus – customer access, service redesign, online presence, billing and payments, customer relationship management and organisational capabilities in our workforce. 

Projects related to service redesign and billings and payments are due to be completed in December 2020. We have also started examining customer access. 
	

	
	Commence implementation of Asset Management Strategy.
	In 2020–21, we started the following background work: 
· a review of data, systems, processes and procedures

· a review of internal roles and responsibilities 
· modelling to assess the impact of increasing renewal gaps, our growing asset base and our ability to support service delivery in the future. 

This is a long-term project that is expected to continue for several years.
	


*Major Initiative
ORGANISATIONAL LEADERSHIP, STRATEGY AND GOVERNANCE

We will be the ‘leading voice’ of the community by delivering confident governance and strategic planning.  
Achievements 

· Council adopted The City of Greater Geelong Sustainability Framework and Action Plan, to encourage and lead a culture of sustainability throughout the organisation and community.

· We established a Redeployment Program to match those employees without work to our community services facing increased COVID-19-related demand.

· We appointed our second Youth Council, to continue to give young people a voice in what we do. 
· We continued live streaming council meetings from the chamber, with 4,836 live views and 3,941 archived views.
· We completed four business improvement projects and supported 22 others across the organisation.
· We delivered the Greater Geelong Clever and Creative Our Progress 2019 report, which highlighted some of the projects and organisations contributing to our community's 30-year vision aspirations. 
· We engaged with the community on major strategies and changes including:

· the draft Social Infrastructure Policy – Our Community Places and Spaces

· the draft Lara Recreation Reserve Masterplan 

· the draft Social Housing Plan 2018–41

· the draft Environment Strategy 2020–30
· our Shared Trails Masterplan

· Ocean Grove Principal Pedestrian Network 

· proposed dog control order changes for Barwon-Coast-managed land.
· We were awarded silver for The City of Greater Geelong Annual Report 2018–19 at the Australasian Reporting Awards.

· We consulted with 800 employees and received 147 written submissions to inform the Working Better Together workplace culture program.
Focus areas

· Adapting how we communicate and engage with our community in a rapidly changing technological landscape.

· Advocating for initiatives that support sustainable prosperity for our community.

Progress report
	
	On track
	
	Needs improvement
	
	Off track
	[image: image48.jpg]



	Off track COVID-19
	
	Not yet available
	(
	Complete


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	  Status

	Increased community satisfaction with overall council performance.
	Annual
	54

(2018)
	>70
	60

(2020)
58
(2019)


	The public’s perception of overall council performance has improved again this year (up from 2 index points since last year and 6 index points from 2018).
	


	Measures of success 
	Frequency
	Baseline
	Target

2022
	YTD

Jun 2020
	Progress comments
	  Status

	Increased community satisfaction with customer service.
	Annual
	70

(2018)
	>80
	73

(2020)
71
(2019)


	Our community’s satisfaction with customer service has increased 3 index points since 2018. This result may be due to a focus on resolving customer enquiries at the frontline and better online transaction options.
	

	Increased community satisfaction in decision-making.
	Annual
	53

(2018)
	>60
	56

(2020)
55
(2019)
	Live streaming of council meetings and community focus meetings continue to have a positive impact on our community.
	

	Increased community satisfaction with community consultation (engagement).
	Annual
	50

(2018)
	>60
	53

(2020)
55

(2019)


	Community satisfaction has decreased slightly, but there has been an overall upward trend over the past four years.  
A new Have Your Say platform and other resources introduced this year have made engagements more accessible to the community, despite COVID-19 restrictions impacting our ability to engage face-to-face.  
	

	Increased community satisfaction with overall council direction.
	Annual
	54

(2019)
	>70
	54

(2020)
55

(2019)
	Community satisfaction has been consistent over the past three surveys and will remain a focus for improvement.
	

	Reduction in Lost Time Injury Frequency Rate. 
	Every three months
	14.9

(June 2018)
	Reduce
	18.1

(June 2020)
32.8

(June 2019)


	This measure was impacted in the last financial year by a changed definition, as well as an increase in the actual number of lost time injuries reported. 

The strong downward trend in the last financial year is likely related to new early intervention programs we introduced. 
	

	Increased employee engagement.
	Annual
	54%

(2017)
	70%
	52% 

(2020)
52% 

(2018)


	With the commencement of the Working Better Together initiative in September 2019, and investment in our People and Culture directorate, we expect to see improved employee engagement in the 2021–22 survey.
	

	Increased employee satisfaction.
	Annual
	62%

(2017)
	80%
	63%

(2020)
58%

(2018)


	With the commencement of the Working Better Together initiative in September 2019, and investment in our People and Culture directorate, we expect to see improved employee engagement in the 2021–22 survey.
	

	Increased positive media coverage.
	Every three months
	55%

(Average of 12 months Oct 17 to Sep 18)
	Increase
	66.0%^
(Average 2019–20)
62.6%

(Average 2018–19)


	Ticketless parking and initiatives to improve Greater Geelong’s liveability and attraction contributed to positive sentiment in the first part of the financial year. From March–June 2020, sentiment was predominantly influenced by media coverage of COVID-19.  
	


^The methodology used to collect this data changed in 2019–20, so caution should be applied when comparing results with previous years.
	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status

	Proactively manage our assets, including land holdings.
	Identify opportunities to sell unused land.


	We sold some parcels of land in the Geelong Ring Road Employment Precinct land, as well as 257 Roslyn Road, Highton. 

The lease or sale of the former Geelong Post Office is underway with Council due to consider a decision in August 2020. 

Our Land and Building Asset Management Subcommittee continued working to proactively manage our assets, including land holdings, by working across the organisation. 

We also started developing a sales and acquisition strategy, designed to improve transparency of land-related sales and purchases.
	

	Consolidate the City of Greater Geelong offices.
	Commence design and development of the Civic Precinct.*
	We completed the Expression of Interest and Request for Tender processes, after which we appointed a developer. We also started community engagement to inform the design of public spaces within the Civic Precinct. 
The design process is well underway and work is due to commence in the second half of 2020.
	

	Communicate and engage more effectively with the community, in areas of need.
	Improve our inclusive engagement practices.
	We updated engagement tools, templates and policies to support more inclusive engagement practices. Actions completed include: 

· piloted new data software 

· built a new online engagement platform, which has increased online activity and provided an alternative to face-to-face options during COVID-19 restrictions
· updated our engagement policy and framework, which will be released for community feedback in 2020–21 

· developed and implemented a COVID-19 community engagement evaluation template.    
	


	Four-year council plan priorities
	2019–20 actions
	Progress comment
	Status

	
	Promote and support the Junior Youth Council.
	We delivered the following Youth Council activities:

· three Youth Council meetings

· Councillor Connect Mentoring Program

· Youth Councillor Coaching sessions 

· two Youth Council reports

· Geelong Youth Summit at GMHBA Stadium in October 2019

· Youth Leadership Program 2020

· Youth Rainbow Leadership Program 2020.

Youth Council members also provided advice, both internal and external, and made recommendations via the Junior Mayor's quarterly report.

The 2020 Youth Council was elected in February 2020.
	   (

	Continue to transform our workplace culture.
	Implement the Organisation Leadership and Capability Framework.
	Our organisation leadership and capability framework was put on hold while we developed an overarching culture vision and plan. The process will restart in July 2020, with plans to launch the framework in December 2020.  
Part of the culture plan is our Working Better Together program. In 2019–20, we achieved the following: 
· consulted with 800 employees and received 147 written submissions 

· reported the insights from this engagement back to the organisation and developed action plans 

· invited all employees to take part in an annual Employee Opinion Survey, which achieved a response rate of 70 per cent 

· conducted a series of Working Better Together sessions with our leadership team.

Due to the need to focus on our COVID-19 response, Working Better Together plans and a review of Employee Opinion survey was postponed.
	

	
	Establish and support an organisational change management function.
	While this function was originally established to support our transition to the Civic Precinct and digital modernisation, the scope has been expanded to cover all significant change initiatives, projects and programs across the business.   
	   (

	Use data and analytics to make better decisions.
	
	We completed a Data Management Strategy in March 2020. We started developing a business case to fund and resource a major data management program of work. This is due to be completed in July 2020. 
We also established an internal Data Governance Advisory Committee to establish policies and guidelines aimed at improving our data management practices.
	

	Make our processes more effective and efficient.
	Commence operation of an Enterprise Project Management Office.
	We recruited to a new role designed to lead and coordinate our Enterprise Project Management function. The position will support the organisation to improve processes and practices. 
	

	
	Commence first year delivery of 5-year service plans.
	We continued implementing prioritised actions identified in the first year of five-year service planning. 

We engaged with our senior leadership team in June 2020 to review the progress of actions within the plans.
	   (

	
	Establish an agreed program for detailed reviews of service delivery.
	We developed a five-year service planning framework, with Year 2 of service planning scheduled to commence July 2020. In addition, we started scoping the service review program.
	   (

	Increase state and federal funding for the region.
	
	We initiated new positions dedicated to grants, government relations and advocacy in 2020. These roles will develop new processes and practices that will improve our capacity to attract, track and administer grants from a range of external funding bodies, including state and federal government. 
	

	Develop, promote and improve the City’s brand.
	Deliver actions as outlined in the Corporate Communications and Marketing Strategy.
	We formed a Corporate Affairs team to improve collaboration and alignment around communications, marketing, government relations and engagement.

We used a range of communication channels to deliver ongoing crisis communications during the COVID-19 pandemic. Communication was focused on restrictions, safety measures and support available for businesses and our community. 
We started a brand benchmarking exercise to gain a better understanding of brand recognition, and community perceptions.
	

	Lead major local organisations in collaborative projects.
	
	Collaborative projects we were involved with in 2019–20 include:

· City Deal initiatives, 

· the Gateway Cities Alliance with Newcastle and Wollongong councils, and Committee for Geelong

· briefings to G21 and Committee for Geelong

· Brand Geelong workshops designed to identify the unique qualities that could be used to sell the region to the world

· the Barwon Regional Partnership Roundtable.

We also developed agreed regional priorities for COVID-19 recovery with G21, Committee for Geelong, Geelong Chamber of Commerce, Geelong Manufacturing Council and Tourism Greater Geelong and the Bellarine.
	

	Use better communication to strengthen our strategic priorities.
	Create a new advocacy function.
	As part of our revised Corporate Affairs function, we established a dedicated team to lead, coordinate and support the Council in government liaison and advocacy activities. 
	   (

	
	Continue Community Focus Meetings and live streaming of Council Meetings.
	We provided live streaming and archived footage of Ordinary Meetings of Council, which increased engagement with our community. 
Community Focus meetings continued throughout the municipality until March 2020, when COVID-19 restrictions prevented the public from attending. These meetings were then moved to City Hall so they could also be live streamed.   
In total, Ordinary and Community Focus Meetings had 4,836 live views, plus 3,941 achieved views in 2018–19. 
	   (

	
	Commence planning for 2020 council elections.
	We commenced a community engagement program to help us meet a state government target of 50 per cent women councillors and mayors by 2025. This program included:

· support for the Women in Local Democracy (WILD)

· workshops by the Victorian Local Governance Association’s Local Women Leading Change campaign 

· a ‘How to Get Elected’ session by Ruth McGowan 

· information booths at SKAART Youth Festival, Pako Festa 2020 and the VALiD Having a Say Conference.

We were forced to cancel 20 planned events due to COVID-19 restrictions and suspended project activities until it was confirmed elections would proceed in October 2020.  
We revised the engagement plan to include improved information on the Geelong Australia website, roadside signage, video messages, increased social media presence and online training.
	   (


*Major Initiative
Local Government Performance Reporting Indicators 

To help measure performance across all Victorian councils in a transparent and accountable way, we report to Local Government Victoria on the following mandatory indicators:
	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Governance
	
	
	
	
	

	Transparency

Council decisions made at meetings closed to the public
[Number of council resolutions made at ordinary or special meetings of council, or at meetings of a special committee consisting only of councillors, closed to the public / Number of council resolutions made at ordinary or special meetings of council, or at meetings of a special committee consisting only of councillors] x100
	4.83%
	12.25%
	8.39%
	9.03%
	We make every effort to ensure council decisions are made at meetings open to the public. We introduced transparent reporting of tender outcomes in 2018-19, and this limited most matters resolved at meetings closed to the public to those involving commercially-sensitive contracts.

	Consultation and engagement
Satisfaction with community consultation and engagement
[Community satisfaction rating out of 100 with how council has performed on community consultation and engagement]
	47
	50
	55
	53
	Community satisfaction has decreased slightly, but there has been an overall upward trend over the past four years. 
A new Have Your Say platform and other resources introduced this year have made engagements more accessible to the community, despite COVID-19 restrictions impacting our ability to engage face-to-face.  

	Attendance
Councillor attendance at council meetings
[The sum of the number of councillors who attended each ordinary and special council meeting / (Number of ordinary and special council meetings) × (Number of councillors elected at the last council general election)] x100
	95.24%
	94.54%
	96.36%
	93.45%
	Our results are consistent with previous years, with only 11 apologies for the financial year 2019–20.

	Service cost
Cost of governance
[Direct cost of the governance service / Number of councillors elected at the last council general election]
	$186,708.33
	$101,558.08
	$48,135.89
	$43,543.45
	Costs have reduced since the return of an elected Council in October 2017, following 18 months of Administrators.


	Satisfaction
Satisfaction with council decisions
[Community satisfaction rating out of 100 with how council has performed in making decisions in the interest of the community]
	48
	53
	55


	56
	Our results reflect the sound decision-making by our current Council. 
In addition, live streaming of council meetings and community focus meetings continue to have a positive impact on our community.


GOVERNANCE

COUNCIL INFORMATION

TABLE 5: Council meetings in 2019–20
	Meeting type
	Number held
	Held at 

	Ordinary council meetings*
	12 (one per month)
	City Hall (30 Gheringhap Street, Geelong)

	Special council meetings*
	3 (as required)
	City Hall (30 Gheringhap Street, Geelong)

	Community focus council meetings*
	10 (all months, except December and January)
	Normally held in a different location each month, these meetings were moved to City Hall from March due to COVID-19 restrictions.


* All meetings were live streamed following the introduction of COVID-19 restrictions in March.  
TABLE 6: Councillor attendance for 2019–20
	Councillor
	Ordinary
	Special
	Community Focus Council
	Total

	S Asher (Mayor)
	10
	3
	9
	22

	K Grzybek (Deputy Mayor)
	12
	3
	10
	25

	A Aitken (Councillor)
	12
	3
	10
	25

	B Harwood (Councillor)
	12
	3
	10
	25

	E Kontelj (Councillor)
	11
	2
	9
	22

	S Mansfield (Councillor)
	10
	2
	9
	21

	J Mason (Councillor)
	11
	3
	10
	24

	P Murnane (Councillor)
	12
	2
	9
	23

	P Murrihy (Councillor)
	11
	3
	10
	24

	R Nelson (Councillor)
	11
	3
	9
	23

	T Sullivan (Councillor)
	11
	3
	9
	23


TABLE 7:  Special committees in 2019–20
	Special committee
	
	Purpose

	Central Geelong Marketing Committee
	
	To market and promote Central Geelong in a coordinated and integrated way, enhancing economic and social viability and general amenity.

	Geelong Major Events  
	
	To coordinate how we attract, assist and fund events.

	Bellarine Multi-Arts Facility (Potato Shed)
	
	To support the long-term management and promotion of the Potato Shed.

	Planning Committee
	
	To consider and determine planning permit applications that have been called in by a councillor.

	Chief Executive Officer (CEO) Employment Matters Special Committee
	
	To oversee the recruitment of the CEO, and other CEO employment matters.


The Development Hearing Panel Special Committee was abolished on 19 August 2019.

Code of conduct

All councils are required to develop and approve a councillor code of conduct within four months of a general election. On 27 February 2018, our Council adopted a revised Councillor Code of Conduct that is designed to:

· help councillors maintain the highest standards of conduct and behaviour

· provide a means to deal with problems councillors might encounter

· attract the highest level of confidence from stakeholders and

· help the mayor and councillors to discharge their public office responsibilities appropriately.

The code also:

· clarifies roles

· explains decision-making arrangements 

· provides guidance on councillor behaviour, interests, gifts and hospitality, lawful conduct and other obligations
· provides a framework and processes for managing councillor conduct.
Councillor allowances

All councillors are entitled to an allowance while performing their duty. Allowances for the mayor and deputy mayor are governed by the City of Greater Geelong Act (Vic) 1993. The Minister for Local Government approved an annual adjustment of two per cent to take effect from 1 December 2019. 
TABLE 8: Current annual allowances
	Councillor
	Allowance

$

	S Asher (Mayor)
	100,434

	K Grzybek (Deputy Mayor)
	31,444

	A Aitken (Councillor)
	31,444

	B Harwood (Councillor)
	31,444

	E Kontelj (Councillor)
	31,444

	S Mansfield (Councillor)
	31,444

	J Mason (Councillor)
	31,444

	P Murnane (Councillor)
	31,444

	P Murrihy (Councillor)
	31,444

	R Nelson (Councillor)
	31,444

	T Sullivan (Councillor)
	31,444


Councillor expenses

Councillors must be reimbursed for expenses incurred while performing their duties. Council has adopted a policy to determine what will be reimbursed, as well as other resources, facilities and support needed to help the mayor and councillors discharge their duties. 

TABLE 9: Details of reimbursements and expenses paid in 2019–20 

	Name
	Travel
	Car
	Childcare
	Information & communication technology
	Conference & Training
	Total

	
	$
	$
	$
	$
	$
	$

	S Asher
	1,110.65
	11,608
	-
	342.68
	1,000 
	14,061.33

	K Grzybek
	916
	-
	-
	342.68
	- 
	1,258.68

	A Aitken
	-
	-
	-
	342.68
	317 
	659.68

	B Harwood
	1,052
	4,150.83
	-
	364.68
	82 
	5,649.51

	E Kontelj
	-
	-
	-
	833.91
	 95 
	928.91

	S Mansfield
	-
	-
	-
	342.68
	 - 
	342.68

	J Mason
	208
	5,731
	-
	342.68
	 559 
	6,840.68

	P Murnane
	-
	-
	-
	342.68
	 - 
	342.68

	P Murrihy
	132
	-
	-
	342.68
	 231 
	705.68

	R Nelson
	594
	-
	-
	342.68
	 41
	977.68

	T Sullivan
	120
	2,133
	-
	342.68
	 36
	2,631.68


AUDIT AND RISK COMMITTEE
Our Audit and Risk Committee provides structured, systematic oversight of Council’s governance, assurance, risk management and internal control practices. This oversight mechanism also helps maintain the integrity of these practices. The Committee:

· is comprised of five voting members; three independent members, the Mayor and one Councillor 

· holds at least four regular meetings per annum 

· provides its minutes to Council for information purposes.
TABLE 10: Audit and Risk Committee 

	AUDIT AND RISK COMMITTEE MEMBER ATTENDANCE
	NUMBER OF MEETINGS ATTENDED

	Mr Geoff Harry (independent member – chair)   
	5

	Ms Lisa Tripodi (independent member)     
	5

	Mr John Watson (independent member)             
	5

	Cr Bruce Harwood 
	1

	Cr Stephanie Asher 
	1

	Cr Kylie Grzybek 
	2

	Cr Jim Mason 
	3


Audit

Audit is an independent function that assesses the effectiveness of risk management, controls and governance processes. Internal audit is focused on processes and controls. External audit provides an independent examination of the financial statements prepared by the organisation. 
The Victorian Auditor-General’s Office provides our external audit service.
Risk Management

Risk management is an important function that helps us meet the expectations of our many stakeholders and provide quality services to our community. It allows decision-makers to be better informed, more decisive and more confident in achieving our specified outcomes and objectives.
The objectives of our risk management program are to: 

· provide a structured and consistent approach to identifying, rating, mitigating, managing and monitoring risks

· assist decision-makers to weigh risks against potential opportunities

· create an environment where employees understand and assume responsibility for managing risks and controls 

· provide relevant and timely information using a clear reporting structure.
GOVERNANCE AND MANAGEMENT CHECKLIST

The following are the results in the prescribed form of council’s assessment against the prescribed governance and management checklist, as at 30 June 2020.
	GOVERNANCE AND MANAGEMENT ITEMS
	
	ASSESSMENT

	GC1
	Community engagement policy (policy outlining Council's commitment to engaging with the community on matters of public interest)
	
	Policy in operation

Date of operation of current policy: 25 July 2017

	GC2
	Community engagement guidelines (guidelines to assist staff to determine when and how to engage with the community)
	
	Guidelines in operation

Date of operation of current guidelines: 25 July 2017

	GC3
	Strategic Resource Plan (plan under section 126 of the Act, outlining the financial and non-financial resources required for at least the next four financial years)
	
	Adopted in accordance with section 126 of the Local Government Act 1989

Date of adoption: 30 June 2020

	GC4
	Annual budget (plan under section 130 of the Act setting out the services to be provided and initiatives to be undertaken over the next 12 months, and the funding and other resources required)
	
	Adopted in accordance with section 130 Local Government Act 1989

Date of adoption: 30 June 2020

	GC5
	Asset management plans (plans that set out the asset maintenance and renewal needs for key infrastructure asset classes for at least the next 10 years)
	
	Adopted

Date of adoption:

· Asset Management Policy (26 May 2020)
· Non-current Asset Accounting Policy adopted          (26 May 2020)
· Fleet Asset Management Plan (1 January 2006)
· IT Asset Management Plan (1 September 2012)
· Building Asset Management Plan (1 January 2012)
· Road Asset Management Plan (1 September 2013)
· Footpath Asset Management Plan (1 March 2012)
· Bridges and Major Culverts Asset Management Plan            (1 August 2013)
· Drainage Asset Management Plan (14 August 2007)
Section 92 of the Local Government Act 2020 requires us to adopt an asset plan by 30 June 2022.

Our Asset Management Transformation Program is preparing this for adoption by Council in 2020–21, with the following asset management plans: waterfront; drainage; water sensitive urban design; bridges; buildings; footpaths and roads.

	GC6
	Rating strategy (strategy setting out the rating structure of Council to levy rates and charges)
	
	Strategy in operation

Date of operation of current strategy: 30 June 2020

	GC7
	Risk policy (policy outlining Council's commitment and approach to minimising the risks to operations)
	
	Policy in operation
Date of operation of current strategy: 20 November 2019

	GC8
	Fraud policy (policy outlining Council's commitment and approach to minimising the risk of fraud)
	
	Policy in operation
Date of operation of current policy: 26 April 2018

	GC9
	Municipal emergency management plan (plan under section 20 of the Emergency Management Act 1986 for emergency prevention, response and recovery)
	
	Prepared and maintained in accordance with section 20 of the Emergency Management Act 1986
Date of preparation: 31 October 2018

	GC10
	Procurement policy (policy under section 186A of the Local Government Act 1989, outlining the matters, practices and procedures that will apply to all purchases of goods, services and works)
	
	Prepared and approved in accordance with section 186A of the Local Government Act 1989

Date of approval: 30 June 2020

	GC11
	Business continuity plan (plan setting out the actions that will be taken to ensure that key services continue to operate in the event of a disaster)
	
	Plan in operation
Date of operation of current plan: 16 May 2011
Updated in the 2019–20 financial year to include a revised business impact assessment. This identified critical activities and formalised resource dependencies. The business continuity framework and policy have both been approved by our Executive Leadership Team.

	GC12
	Disaster recovery plan (plan setting out the actions that will be undertaken to recover and restore business capability in the event of a disaster)
	
	Plan in operation

We have an IT disaster recovery plan

Date of operation of current plan: 25 June 2014



	GC13
	Risk management framework (framework outlining Council's approach to managing risks to the Council's operations)
	
	Framework in operation

Date of operation of current framework: 11 November 2019

	GC14
	Audit Committee (advisory committee of Council, under section 139 of the Act, whose role is to oversee the integrity of a Council's financial reporting, processes to manage risks to the Council's operations and compliance with applicable legal, ethical, and regulatory requirements)
	
	Established in accordance with section 139 of the Local Government Act 1989

Date of establishment: 28 November 2017
Section 54 of the Local Government Act 2020 requires us to adopt an Audit and Risk Committee Charter by 1 September 2020.

	GC15
	Internal audit (independent accounting professionals engaged by the Council to provide analyses and recommendations aimed at improving Council's governance, risk and management controls)
	
	Independent auditor engaged

Date of engagement of current provider: 7 December 2016


	GC16
	Performance reporting framework (a set of indicators measuring financial and non-financial performance, including the performance indicators referred to in section 131 of the Act)
	
	Framework in operation

Date of operation of current framework: 20 May 2020
The updated corporate performance reporting framework, which currently satisfies the requirements of section 131 of the Local Government Act 1989, was approved by our Executive Leadership Team.

	GC17
	Council Plan reporting (report reviewing the performance of the Council against the Council Plan, including strategic indicator results for the first six months of the financial year)
	
	Report in place

Date of current report: 11 February 2020


	GC18
	Financial reporting (quarterly statements to Council, under section 138 of the Act, comparing budgeted revenue and expenditure with actual revenue and expenditure)
	
	Statements presented to council in accordance with section 138(1) of the Local Government Act 1989
Dates statements presented:

Quarterly statement 4 – 10 September 2019 

(final quarter for 2018–19)
Quarterly statement 1 – 12 November 2019

Quarterly statement 2 – 25 February 2020  

Quarterly statement 3 – 12 May 2020

	GC19
	Risk reporting (six-monthly reports of strategic risks to Council's operations, their likelihood and consequences of occurring and risk minimisation strategies)
	
	Reports prepared and presented to council:

Report 1 – 24 September 2019

Report 2 – 28 January 2020

Report 3 – 24 March 2020 

Report 4 – 30 June 2020

	GC20
	Performance reporting (six-monthly reports of indicators measuring the results against financial and non-financial performance, including performance indicators referred to in section 131 of the Act)
	
	Council Plan Quarterly Report December 2019 prepared and presented: 11 February 2020

Quarterly Financial Report December 2019 prepared and presented: 25 February 2020
We report annually against a performance reporting framework which satisfies section 131 of the Local Government Act 1989. We also produce quarterly financial reports.

	GC21
	Annual report (under sections 131, 132 and 133 of the Act, an annual report to the community containing a report of operations and audited financial performance statements)
	
	Considered at a meeting of our Council in accordance with section 134 of the Local Government Act 1989

Date Annual Report presented: 29 October 2019

	GC22
	Councillor Code of Conduct (code under section 76C of the Act, setting out the conduct principles and the dispute resolution processes to be followed by Councillors)
	
	Reviewed in accordance with section 76C of the Local Government Act 1989

Date reviewed: 27 February 2018

	GC23
	Delegations (a document setting out the powers, duties and functions of Council and the Chief Executive Officer that have been delegated to members of staff)
	
	Reviewed in accordance with section 98(6) of the Local Government Act 1989

Date of review: 23 October 2018
Section 11 of the Local Government Act 2020 requires us to review and adopt Council to Chief Executive Officer delegations by 1 September 2020. 

	GC24
	Meeting procedures (a local law governing the conduct of meetings of Council and special committees)
	
	Meeting procedures local law made in accordance with section 91(1) of the Local Government Act 1989
Date local law made: 20 September 2017
Section 60 of the Local Government Act 2020 requires us to adopt and apply governance rules by 1 September 2020 that describe the way we will conduct Council meetings and make decisions.


We certify that this information presents fairly the status of council’s governance and management arrangements.
	[image: image49.png]Cr Stephanie Asher Martin Cutter
Mayor Chief Executive Officer
Dated: 1 September 2020 Dated: 19 August 2020







STATUTORY INFORMATION

The following information is provided in accordance with legislative and other requirements applying to council.
Documents available for public inspection

In accordance with regulation 12 of the Local Government (General) Regulations 2015, we are required to provide copies of the following documents for public inspection, for the purposes of section 222 of the Local Government Act (Vic) 1989, at 30 Gheringhap Street, Geelong:

· A document containing details of overseas or interstate travel (other than interstate travel by land for less than three days) undertaken in an official capacity by any councillor, or member of staff, in the previous 12 months.

· Minutes of ordinary and special meetings held in the previous 12 months, which are kept under section 93 of the Act, other than those agendas and minutes relating to a part of a meeting closed to members of the public under section 89 of the Act that are confidential information within the meaning of section 77(2) of the Act.

· The minutes of meetings of special committees established under section 86 of the Act and held in the previous 12 months, other than those minutes relating to a part of a meeting which was closed to members of the public under section 89 of the Act that are confidential information within the meaning of section 77(2) of the Act.

· A register of delegations kept under sections 87(1) and 98(4) of the Act, including the date on which the last review took place under sections 86(6) and 98(6), respectively, of the Act.

· A document containing details of all leases involving land which were entered into by the Council as lessor, including the lessee and the terms and the value of the lease.

· A register, maintained under section 224(1A) of the Act, of authorised officers appointed under that section.

· A list of donations and grants made by the council in the previous 12 months, including the names of persons who, or bodies which, have received a donation or grant, and the amount of each donation or grant.

Contracts

During the year, we did not enter into any service contracts valued at $150,000 or more, or works contracts for $200,000 or more, for works or more of a kind specified in section 186(5)(a) and (c) of the Act. We also did not enter into any other contracts valued at $150,000 or more for goods or services, or $200,000 or more for works, without engaging in a competitive process.

Food Act Ministerial directions

In accordance with section 7E of the Food Act (Vic) 1984, we are required to publish a summary of any Ministerial Directions received during the financial year in our annual report, however we didn’t receive any in 2019–20.

Information privacy

We are committed to protecting people's right to privacy and the responsible and fair handling of personal information, consistent with the Privacy and Data Protection Act (Vic) 2014 and Health Records Act (Vic) 2001.
Our policies set out our requirements for the managing and handling of personal information. The policies are public documents which are available on request, or via our website. 

Freedom of Information

In accordance with section 7(4AA)(a) and 7(4AA)(b) of the Freedom of Information Act (Vic) 1982, we are required to publish certain statements in the annual report or separately, such as on our website, concerning our functions and information available. We have chosen to publish the statements separately, however the following summarises the application and operation of the Freedom of Information Act (Vic) 1982.

Access to documents may be obtained through written request to the Freedom of Information Officer, as detailed in section 17 of the Freedom of Information Act (Vic) 1982 and in summary as follows:

· it should be in writing

· it should identify the document being requested as clearly as possible
· it should be accompanied by the appropriate application fee (the fee may be waived in certain circumstances).

Requests for documents in our possession should be addressed to the Freedom of Information Officer. Requests can also be lodged online, or by email.

Access charges may also apply once documents have been processed and a decision on access has been made –for example, photocopying, and search and retrieval charges.

Further information regarding freedom of information can be found at www.foi.vic.gov.au and on our website.

Protected disclosure procedures
In accordance with section 69 of the Public Interest Disclosures Act 2012 (the Act), our website at www.geelongaustralia.com.au provides information about making a public interest disclosure.  

The Act aims to ensure openness and accountability in government by encouraging people to disclose improper conduct within the public sector and provide protection for people who make disclosures.

There were three disclosures notified to the Independent Broad-based Anti-Corruption Commission under section 21(2) during 2019–20.

Road Management Act Ministerial direction

In accordance with section 22 of the Road Management Act (Vic) 2004, a council must publish a copy or summary of any Ministerial direction in its annual report.
There was one Ministerial direction given under section 22 of the Road Management Act in the period 1 July 2019 to 30 June 2020. On 2 April 2020, the Minister for Roads made the following direction: 

“I, Jaala Pulford, Minister for Roads, considering it to be in the public interest to do so, direct the City of Greater Geelong, as the responsible road authority for Malop Street, Geelong, to perform its functions and exercise its powers under the Road Management Act 2004 (Road Management Act) in a manner not inconsistent with the Green Spine Project.

Further, and in particular, the City of Greater Geelong is directed not to perform a function or exercise a power under the Road Management Act to:

· undertake any works to remove road infrastructure and road-related infrastructure including the botanical walk on Malop Street constructed under or consistent with the Green Spine project;

· remove the recently constructed separated bike lanes on Malop Street between Moorabool Street and Yarra Street;

· install vehicle turning lanes at the intersections of Malop Street and Yarra Street and Malop Street and Moorabool Street; and

· increase or alter existing street 2P car parking locations on Malop Street between Moorabool Street and Yarra Street.”

This direction remains in place until the completion of works associated with the Green Spine Project.
Charter of Human Rights and Responsibilities 

In June 2006, the Victorian Parliament passed the Charter of Human Rights and Responsibilities Act (Vic) 2006 (the Charter). The Charter came into effect on 1 January 2008.

The Charter enshrines civil and political rights, and some cultural rights, into Victorian law, while promoting and protecting principles of freedom, respect, equality and dignity.

We consider the 20 human rights established by the Charter when delivering our services, developing our policies or implementing our plans.

Local Laws

The following local laws remain current.

Neighbourhood Amenity Local Law 2014

This local law regulates activities of people and provides standards and conditions for specified activities to protect people in, or the environment of, the municipal district. The local law aims to achieve the following objectives that align with our overall objectives and strategies:

· to secure community safety

· to protect public assets

· to enhance neighbourhood amenity.

Council Meeting Procedures Local Law 2017

This local law relates to meetings of the Greater Geelong City Council and special committees. The objectives include:

· to regulate and control use of the Common Seal of Council

· to regulate proceedings for the election of the mayor and deputy mayor

· to facilitate the orderly conduct of, and regulate proceedings at, meetings of council and special committees 

· to facilitate the good government of the Council and ensure its decisions are made in the best interests of the community

· to promote and encourage community participation in governance.

Local Government Act 2020

After five years of deliberation and consultation, the Local Government Act 2020 (new Act) gained Royal Assent on 24 March 2020.

The new Act has been developed around five key reform themes:

1. Improved service delivery – including improved procurement and investment policies; workforce planning; gender equity, diversity and inclusiveness; and revised CEO remuneration policy.
2. Strong local democracy – including single member wards (to be implemented for the 2024 election for the City of Greater Geelong); complaints policy; and leadership role for Mayor.
3. Improve conduct – including new mandatory standards of conduct; conflicts of interest simplified; and arbiters to deal with matters locally and quickly.
4. Community confidence – including candidates and councillors to complete mandatory training; and council electoral rolls aligned to State electoral roll.
5. A new relationship – including removal of unnecessary administrative burden and Ministerial involvement; and councils exercise powers and perform their role in accordance with overarching governance principles.

Importantly, the new Act (Part 11, Division 1, Section 331) repealed the City of Greater Geelong Act 1993 as of 6 April 2020. Section 329(4) of the new Act states that the City of Greater Geelong Act 1993 continues to apply in respect of any Councillor, Mayor or Deputy Mayor in office, until the general elections in 2020.

Despite the repeal of the City of Greater Geelong Act 1993, the Mayor of the City of Greater Geelong will continue to be elected by councillors for a two-year term, under Section 26(2) of the new Act.

DOMESTIC ANIMAL MANAGEMENT PLAN UPDATE 

We have a legal obligation under the Domestic Animals Act (Vic) 1994 to produce a four-year domestic animal management plan and evaluate its progress in our annual report. 
We have one of the largest dog and cat populations of any Victorian municipality, with 35,370 registered dogs and 11,047 registered cats. 

Council adopted the Domestic Animal Management Plan 2018–21 on 12 March 2018, following an extensive engagement period. 

Activities we’ve undertaken in the last 12 months in support of the plan include:

· completed the July 2019 cat desexing program 

· audited dog signage across the municipality, with new signs rolled out to key locations 
· installed temporary ‘pick up poo’ signs at sporting grounds 

· rebranded animal management vehicles to improve our visibility within the community 

· communicated via the Park Your Pet App 
· engaged with our community about proposed changes to dog control orders on Barwon-Coast-managed land 

· distributed City-branded dog poo bag dispensers at City-attended pet events 
· created a video about effective dog control 
· provided pet selection articles and links on our website 
· developed a dog attack registry to identify trends in the municipality.

ACCESS AND INCLUSION PLAN UPDATE

We have a legal obligation under the Disability Act (Vic) 2006 to produce a disability action plan and evaluate its progress in the annual report. 
Our Access and Inclusion Action Plan 2018–22 was endorsed by Council in November 2018. The action plan is based on four key areas and contains 37 goals with 49 measures. 
TABLE 11: Key projects undertaken in 2019–20 
	Key area
	Number of projects undertaken
	
	Examples of 2019–20 actions

	Promoting inclusion and participation in the community of persons with a disability.
	6
	
	· We engaged people with a lived experience of disability at the VALID Having a Say Conference to find out about their perceptions of Geelong.

· We consulted on the commission of an ‘Inclusive Art Sculpture’ for our public art collection.

· We implemented a new hearing augmentation system at City Hall.

· We increased access to swimming lessons for children with disabilities and children from low income families in the 3219 area.

· We facilitated the Access and Inclusion Advisory Committee, whose members have a lived experience of disability and advise us on our policies and activities. 

· We improved access along the Eastern Beach Waterfront by installing rubber beach matting and floating Mobi-Chairs.

· We provided a Marveloo (portable, fully-accessible changing places facility) for use at the Kardinia Park Festival of Sport and the Queenscliff Music Festival.

	Reducing barriers in accessing goods, services and facilities
	12
	
	· We supported 220 clients through 3,215.67 hours of home modification. 

· We provided input into the design and delivery of over $35 million new subdivision assets, including new roads, kerb and footpath upgrades, shared paths and bus routes. 

· We identified ways to improve access to The Geelong After Dark event, including an accessibility map overlay showing all access areas and 'quiet spaces'.

· We engaged to help us design the new Rippleside Park Inclusive Play Space, an innovative and world-class space for children of all abilities.

· We discussed opportunities to improve accessibility in Central Geelong and on the Waterfront with the Department of Environment Land Water and Planning. 

· We implemented a Changing Places facility in Geelong Westfield Shopping Centre, so there are now seven Changing Places facilities in the municipality, with more planned. 

	Reducing barriers to obtaining and maintaining employment. 
	3
	
	· We refined our employee learning program about disability access and community inclusion.

· We made council plans, strategies and guidelines available to all employees, including employees with no or limited online access.

· We provided information to foster interest and participation in the 2020 council elections and pathways to employment, as part of the 2020 VALID Having a Say Conference.

	Achieving tangible changes in attitudes and practices that discriminate against persons with a disability.
	3
	
	· We supported events for International Day of People with Disability, including the 'Through My Eyes’ art exhibition at the Gordon Gallery, which exhibited 111 pieces of work from 100 artists and resulted in 16 per cent of works being sold.


DEVELOPMENT CONTRIBUTIONS PLAN (DCP) PROGRESS REPORT

In accordance with sections 46GM and 46QM of the Planning and Environment Act 1987, we must prepare and give a report to the Minister for Planning on infrastructure (not applicable to us) and development contributions, including levies and works-in-kind. This information must be published in our annual report. 

Development contributions are payments, or works-in-kind, made by the proponent of a new development for the provision of infrastructure.

For 2019–20, the following information about infrastructure and development contributions has been disclosed.

Development contributions

TABLE 12: Total DCP levies received in 2019–20 

	DCP name 
	Year Approved
	Levies received in 2019–20 financial year ($)

	DCP01 Armstrong Creek North East Industrial
	2010
	$0.00

	DCP02 Jetty Road Urban Growth Area Stage 1
	2012
	1,600,938.00

	DCP03 Armstrong Creek East Precinct
	2012
	3,439,559.00

	DCP04 Armstrong Creek West Precinct
	2013
	1,972,157.55

	DCP05 Armstrong Creek Horseshoe Bend Precinct
	2014
	434,871.00

	DCP06 Armstrong Creek Town Centre Precinct
	2014
	0.00

	DCP07 Lara West Urban Growth Area
	2014
	2,979,699.00

	Total
	
	10,427,224.55

	
	
	


TABLE 13: DCP land, works, services or facilities accepted in-kind in 2019–20 

	DCP name 

(year approved)
	Project ID
	Project description
	Item purpose
	  Project value 

($)               

	DCP03 Armstrong Creek East Precinct – 2012
	DI_TR_1
	Off-road shared trail network
	Trails
	173,587

	DCP05 Armstrong Creek Horseshoe Bend Precinct – 2014
	DI_DR_06
	Drainage works – Horseshoe Bend Road Retarding Basin – construction 
	Drainage
	2,439,929

	DCP05 Armstrong Creek Horseshoe Bend Precinct – 2014
	DI_TR_3
	Greenway improvement works 
	Trails
	72,145

	DCP05 Armstrong Creek Horseshoe Bend Precinct – 2014
	DI_RD_04a
	Intersection – Surf Coast Highway and Boundary Road (Stage 1) – contribution to out-of-sequence development
	Roads
	179,464

	DCP05 Armstrong Creek Horseshoe Bend Precinct – 2014
	DI_RD_04b
	Intersection – Surf Coast Highway and New Boundary Road
	Roads
	2,194,493

	DCP05 Armstrong Creek Horseshoe Bend Precinct – 2014
	DI_TR_1
	Shared path network – off-road
	Trails
	425,287

	DCP04 Armstrong Creek West Precinct – 2013
	DI_DR_02
	Armstrong Creek waterway improvement works – north-south connector road to east-west connector road (Main St ext)
	Drainage
	257,238

	DCP04 Armstrong Creek West Precinct – 2013
	DI_RO_10
	Creek road crossing – structure – north-south Connector
	Roads
	514,232

	DCP04 Armstrong Creek West Precinct – 2013
	DI_LA_09
	Drainage works – sedimentation Basin (property 15) – land
	Land
	271,000

	DCP04 Armstrong Creek West Precinct – 2013
	DI_DR_07
	Drainage works – wetland retarding basins (WLRB1) – construction
	Drainage
	446,797

	DCP04 Armstrong Creek West Precinct – 2013
	DI_DR_08
	Drainage works – wetland retarding basins (WLRB2) ​– construction
	Drainage
	1,463,144

	DCP04 Armstrong Creek West Precinct – 2013
	DI_DR_12
	Drainage works – wetland retarding basins (WLRB6) – construction
	Drainage
	2,028,783

	DCP04 Armstrong Creek West Precinct – 2013
	DI_DR_13
	Drainage works – wetland retarding basins (WLRB7) – construction
	Drainage
	1,990,296

	DCP04 Armstrong Creek West Precinct – 2013
	DI_DR_14
	Drainage works – wetland retarding basins (WLRB8) – construction
	Drainage
	1,868,290

	DCP04 Armstrong Creek West Precinct – 2013
	DI_RO_09
	Intersection – Mac (retail/school precinct)
	Roads
	450,523

	DCP04 Armstrong Creek West Precinct – 2013
	DI_OS_6
	Playground equipment – local parks (5)
	Open Space
	128,846

	DCP04 Armstrong Creek West Precinct – 2013
	DI_TR_2
	Shared path network – off-road
	Trails
	566,593

	DCP02 Jetty Road Urban Growth Area Stage 1 – 2012
	OS003
	Sub-regional park – improvements
	Open Space
	20,802

	Total
	
	
	
	15,491,449

	
	
	
	
	


TABLE 14: Land, works, services or facilities delivered in 2019–20 from DCP levies collected

	Project description
	Project ID
	DCP name 

(year approved)
	DCP fund expended 

($)
	Works-in-kind accepted 

($)
	Council's contribution 

($)
	Other contributions 

($)
	Total project expenditure 

($)
	Percentage of item delivered

                      (%)

	Off-road shared trail network
	DI_TR_1
	DCP03 Armstrong Creek East Precinct - 2012
	
	173,587
	
	
	173,587
	3.00

	Drainage Works – Horseshoe Bend Road Retarding Basin – construction 
	DI_DR_06
	DCP05 Armstrong Creek Horseshoe Bend Precinct - 2014
	
	2,439,929
	
	
	2,439,929
	100.00

	Greenway improvement works 
	DI_TR_3
	DCP05 Armstrong Creek Horseshoe Bend Precinct - 2014
	
	72,145
	
	
	72,145
	16.08

	Intersection – Surf Coast Highway and Boundary Road (Stage 1) – contribution to out-of-sequence development
	DI_RD_04a
	DCP05 Armstrong Creek Horseshoe Bend Precinct - 2014
	
	179,464
	
	
	179,464
	25.00

	Intersection – Surf Coast Highway and New Boundary Road
	DI_RD_04b
	DCP05 Armstrong Creek Horseshoe Bend Precinct - 2014
	
	2,194,493
	
	
	2,194,493
	57.20

	Shared path network – off-road
	DI_TR_1
	DCP05 Armstrong Creek Horseshoe Bend Precinct - 2014
	
	425,287
	
	
	425,287
	8.19

	Armstrong Creek waterway improvement works – north-south connector road to east- west connector road (Main St ext)
	DI_DR_02
	DCP04 Armstrong Creek West Precinct - 2013
	
	257,238
	
	
	257,238
	15.45

	Creek road crossing – structure - north-south connector
	DI_RO_10
	DCP04 Armstrong Creek West Precinct - 2013
	
	514,232
	
	
	514,232
	98.72

	Drainage works – sedimentation Basin (property 15) – land
	DI_LA_09
	DCP04 Armstrong Creek West Precinct - 2013
	
	271,000
	
	
	271,000
	100.00

	Drainage works – wetland retarding basins (WLRB1) – construction
	DI_DR_07
	DCP04 Armstrong Creek West Precinct - 2013
	
	446,797
	
	
	446,797
	11.86

	Drainage works – wetland retarding basins (WLRB2) – construction
	DI_DR_08
	DCP04 Armstrong Creek West Precinct – 2013
	
	1,463,144
	
	
	1,463,144
	91.65

	Drainage works – wetland retarding basins (WLRB6) – construction
	DI_DR_12
	DCP04 Armstrong Creek West Precinct – 2013
	
	2,028,783
	
	
	2,028,783
	90.64

	Drainage works – wetland retarding basins (WLRB7) – construction
	DI_DR_13
	DCP04 Armstrong Creek West Precinct – 2013
	
	1,990,296
	
	
	1,990,296
	100.00

	Drainage works – wetland retarding basins (WLRB8) – construction
	DI_DR_14
	DCP04 Armstrong Creek West Precinct – 2013
	
	1,868,290
	
	
	1,868,290
	78.98

	Intersection – Mac (retail/school precinct)
	DI_RO_09
	DCP04 Armstrong Creek West Precinct – 2013
	
	450,523
	
	
	450,523
	100.00

	Playground equipment – local parks (5)
	DI_OS_6
	DCP04 Armstrong Creek West Precinct – 2013
	
	128,846
	
	
	128,846
	20.00

	Shared path network – off-road
	DI_TR_2
	DCP04 Armstrong Creek West Precinct – 2013
	
	566,593
	
	
	566,593
	24.81

	Sub-regional park – improvements
	OS003
	DCP02 Jetty Road Urban Growth Area Stage 1 – 2012
	
	20,802
	
	
	20,802
	7.30

	NAC community complex – construction
	DI_C_1
	DCP03 Armstrong Creek East Precinct  
	21,404
	
	
	
	21,404
	1.84

	Sparrovale Wetlands – construction
	DI_DR_12
	DCP05 Armstrong Creek Horseshoe Bend Precinct  
	1,652,480
	
	
	
	1,652,480
	93.44

	Sparrovale Wetlands – land (1–87 Grove Road, Armstrong Creek)
	DI_LA_22
	DCP05 Armstrong Creek Horseshoe Bend Precinct 
	3,807
	
	
	
	3,807
	0.18

	Sparrovale Wetlands - land (109– 215 Sparrovale Road, Charlemont)
	DI_LA_23
	DCP05 Armstrong Creek Horseshoe Bend Precinct 
	4,621
	
	
	
	4,621
	0.06

	Sparrovale Wetlands – management plan 
	DI_DR_13
	DCP05 Armstrong Creek Horseshoe Bend Precinct  
	1,442,671
	
	
	
	1,442,671
	50.49

	Community Complex – NAC – construction
	DI_C_1
	DCP04 Armstrong Creek West Precinct  
	35,731
	
	
	
	35,731
	0.34

	Children's and community hub – construction
	C002
	DCP02 Jetty Road Urban Growth Area Stage 1  
	3,650
	
	
	
	3,650
	5.00

	Griggs Creek – rehabilitation and revegetation
	OS001
	DCP02 Jetty Road Urban Growth Area Stage 1 
	67,953
	
	
	
	67,953
	100.00

	Intersection – north-south collector road (Part A) and Geelong Portarlington Road
	R003
	DCP02 Jetty Road Urban Growth Area Stage 1  
	1,172,651
	
	
	
	1,172,651
	90.00

	North-south collector road (Part A) – construction (Stage 1)
	R001
	DCP02 Jetty Road Urban Growth Area Stage 1  
	1,995,942
	
	
	
	1,995,942
	75.00

	Pedestrian signals at Bellarine Rail Trail
	P003
	DCP02 Jetty Road Urban Growth Area Stage 1  
	238,110
	
	
	
	238,110
	50.00

	Regional community and learning hub
	C003
	DCP02 Jetty Road Urban Growth Area Stage 1  
	77,947
	
	
	
	77,947
	5.00

	Intersection - O'Hallorans Rd /Patullos Rd / Elcho Rd - 165 Patullos Road - land acquisition
	DI_LA_3
	DCP07 Lara West Urban Growth Area  
	44,743
	
	
	
	44,743
	100.00

	Intersection – O'Hallorans Road / Patullos Road /Elcho Road – 180 Patullos Road – land acquisition
	DI_LA_4
	DCP07 Lara West Urban Growth Area  
	5,402
	
	
	
	5,402
	25.25

	Intersection – O'Hallorans Road / Patullos Road / Elcho Road – 5 Elcho Road – land acquisition
	DI_LA_5
	DCP07 Lara West Urban Growth Area  
	535
	
	
	
	535
	100.00

	Total
	
	
	6,767,647
	15,491,450
	0
	0
	22,259,097
	


PERFORMANCE STATEMENT                        
Description of municipality 

For the year ended 30 June 2020

The City of Greater Geelong municipality is located 75 kilometres from the Melbourne CBD. The municipality covers 1,252 square kilometres, comprising country, coastal and suburban areas. Greater Geelong is bounded by Moorabool Shire, Wyndham City, Borough of Queenscliffe, Surf Coast Shire and Golden Plains Shire.

The municipality has a population of almost 259,000, which is expected to increase to more than 393,000 by 2041 – growth of nearly 52 per cent. Geelong has a diverse economy with over 18,800 businesses and a labour force of approximately 128,000 people. While Greater Geelong has recorded strong Gross Regional Product and jobs growth in recent years, the coronavirus (COVID-19) pandemic, and associated restrictions, have interrupted this trend. Forecasts show that all local industries have experienced job losses and reduced revenue, except healthcare and social assistance.  
The industries that contribute the most jobs and value-added Gross Regional Product in Greater Geelong include health care and social assistance, education and training, construction, retail trade and manufacturing.
Other Information

For the year ended 30 June 2020
COVID-19 impact on Council in 2019–20
To address the social and economic impacts of COVID-19 restrictions, Council approved support and recovery packages of over $10.8 million for the 2019–20 and 2020–21 financial years. It also adopted a COVID-19-hardship policy, to provide financial relief to businesses and individuals. 

To minimise the potential spread of COVID-19, many City facilities were closed a few days before government restrictions took effect, including libraries. Our Swim Sport and Leisure centres were also impacted in January with temporary closures due to air-quality concerns and this has been reflected in overall visitor participation rates. 

Despite the challenges, the majority of our services, including waste and recycling, road maintenance and community services, continued - with the delivery of some services modified to comply with restrictions. Our Maternal Child Health Services maintained participation rates, despite moving some appointments online. 

Where COVID-19 impacts have been identified, as affecting the indicators in this report, explanatory notes have been provided.

Basis for preparation

Council is required to prepare and include a performance statement within its annual report. The performance statement includes the results of the prescribed sustainable capacity, service performance and financial performance indicators and measures, together with a description of the municipal district and an explanation of material variations in the results. This statement has been prepared to meet the requirements of the Local Government Act (Vic) 1989 and Local Government (Planning and Reporting) Regulations 2014.
Where applicable, the results in the performance statement have been prepared on accounting bases consistent with those reported in the Financial Statements. The other results are based on information drawn from council information systems, or from third parties (e.g. Australian Bureau of Statistics).
The performance statement presents the actual results for the current year and for the prescribed financial performance indicators and measures, as forecast by the council’s strategic resource plan. The Local Government (Planning and Reporting) Regulations 2014 require explanation of any material variations in the results contained in the performance statement.
The forecast figures included in the performance statement are those adopted by council in its strategic resource plan on 25 June 2019, and which forms part of the council plan. The strategic resource plan includes estimates, based on key assumptions about the future that were relevant at the time of adoption and aimed at achieving sustainability over the long term. Detailed information on the actual financial results is contained in the General-Purpose Financial Statements. The strategic resource plan can be obtained by contacting council.

Sustainable capacity indicators
For the year ended 30 June 2020
	INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Population

	C1
	Expenses per head of population
[Total expenses / 
Population]
	$1,394.33
	$1,455.15
	$1,439.94
	$1,554.22
	The 2019–20 result has been impacted by several one-off expenses, including increased waste charges, higher asset write-offs and doubtful debts.

	C2
	Infrastructure per head of population
[Value of infrastructure / Population]
	$6,294.53
	$6,695.35
	$7,080.74
	$7,955.62
	The value of infrastructure assets has increased largely due to building revaluations and an increase in gifted assets.

	C3
	Population density per length of road
[Population / Kilometres of local roads]
	107.12
	110.26
	111.85
	112.28
	We add to our local road network every year, but the population is increasing at a faster rate than the local road network.

	Own-source revenue

	C4
	Own-source revenue per head of population
[Own source revenue / Population]
	$1,053.39
	$1,221.66
	$1,258.73
	$1,202.83
	

	Recurrent grants

	C5
	Recurrent grants per head of population
[Recurrent grants / Population]
	$264.72
	$232.62
	$236.45
	$229.83
	

	Disadvantage

	C6
	Relative Socio-Economic Disadvantage
[Index of Relative Socio-Economic Disadvantage by decile]
	5
	6
	6
	6
	Greater Geelong's SEIFA Index of Disadvantage in 2011 was in the lowest 50% in Victoria and in 2016 moved to the lowest 60% in Victoria. While this shows a more favourable state-wide comparison, the Index itself has shown no significant change, only moving from 993 in 2011 to 994 in 2016.

	Workforce turnover

	C7
	Percentage of staff turnover
[Number of permanent staff resignations and terminations / Average number of permanent staff for the financial year] x100
	8.8%
	10.9%
	8.8%
	8.9%
	Our turnover rate has remained steady over the past four years, except for 2017–18, when we had a higher than usual number of resignations.


Service performance indicators
For the year ended 30 June 2020
	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Aquatic Facilities

	AF6
	Utilisation

Utilisation of aquatic facilities
[Number of visits to aquatic facilities / Population]
	8.48
	8.36
	8.82
	6.53
	The utilisation of our aquatic facilities was impacted by:

· unfavourable weather during the 2019–20 summer season

· centre closures due to smoke haze from bushfires

· centre closures caused by COVID-19 restrictions.  

	Animal Management

	AM7
	Health and safety

Animal management prosecutions [Number of successful animal management prosecutions / Number of animal management prosecutions] x100
	New in 2020


	New in 2020


	New in 2020


	100%

	Animal management prosecutions presented to the Magistrates Court have increased over the past three years in proportion to the reported number of serious dog attacks. All 27 prosecutions heard this financial year were successfully prosecuted.  

Six additional prosecutions were postponed until 2020–21, due to COVID-19 restrictions.

	Food Safety 

	FS4
	Health and safety

Critical and major non-compliance outcome notifications
[Number of critical non-compliance outcome notifications and major non-compliance notifications about a food premises followed up / Number of critical non-compliance outcome notifications and major non-compliance notifications about a food premises] x100
	96.48%

	99.46%
	99.32%
	98.19%
	Despite slight variations, we have performed very well in this indicator since 2017. In the 2019 calendar year, only three notifications did not receive timely follow-up, as the businesses were not trading frequently.

	Governance

	G5
	Satisfaction

Satisfaction with council decisions
[Community satisfaction rating out of 100 with how council has performed in making decisions in the interest of the community]
	48
	53
	55
	56
	Our results reflect the sound decision-making by our current Council. In addition, live streaming of council meetings and community focus meetings continue to have a positive impact on our community.


	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Libraries

	LB4
	Participation

Active library members
[The sum of the number of active library borrowers in the last 3 financial years / The sum of the population in the last 3 financial years] x100
	19.28%
	18.17%
	18.20%
	17.57%
	The definition of this indicator changed in 2019–20 and now averages the past three years data. The result is therefore not comparable to past years. 

COVID-19 restrictions had a significant impact on collection use as Geelong Regional Library Corporation branches were closed from 19 March to 8 June, then opened to restricted hours and patron limits.

Note this indicator only measures collection item loans and doesn’t capture other library activity, such as events, programs, Wi-Fi use and in-library attendance. 

	Maternal and Child Health (MCH) 

	MC4
	Participation

Participation in the MCH service

[Number of children who attend the MCH service at least once (in the year) / Number of children enrolled in the MCH service] x100
	73.46%
	73.78%
	73.17%
	73.14%
	Moving some face-to-face services online to accommodate COVID-19 restrictions has had no obvious impact on participation rates.


	MC5
	Participation

Participation in the MCH service by Aboriginal children

[Number of Aboriginal children who attend the MCH service at least once (in the year) / Number of Aboriginal children enrolled in the MCH service] x100
	73.26%
	64.86%
	63.39%
	76.37%
	We have continued to build our partnership with the Wathaurong Aboriginal Co-operative to provide a place-based Maternal and Child Health service.

	Roads

	R5
	Satisfaction 

Satisfaction with sealed local roads
[Community satisfaction rating out of 100 with how council has performed on the condition of sealed local roads]
	47
	49
	54
	60
	Our Roads to Success in-house business improvement program, improved engagement and online interactive map of infrastructure projects has led to an increase in community satisfaction of 13 index points since 2017.


	SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Statutory Planning

	SP4
	Decision making

Council planning decisions upheld at VCAT
[Number of VCAT decisions that did not set aside council's decision in relation to a planning application / Number of VCAT decisions in relation to planning applications] x100
	61.54%
	68.00%
	64.00%
	54.17%
	In 2019–20, 13 of the 24 matters referred to VCAT were set aside. As only 2 per cent of total planning decisions were referred to VCAT, this is a very small proportion of planning decisions overall. Notably, there is no obvious pattern to the types of planning decisions being set aside. 

One appeal was postponed until 2020–21 due to COVID-19 restrictions.  

	Waste Collection

	WC5
	Waste diversion

Kerbside collection waste diverted from landfill
[Weight of recyclables and green organics collected from kerbside bins / Weight of garbage, recyclables and green organics collected from kerbside bins] x100
	56.32%
	54.75%
	54.00%
	55.73%
	Green waste and recycling ratios have been relatively consistent over the past few years. 

The growing population is increasing green organic and waste tonnage, but recycling tonnage has remained the same because of changes in product stream, newspapers and glass content.   




As part of the ongoing review and improvement of reporting, Local Government Victoria retired the following indicator:
	RETIRED

SERVICE/INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Animal Management

	AM4
	Health and safety 

Animal management prosecutions
[Number of successful animal management prosecutions]
	73.46%
	73.78%
	73.17%
	Retired in 2020
	As of 1 July 2019, this indicator was replaced by the amended Animal management prosecution measure AM7.


Financial performance indicators
For the year ended 30 June 2020
	DIMENSION/ INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	FORECASTS
	MATERIAL VARIATIONS AND COMMENTS

	
	
	
	
	
	2021
	2022
	2023
	2024
	

	Efficiency 

	E2
	Expenditure level

Expenses per property assessment
[Total expenses / Number of property assessments]
	$2,804.67
	$2,974.29
	$2,952.67
	$3,193.97
	$3,077.32 
	$3,164.58
	$3,254.59
	$3,327.88
	The 2019–20 result has been impacted by higher one-off expenses, but these costs are not expected to be recurring.


	E4
	Revenue level

Average rate per property

[Total rate revenue / Number of property assessments]
	New in 2020
	New in 2020
	New in 2020
	$1,602.56 
	$1,632.56 
	$1,675.27
	$1,723.69
	$1,773.94
	The average rate per property is forecast to grow from 2021 due to an expected increase in special rates and charges schemes.  

	Liquidity

	L1
	Working capital

Current assets compared to current liabilities
[Current assets / Current liabilities] x100
	147.35%
	145.35%
	155.09%
	112.69%
	152.95%
	101.84%
	109.69%
	93.99%
	Changes in our 2019–20 liquidity ratio are the result of newly adopted accounting standards, which have increased the value of our short-term liabilities.

Working capital is forecast to decrease from 2022 due to reduced cash balances.

	L2
	Unrestricted cash

Unrestricted cash compared to current liabilities
[Unrestricted cash / Current liabilities] x100
	122.64%
	115.02%
	118.83%
	75.68%
	134.32%
	83.82%
	92.08%
	76.49%
	Restricted cash, in the form of unspent conditional grants, increased in 2019–20. This decreased our overall percentage of unrestricted cash. 

Reduced cash balances and increasing current liabilities are forecast to impact this result in the future.

	Obligations

	O2

	Loans and borrowings

Loans and borrowings compared to rates
[Interest bearing loans and borrowings / Rate revenue] x100
	22.28%
	22.73%
	28.83%
	34.31%
	54.56%
	61.67%
	68.62%
	62.77%
	Our loan for $25 million was drawn down in May 2020, impacting this financial year’s result.  

Our forecast years reflect loans increasing to fund large capital projects, including the Civic Precinct.

	DIMENSION/ INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	FORECASTS
	MATERIAL VARIATIONS AND COMMENTS

	O3
	Loans and borrowings

Loans and borrowings repayments compared to rates
[Interest and principal repayments on interest bearing loans and borrowings / Rate revenue] x100
	5.70%
	5.06%
	4.70%
	4.34%
	5.50%
	6.56%
	7.73%
	8.06%
	Our forecast years reflect loans increasing to fund large capital projects, including the Civic Precinct.

	O4
	Indebtedness 

Non-current liabilities compared to own source revenue
[Non-current liabilities / Own source revenue] x100
	15.22%
	18.36%
	23.93%
	30.10%
	42.24%
	42.52%
	48.58%
	43.70%
	Our loan for $25 million was drawn down in May 2020, impacting this financial year’s result.  

Our forecast years reflect loans increasing to fund large capital projects, including the Civic Precinct.

	O5
	Asset renewal and upgrade 

Asset renewal and upgrade expense compared to depreciation
[Asset renewal and asset upgrade expenditure / Asset depreciation] x100
	New in 2020
	New in 2020
	New in 2020
	67.30%
	76.17%
	86.43%

	65.87%

	54.87%

	We have planned significant expenditure increases to fund asset renewal and upgrades in 2020–21 and 2021–22.

	Operating Position

	OP1
	Adjusted underlying result
Adjusted underlying surplus (or deficit)
[Adjusted underlying surplus (or deficit) / Adjusted underlying revenue] x100
	-3.54%
	1.99%
	5.38%
	-3.42%
	-0.24%
	8.36%
	6.91%
	7.63%
	COVID-19 has negatively impacted our service revenue. In addition, our community support and recovery packages have resulted in short-term deficits in 2019–20. While we expect these to carry over into 2020–21, we are forecasting a return to a surplus position from 2021–22.

	Stability

	S1
	Rates concentration
Rates compared to adjusted underlying revenue
[Rate revenue / Adjusted underlying revenue] x100


	64.45%
	58.93%
	59.50%
	61.87%
	64.15%
	59.58%
	62.22%
	62.26%
	

	DIMENSION/ INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	FORECASTS
	MATERIAL VARIATIONS AND COMMENTS

	S2
	Rates effort
Rates compared to property values
[Rate revenue / Capital improved value of rateable properties in the municipality] x100
	0.40%
	0.41%
	0.36%
	0.33%
	0.33%
	0.35%
	0.37%
	0.38%
	


As part of the ongoing review and improvement of reporting, Local Government Victoria retired the following indicators:
	RETIRED
DIMENSION/ INDICATOR/MEASURE
	RESULTS 2017
	RESULTS 2018
	RESULTS 2019
	RESULTS 2020
	MATERIAL VARIATIONS AND COMMENTS

	Efficiency

	E1
	Revenue level 

Average residential rate per residential property assessment
[Residential rate revenue / Number of residential property assessments]
	$1,487.58
	$1,525.79
	$1,585.94
	Retired in 2020

	As of 1 July 2019, this measure was replaced by E4.


	Obligations

	O1
	Asset renewal 

Asset renewal compared to depreciation
[Asset renewal expense / Asset depreciation] x100]
	52.03%
	47.55%
	50.36%
	Retired in 2020


	As of 1 July 2019, this measure was replaced by O5.



CERTIFICATION OF THE PERFORMANCE STATEMENT
[image: image50.png]In my opinion, the accompanying performance statement has been prepared in accordance with the Local
Govemment Act (Vi) 1989 and the Local Govemement (Planning and Reporting) Regulations 2014.

[y
Raren Glesicky GPA
Princpal Actauning Offcer
Dated & Sepember 2020

n our opinion, the accompanying performance statement of The City of Greater Geelong forthe year ended 30
June 2020 presents fairly the resuts of counci's performance, n accordance with the Local Government Act (Vic)
199 and the Local Governement (Planning and Reporing) Regulatons 2014.

“The performance statement contains the relevant performance indicators, measures and results i relaion fo
senvice performance, financia performance and sustainable capabilty.

At the date of signing, we are not aware of any circumstances that would render any paricuars i the performance.
Statement to be misieading or inaccurat.

We have been authorised by the Greater Geslong City Council and by the Local Govemement (Planning and
Reporting) Regulations 2014 to cerly ths performanc statement i s fnal form.

[ St tdar

CrStepnanie Asner
Mayor
Dated: & September 2020

(o
Cniony A
Counciar
Doted: September 2020

Wartn Cufter
Chief Execuive Offcer
Dated: & September 2020



 

Independent auditor’s report of the Performance Statement 2019–20

[image: image51.png]Independent Auditor’s Report Victorian Auditor-General

VAGO

To the Councillors of the City of Greater Geelong

Opinion.

asisfor Opnion.

responsibilesfor the
performance

responsibilesfor the
auditof the

1 have auited the accompanying performance satement ofthe Cit of
Greater Geelong(the councl) which compriss the:

* descipton o municipaty for the year ended 30 une 2020
* sustainabl capacity indicators fo the year ended 30 June 2020
+ service performnce ndictorsfo theyear ended 30 June 2020
+ financial performance indcators orthe year ended 30 June 2020
+ otherinformation nd

* the certifcation ofthe prformancestatement.

' my opinion, the performance statement pesents ar, i 3l material
respects,the performanc of the counci forthe year ended 30 June 2020 in
‘accordance withthe performance reporting requirements of Pat 6 of the
Local Government Act 1985.

1 have conducted my audit inaccordance with the Audt Act 1994 which
incorporates the AustraianStandards on Assurance Engagements. further
escibe my responsiiltes under that Act and those standards n the
Audito's Responsiilte orthe Audit oftheperformance tatement secton
of my report.

My independence i etablished by the Consttution Act 1975.1 and my staff
are independent of the counci in ccordance with the ethical requiemens of
the AccountingProfessional and Etica Standards Board's APES 110 Code of
Ethic forProfessional Accountonts the Code) that ae rlevant o my audt of
the performance satement i Victora and hav also ufiled our other thical
responsiiltes i accordance with the Code.

| blieve that the sudit evidence | have obtined s suficent and approprite
o prvide 3 basi for my opinion.

“The Councilors are resporsioe for the reparaton and falfpresentaton of
the performance sttement insccorcance with the performance reportng
requirements of the Loca Government Act 1989 and or such nterna control
asthe Councllors determines s necessaryto enabe thepreparation and fir
presentation of th satement of performance that s freefrom material
misstatement, whether due to fraud or eror

s required by the Auit Act 1994,y responsibilty s to xpress an opinion
‘onthe performance satement based onthe aucit. My objectives for th aucit
are o obtan ressonable assurance sbout whethr the peformance
statement 55 3 whole i fre from material misstatement,whether due to
fraud or eror, and o ssue an aucitorsreport tht ncuds my opirion
Reasonable assurances  igh evel of ssurance,but s ot a guarantee that
an audit conducted in accordance with the Austraan Standards on Assurnce
Engagements willahways dtect a materal mistatement when F exsts.

Lol 31 /35 Colins Sost,Malbourre Vi 3000
T 038601 7000 snciss@oudtic govou wmsoudisicgony




[image: image52.png]issatements can aricefromfraud orsror and are considered materal ,
ndividally o inthe geregate,they couid ressonably b expected to
infiuence the ceciionsof users tsken on the bsis o i performance.

25 partof an auditin accordance with the Australian Sandards on Assurance
Engagements | execiseprofessions judgement and maintain professional
scepticim throughou the aud. |3k

* idencity and asses the isks of materal misstatement of performance
statemens, whsther dus to fraud or errr,design snd perform it
procecuresresponsive to those isks, and obtan audt evidence tht s
suffcient and appropriatetoprovide  bass formy opirion Theriskof
ot detecting  mteris miststement reufting from frud = igher
han forone resuiingfrom errr, 2 fraud may involve colluson,
forgery, intentional omission, misrepresentations, o the override of
incemalcontro.

* obtain an understanding of inemal contrl reevant o the auditin
order to design audit procedures that ae appropriae nthe
‘ircumstances, butnot for the purpose of xpressig an opiion onthe.
ffectiveness ofthe counci intamal control

* cvalate the cveral prsentation, sructure and content of the
performance statement, inciding the discesures, and whether
performance statement represants the underlying events and resus in
‘2 manner that achieves i pesentation.

1 communicate withthe Counilors regarding, among other mateers,the
planned scope snd timingof the st and sgnficant sudit inding, ncuding
any sgnficant deficencies inintemal control that | ety during my U

MELBOURNE Sankhu Chuinimar
14 Seprember 2020 s dlegatefor the Auditor-Generalof icoria




CONTACT US
This document contains important information about the City of Greater Geelong. Please contact us if you have any questions or would like to request a hard copy of the report. 
Under normal circumstances, you can also view hard copies at our customer service centres and branches of the Geelong Regional Library Corporation. However, please be aware these services may be impacted by COVID-19 restrictions.
City of Greater Geelong
PO Box 104
Geelong VIC 3220
P: 5272 5272

E: contactus@geelongcity.vic.gov.au
www.geelongaustralia.com.au


Latest news:
 
  @CityofGreaterGeelong

 
 @GreaterGeelong
 
   @GreaterGeelong

 
 @GreaterGeelong
Council plan overall progress result 


33.8 per cent (44) of all initiatives were completed, and a further 46.9 per cent (61) are on track.








Council plan overall progress result 


33.8 per cent (44) of all initiatives were completed, and a further 46.9 per cent (61) are on track.








Major initiative progress results


50 per cent (7) of major initiatives were completed, and a further 35.7 per cent (5) are on track.








Other initiative progress result


31.9 per cent (37) of other initiatives were completed, and a further 48.3 per cent (56) are on track. 











� The appointment of the monitors was made in accordance with section 223CA of the Local Government Act (Vic) 1989.


� As at 30 June 2020


� Excludes casual employees





19

_1662916929.xls
Chart1

		2016–17

		2017–18

		2018–19

		2019–20



Investments

103

102.6

105.5

103.4



Sheet1

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Surplus/(Deficit)		76.3		57.6		46.2		76.0		125.3		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Comprehensive Results		73.7		64.6		66.0		217.5		156.3		251.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Assets		2,123.4		2,180.5		2,236.0		2,471.5		2,667.8		2,962.6

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Investments		91.9		87.2		103.0		102.6		105.5		103.4

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Capital Program		106.7		84.2		76.9		113.3		124.5		122.9

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Liabilities		135.7		128.2		117.7		135.7		157.6		201.3

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Loans		64.5		54.8		45.5		48.7		65.8		82.6

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Debt commitment		6.88		6.49		5.70		5.06		4.60		4.8

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Ratepayer equity		1,987.7		2,052.3		2,118.3		2,335.8		2,492.1		2,761.2





Sheet1

		



Total Assets



		



Investments



		



Capital Program



		



Total Liabilities



		



Loans



		



Debt commitment



		



Ratepayer equity



		



Surplus/(Deficit)



		



Total Comprehensive Results




_1662916931.xls
Chart1

		2016–17

		2017–18

		2018–19

		2019–20



Total Comprehensive Results

66

217.5

156.3

251



Sheet1

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Surplus/(Deficit)		76.3		57.6		46.2		76.0		125.3		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Comprehensive Results		73.7		64.6		66.0		217.5		156.3		251.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Assets		2,123.4		2,180.5		2,236.0		2,471.5		2,649.7		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Investments		91.9		87.2		103.0		102.6		105.5		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Capital Program		106.7		84.2		76.9		113.3		124.5		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Liabilities		135.7		128.2		117.7		135.7		157.6		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Loans		64.5		54.8		45.5		48.7		65.8		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Debt commitment		6.88		6.49		5.70		5.06		4.60		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Ratepayer equity		1,987.7		2,052.3		2,118.3		2,335.8		2,492.1		85.0





Sheet1

		



Total Assets



		



Investments



		



Capital Program



		



Total Liabilities



		



Loans



		



Debt commitment



		



Ratepayer equity



		



Surplus/(Deficit)



		



Total Comprehensive Results




_1662916923.xls
Chart1

		2016–17

		2017–18

		2018–19

		2019–20



Total Liabilities

117.7

135.7

157.6

201.3



Sheet1

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Surplus/(Deficit)		76.3		57.6		46.2		76.0		125.3		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Comprehensive Results		73.7		64.6		66.0		217.5		156.3		251.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Assets		2,123.4		2,180.5		2,236.0		2,471.5		2,667.8		2,962.6

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Investments		91.9		87.2		103.0		102.6		105.5		103.4

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Capital Program		106.7		84.2		76.9		113.3		124.5		122.9

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Liabilities		135.7		128.2		117.7		135.7		157.6		201.3

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Loans		64.5		54.8		45.5		48.7		65.8		82.6

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Debt commitment		6.88		6.49		5.70		5.06		4.60		4.8

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Ratepayer equity		1,987.7		2,052.3		2,118.3		2,335.8		2,492.1		2,761.2





Sheet1

		



Total Assets



		



Investments



		



Capital Program



		



Total Liabilities



		



Loans



		



Debt commitment



		



Ratepayer equity



		



Surplus/(Deficit)



		



Total Comprehensive Results




_1662916926.xls
Chart1

		2016–17

		2017–18

		2018–19

		2019–20



Capital Program

76.9

113.3

124.5

122.9



Sheet1

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Surplus/(Deficit)		76.3		57.6		46.2		76.0		125.3		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Comprehensive Results		73.7		64.6		66.0		217.5		156.3		251.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Assets		2,123.4		2,180.5		2,236.0		2,471.5		2,667.8		2,962.6

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Investments		91.9		87.2		103.0		102.6		105.5		103.4

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Capital Program		106.7		84.2		76.9		113.3		124.5		122.9

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Liabilities		135.7		128.2		117.7		135.7		157.6		201.3

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Loans		64.5		54.8		45.5		48.7		65.8		82.6

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Debt commitment		6.88		6.49		5.70		5.06		4.60		4.8

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Ratepayer equity		1,987.7		2,052.3		2,118.3		2,335.8		2,492.1		2,761.2





Sheet1

		



Total Assets



		



Investments



		



Capital Program



		



Total Liabilities



		



Loans



		



Debt commitment



		



Ratepayer equity



		



Surplus/(Deficit)



		



Total Comprehensive Results




_1662916921.xls
Chart1

		2016–17

		2017–18

		2018–19

		2019–20



Ratepayer equity

2118.3

2335.8

2492.1

2761.2



Sheet1

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Surplus/(Deficit)		76.3		57.6		46.2		76.0		125.3		85.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Comprehensive Results		73.7		64.6		66.0		217.5		156.3		251.0

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Assets		2,123.4		2,180.5		2,236.0		2,471.5		2,667.8		2,962.6

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Investments		91.9		87.2		103.0		102.6		105.5		103.4

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Capital Program		106.7		84.2		76.9		113.3		124.5		122.9

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Total Liabilities		135.7		128.2		117.7		135.7		157.6		201.3

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Loans		64.5		54.8		45.5		48.7		65.8		82.6

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Debt commitment		6.88		6.49		5.70		5.06		4.60		4.8

				2014–15		2015–16		2016–17		2017–18		2018–19		2019–20

		Ratepayer equity		1,987.7		2,052.3		2,118.3		2,335.8		2,492.1		2,761.2





Sheet1

		



Total Assets



		



Investments



		



Capital Program



		



Total Liabilities



		



Loans



		



Debt commitment



		



Ratepayer equity



		



Surplus/(Deficit)



		



Total Comprehensive Results




